Annex No. 5

| Milestone | Action | Action description | Completion deadline | Payment schedule |
| --- | --- | --- | --- | --- |
| 1 | Acceptance of the Site: | means the moment when the Client hands over the Site to the Contractor and the Contractor takes over the Site from the Client; | at latest within 7 calendar days from delivery of the Client’s written request to commence performance under Art. 3.1.1 of the Agreement | ----------------- |
| 2 | Commencement of Work: | means the moment when the Contractors commences performance of the Work | at latest within 14 calendar days from takeover of the Site, unless agreed otherwise in writing | Payment of 40% of the Price for the given work item (given store) after delivery of the panels/inverters, DC distributors / supporting structure and commencement of installation (at the given store) under Annex No. 12 to the Agreement |
| 3 | Performance of Work: | means the moment when the Contractor completes all construction works on the Work and duly demonstrates that the Work is fully functional as a whole | at latest within 4 weeks from the date of takeover of the Site, unless agreed otherwise in writing (to be completed by the participant based on their bid. The Contracting Authority requires the period of work implementation to be maximally 8 weeks from the date of takeover of the Site.) | ----------------- |
| 4 | Procurement of official approval: | means the moment when the approval and/or other consent required for the use of the Work comes into legal force, and if does not come into legal force, then when it becomes effective | no later than 21 days after the date after the performance of the Work pursuant to Milestone 3 | Payment of 25% of the price of the relevant item of Work (relevant store) as per Annex No. 12 to the Contract. |
| 5 | Procurement of the approval of the distributor and first parallel connection: | means procuring a consenting opinion for the connection of the PV plant by the entity authorised to issue such consent and after the first parallel connection to the distribution grid | no later than 30 days after the date after the performance of the Work pursuant to Milestone 3 | ----------------- |
| 6 | Handover of the Work to the Client: | has the meaning set forth in Art. 5.1.1 of this Contract. | no later than the 3rd day after obtaining the distributor’s consent and the first parallel connection to the distribution grid according to Milestone No. 5 | Payment of 35% of the price of the relevant item of Work (relevant store) as per Annex No. 12 to the Contract. |

Schedule for Work performance - applicable to each individual item of Work (individual store)

The Client shall send a written invitation to the Contractor to commence performance of the relevant item of Work (relevant store)