## List1
|  |  | Latest milestone deadlines | Calendar months / y. |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | (to be corrected as contract gets in force "0")
|  |  |  | From day "0" (months) |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | Notes
Item | Activity |  |  | Start | Stop
0 | Contract in force - Signing of the Contract for Work (day "0") / * (First payment invoice, Performance Security) | AIB |  | 0
|  | Contractor |  | 0
1 | Kick off meeting | AIB |  | 0.25 | 0.5
Contractor
2 | Freezing of layout / * | AIB | 2024-09-15 | 1.25
Contractor
3 | Basic information (Final TOP data for all medias. Preliminary (80 % final) of load data, conduits/channels for media/electric dimensions - connected to civil works as needed for general designer for building engineering and authority approval process) / * | AIB | 2024-09-22 | 1.5
Contractor
4 | Document for construction readiness (Final load data, equipment dimension drawings, cable/media channels, conduits connected to civil works) / * , ** | AIB | 2024-10-20 | 2.5
Contractor
5 | Basic engineering | AIB |  | 0.25 | 4
Contractor
6 | Basic engineering (completion) / * , ** | AIB | 2024-11-30 | 4
Contractor
7 | Detail engineering | AIB |  | 5 | 9
Contractor
8 | Document for the installation of the Equipment (base for AIB tendering of site installation) / * , ** | AIB | 2025-04-30 | 9
Contractor
9 | Detail engineering (completion) / * | AIB | 2025-04-30 | 9
Contractor
10 | Ordering of long lead items, Workshop manufacturing (including min. 3 AIB workshop inspections) | AIB |  | 4 | 17
Contractor
11 | Inhouse testing (pre-assemby at workshop, system integration test - with AIB participation) | AIB |  | 18 | 21
Contractor
12 | Delivery to site (as per need / several lots) Confirmed in writing by the Customer | AIB |  | 22 | 22
Contractor
13 | Delivery to site completed / * , ** | AIB | 2026-06-15 | 22
Contractor
14 | Equipment installation with supervision | AIB |  | 23 | 25.5
Contractor
15 | Cold commissioning | AIB |  | 25.5 | 26
Contractor
16 | Start-up and Hot Commissioning / 1 | AIB |  | 26 | 26.5
Contractor
17 | Finished hot commissioning / * , ** | AIB | 2026-09-18 | 26.5
Contractor
18 | Initial operation test | AIB |  | 26.5 | 27
Contractor
19 | Performance tests / 2 | AIB |  | 28 | 29
Contractor
20 | Project Closing Certificate / * , ** | AIB | 2026-12-31 | 29
Contractor
21 | Final performance tests / 3 | AIB |  | 30
Contractor
22 | Post-Warranty Control Certificate / * | AIB
Contractor
Legend:
/ * = Milestone
/ ** = Connected to delay penalty
/ 1: Initial Operation Tests
/ 2: Test of stable operation
/ 3: Acceptance test
AIB proposal
Contractor proposal