## Gantt chart
Type | Name of the activity | Start | End | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026
|  |  |  | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII.
A1 | Public procurement and project management | 2020-03-05 | 2024-09-14
M1 | Launch of tender for construction works |  | 2021-03-19 | [14 empty] | M1
M2 | Launch of tender for construction supervision services |  | 2022-01-12 | [24 empty] | M2
M3 | Launch of tender for authorial supervision services |  | 2022-01-07 | [24 empty] | M3
M4 | Signature of the authorial supervision contract |  | 2022-02-08 | [25 empty] | M4
M5 | Signature of the construction works contract |  | 2022-03-28 | [26 empty] | M5
M6 | Signature of the construction supervision contract |  | 2022-08-30 | [31 empty] | M6
M7 | Approval of the communication plan |  | 2021-08-31 | [19 empty] | M7
M17 | Final event organised |  | 2024-09-14 | [56 empty] | M17
A2 | Construction supervision and authorial supervision | 2022-08-02 | 2025-03-11
M8 | Launch of authorial supervision |  | 2022-08-02 | [31 empty] | M8
M9 | Launch of construction supervision |  | 2022-08-31 | [31 empty] | M9
M10 | Submission of an interim report on the construction supervision |  | 2022-11-01 | [34 empty] | M10
M11 | Submission of an interim report on the construction supervision |  | 2023-04-01 | [39 empty] | M11
M12 | Completion of the construction supervision and authorial supervision |  | 2025-03-11 | [62 empty] | M12
A3 | Construction works | 2022-08-12 | 2024-09-11
M13 | Launch of construction works |  | 2022-08-12 | [31 empty] | M13
M14 | Relocation of unpaved field road |  | 2024-09-11 | [56 empty] | M14
M15 | Retaining wall, in the vicinity of track no.1 (railway km 281.605 - 282.080) |  | 2024-09-11 | [56 empty] | M15
M16 | Completion of construction works |  | 2024-09-11 | [56 empty] | M16