## Gantt chart
Type | Name of the activity | Start | End | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024
|  |  |  | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII.
A1 | Preliminary and detailed/executive design | 2019-12-05 | 2024-12-31
M1 | Preparation of design docuentation for territorial decision(s) (preliminary design) started |  | 2019-12-05 | [35 empty] | M1
M2 | Design documentation for territorial decision(s) (preliminary desig) prepared |  | 2023-07-26 | [78 empty] | M2
M3 | Territiorial decision(s) issued |  | 2024-03-27 | [86 empty] | M3
M4 | Preparation of design documentation for building permits and construction execution |  | 2023-09-30 | [80 empty] | M4
M5 | Draft design documentation for building permits and construction execution |  | 2024-04-29 | [87 empty] | M5
M6 | Approval decision of Ministry of Transport to Design documentation for building permits and construction execution (detailed/executive design) issued |  | 2024-07-11 | [90 empty] | M6
M7 | Application for first building permit submitted |  | 2024-07-31 | [90 empty] | M7
M8 | First building permit issued |  | 2024-08-31 | [91 empty] | M8
M9 | Last building permit issued |  | 2024-12-31 | [95 empty] | M9
A2 | Project management and public procurement | 2017-02-07 | 2024-12-31
M10 | Public procurement procedure for design contractor published |  | 2018-04-14 | [15 empty] | M9
M11 | EIA opinion issued |  | 2018-03-08 | [14 empty] | M11
M12 | Kick of meeting organised |  | 2018-02-15 | [13 empty] | M12
M13 | Communication plan approved |  | 2018-06-28 | [17 empty] | M13
M14 | Contract signed for design |  | 2019-11-19 | [34 empty] | M14
M15 | Final meeting organised |  | 2024-12-31 | [95 empty] | M15