## ALSE
LEGENDA
[9 empty] | Foundation check | [6 empty] | Installation phase | [7 empty] | Initial operation test | [5 empty] | ALINVEST SCHEDULE FOR INSTALLATION and COMMISSIOING PRELIMINARY MANPOWER HISTOGRAMM (ONLY FOR REFERENCE)
[9 empty] | Shipping & Unloading | [6 empty] | Cold Commissioning phase | [7 empty] | Performance test
UPDATED: | 2025-11-17 | [7 empty] | Training | [6 empty] | Hot commissioning phase | [7 empty] | Project Closing Certificate
Rev. |  | 02
| Weeks 2026 | [83 empty] | Weeks 2027
| 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49 |  | 50 |  | 51 |  | 52 |  | 53 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5
LINE 1+2
LINE 3+4
EQUIPMENT | time axis 2026-03-16 to 2027-02-07
| FOUNDATIONS CHECK for 4 LINES | [41 empty] | SUMMER HOLIDAYS | [37 empty] | WINTER HOLIDAYS
Foundations check | bar: 2026-03-16 to 2026-03-29
LINE 1+2
SHIPPING and UNLOADING | bar: 2026-04-27 to 2026-07-12
START INSTALLATION | bar: 2026-05-04 to 2026-05-10
Positioning caster base frame | bar: 2026-05-10 to 2026-05-11
Assembly and positioning downstream frame | bar: 2026-05-11
Assembly of accessories | bar: 2026-05-17
Positioning stands and transverse beams and Positioning top of caster hydraulic buffer | bar: 2026-05-17 to 2026-05-18
Mandrel positioning | bar: 2026-05-24
Positioning roll change device and bottom roll motor | bar: 2026-05-24 to 2026-05-25
Axis alignment | bar: 2026-05-25 to 2026-05-31
Starting of anchor bolts fixing | bar: 2026-05-31
Cabinets | bar: 2026-05-18
Cabke pulling | bar: 2026-05-24 to 2026-05-25
Electrician activities | bar: 2026-05-24 to 2026-07-26
Concrete embedding of bolts | bar: 2026-05-31 to 2026-06-01; 2026-06-15 to 2026-06-21; 2026-07-06 to 2026-07-12
Positioning of tip table and idle roll | bar: 2026-06-01 to 2026-06-07
Auto start up pivoting box and assembly P02 pivoting pulpit | bar: 2026-06-07
Edge miller-pinch roll-shear-coil car slides-coil-deflector roll | bar: 2026-06-07 to 2026-06-14
Positioning motorization group-spindle support-spindle | bar: 2026-06-14 to 2026-06-21
Positioning hydraulic units and manifolds | bar: 2026-06-21
Level control actuator | bar: 2026-06-21 to 2026-06-22
Degasser, CFF and launder positioning + start up | bar: 2026-06-22 to 2026-06-28
Water skids-Water heater-Water circuit | bar: 2026-06-22 to 2026-06-29
Pulpits | bar: 2026-06-29
Hydraulic circuit | bar: 2026-06-29 to 2026-07-12
Hydraulic circuit flushing | bar: 2026-06-29 to 2026-07-05
Graphite system-Spray bars | bar: 2026-07-06 to 2026-07-12
Scan gauge system-pneumatic circuit + start up | bar: 2026-07-12
Safety fences | bar: 2026-07-13 to 2026-07-19
Chips exaust system | bar: 2026-07-13 to 2026-07-19
The cold and hot commissioning will start ONLY with energy - oil - compressed air - water available
Cold Commissioning: I/O test | bar: 2026-07-20 to 2026-07-27
Cold Commissioning: Sofware check | bar: 2026-07-27 to 2026-08-09
Cold Commissioning: General function | bar: 2026-08-03 to 2026-08-09
Hot Commissioning | bar: 2026-08-24 to 2026-08-30
Initial Operation test | bar: 2026-08-31 to 2026-09-20
Performance test | bar: 2026-09-21 to 2026-11-15
Training | bar: 2026-08-24 to 2026-09-06; 2026-10-05 to 2026-10-18
Project Closing certificate | bar: 2027-01-25 to 2027-01-31
All the above dates refer to the use of specialized personnel as per our instructions
LINE 3+4
SHIPPING and UNLOADING | bar: 2026-06-29 to 2026-09-13
START INSTALLATION | bar: 2026-07-06 to 2026-07-12
Positioning caster base frame | bar: 2026-07-12 to 2026-07-13
Assembly and positioning downstream frame | bar: 2026-07-13
Assembly of accessories | bar: 2026-07-19
Positioning stands and transverse beams and Positioning top of caster hydraulic buffer | bar: 2026-07-19 to 2026-07-20
Mandrel positioning | bar: 2026-07-26
Positioning roll change device and bottom roll motor | bar: 2026-07-26 to 2026-07-27
Axis alignment | bar: 2026-07-27 to 2026-08-02
Starting of anchor bolts fixing | bar: 2026-08-02
Cabinets | bar: 2026-07-20
Cabke pulling | bar: 2026-07-26 to 2026-07-27
Electrician activities | bar: 2026-07-26 to 2026-09-27
Concrete embedding of bolts | bar: 2026-08-02 to 2026-08-03; 2026-08-17 to 2026-08-23; 2026-09-07 to 2026-09-13
Positioning of tip table and idle roll | bar: 2026-08-03 to 2026-08-09
Auto start up pivoting box and assembly P02 pivoting pulpit | bar: 2026-08-09
Edge miller-pinch roll-shear-coil car slides-coil-deflector roll | bar: 2026-08-09 to 2026-08-16
Positioning motorization group-spindle support-spindle | bar: 2026-08-16 to 2026-08-23
Positioning hydraulic units and manifolds | bar: 2026-08-23
Level control actuator | bar: 2026-08-23 to 2026-08-24
Degasser, CFF and launder positioning + start up | bar: 2026-08-24 to 2026-08-30
Water skids-Water heater-Water circuit | bar: 2026-08-24 to 2026-08-31
Pulpits | bar: 2026-08-31
Hydraulic circuit | bar: 2026-08-31 to 2026-09-13
Hydraulic circuit flushing | bar: 2026-08-31 to 2026-09-06
Graphite system-Spray bars | bar: 2026-09-07 to 2026-09-13
Scan gauge system-pneumatic circuit + start up | bar: 2026-09-13
Safety fences | bar: 2026-09-14 to 2026-09-20
Chips exaust system | bar: 2026-09-14 to 2026-09-20
The cold and hot commissioning will start ONLY with energy - oil - compressed air - water available
Cold Commissioning: I/O test | bar: 2026-09-21 to 2026-09-28
Cold Commissioning: Sofware check | bar: 2026-09-28 to 2026-10-11
Cold Commissioning: Training | bar: 2026-10-05 to 2026-10-11
Hot Commissioning | bar: 2026-10-12 to 2026-10-18
Initial Operation test | bar: 2026-10-19 to 2026-11-08
Performance test | bar: 2026-11-09 to 2026-12-20; 2027-01-04 to 2027-01-24
Training | bar: 2026-10-12 to 2026-10-25; 2026-11-23 to 2026-12-06
Project Closing certificate | bar: 2027-01-25 to 2027-01-31
All the above dates refer to the use of specialized personnel as per our instructions
FOUNDATIONS CHECK for 4 LINES | 2026-03-16: Weeks 2026; 2027-01-04: Weeks 2027
AIB MECHANICAL MANPOWER | 2026-03-16: 12; 2026-03-23: 13; 2026-03-30: 14; 2026-04-06: 15; 2026-04-13: 16; 2026-04-20: 17; 2026-04-27: 18; 2026-05-04: 19; 2026-05-11: 20; 2026-05-18: 21; 2026-05-25: 22; 2026-06-01: 23; 2026-06-08: 24; 2026-06-15: 25; 2026-06-22: 26; 2026-06-29: 27; 2026-07-06: 28; 2026-07-13: 29; 2026-07-20: 30; 2026-07-27: 31; 2026-08-03: 32; 2026-08-10: 33; 2026-08-17: 34; 2026-08-24: 35; 2026-08-31: 36; 2026-09-07: 37; 2026-09-14: 38; 2026-09-21: 39; 2026-09-28: 40; 2026-10-05: 41; 2026-10-12: 42; 2026-10-19: 43; 2026-10-26: 44; 2026-11-02: 45; 2026-11-09: 46; 2026-11-16: 47; 2026-11-23: 48; 2026-11-30: 49; 2026-12-07: 50; 2026-12-14: 51; 2026-12-21: 52; 2026-12-28: 53; 2027-01-04: 1; 2027-01-11: 2; 2027-01-18: 3; 2027-01-25: 4; 2027-02-01: 5
Foreman | bar: 2026-03-16; 2026-03-23
Helpers | bar: 2026-03-16; 2026-03-23
BP TECHNICIANS
Site manager | bar: 2026-03-16; 2026-03-23
TOTAL: | 2026-03-16: 3; 2026-03-23: 3; 2026-03-30: 0; 2026-04-06: 0; 2026-04-13: 0; 2026-04-20: 0; 2026-04-27: 0; 2026-05-04: 0; 2026-05-11: 0; 2026-05-18: 0; 2026-05-25: 0; 2026-06-01: 0; 2026-06-08: 0; 2026-06-15: 0; 2026-06-22: 0; 2026-06-29: 0; 2026-07-06: 0; 2026-07-13: 0; 2026-07-20: 0; 2026-07-27: 0; 2026-08-03: 0; 2026-08-10: 0; 2026-08-17: 0; 2026-08-24: 0; 2026-08-31: 0; 2026-09-07: 0; 2026-09-14: 0; 2026-09-21: 0; 2026-09-28: 0; 2026-10-05: 0; 2026-10-12: 0; 2026-10-19: 0; 2026-10-26: 0; 2026-11-02: 0; 2026-11-09: 0; 2026-11-16: 0; 2026-11-23: 0; 2026-11-30: 0; 2026-12-07: 0; 2026-12-14: 0; 2026-12-21: 0; 2026-12-28: 0; 2027-01-04: 0; 2027-01-11: 0; 2027-01-18: 0; 2027-01-25: 0; 2027-02-01: 0 | 0
LINE 1+2 | 2026-03-16: Weeks 2026; 2027-01-04: Weeks 2027
AIB MECHANICAL MANPOWER | 2026-03-16: 12; 2026-03-23: 13; 2026-03-30: 14; 2026-04-06: 15; 2026-04-13: 16; 2026-04-20: 17; 2026-04-27: 18; 2026-05-04: 19; 2026-05-11: 20; 2026-05-18: 21; 2026-05-25: 22; 2026-06-01: 23; 2026-06-08: 24; 2026-06-15: 25; 2026-06-22: 26; 2026-06-29: 27; 2026-07-06: 28; 2026-07-13: 29; 2026-07-20: 30; 2026-07-27: 31; 2026-08-03: 32; 2026-08-10: 33; 2026-08-17: 34; 2026-08-24: 35; 2026-08-31: 36; 2026-09-07: 37; 2026-09-14: 38; 2026-09-21: 39; 2026-09-28: 40; 2026-10-05: 41; 2026-10-12: 42; 2026-10-19: 43; 2026-10-26: 44; 2026-11-02: 45; 2026-11-09: 46; 2026-11-16: 47; 2026-11-23: 48; 2026-11-30: 49; 2026-12-07: 50; 2026-12-14: 51; 2026-12-21: 52; 2026-12-28: 53; 2027-01-04: 1; 2027-01-11: 2; 2027-01-18: 3; 2027-01-25: 4; 2027-02-01: 5
Foreman | bar: 2026-04-27; 2026-05-04; 2026-05-11; 2026-05-18; 2026-05-25; 2026-06-01; 2026-06-08; 2026-06-15; 2026-06-22; 2026-06-29; 2026-07-06; 2026-07-13; 2026-07-20; 2026-07-27; 2026-08-03; 2026-08-24; 2026-08-31; 2026-09-07
Assembler junior | 2026-04-27: 1; 2026-05-04: 3; 2026-05-11: 3; 2026-05-18: 3; 2026-05-25: 3; 2026-06-01: 4; 2026-06-08: 4; 2026-06-15: 4; 2026-06-22: 4; 2026-06-29: 4; 2026-07-06: 3; 2026-07-13: 2; 2026-07-20: 1; 2026-07-27: 1; 2026-08-03: 1
Assembler senior | 2026-04-27: 1; 2026-05-04: 3; 2026-05-11: 1; 2026-05-18: 1; 2026-05-25: 1; 2026-06-01: 2; 2026-06-08: 3; 2026-06-15: 3; 2026-06-22: 3; 2026-06-29: 3; 2026-07-06: 3; 2026-07-13: 3; 2026-07-20: 3; 2026-07-27: 2; 2026-08-03: 2
Technician specialized in machine alignment | bar: 2026-05-18; 2026-05-25; 2026-06-01
Construction worker | bar: 2026-05-25; 2026-06-15; 2026-07-06
Hydraulic technician | 2026-05-18: 2; 2026-05-25: 3; 2026-06-01: 4; 2026-06-08: 4; 2026-06-15: 4; 2026-06-22: 4; 2026-06-29: 4; 2026-07-06: 4; 2026-07-13: 2; 2026-07-20: 2; 2026-07-27: 2
Assembler senior Welder | bar: 2026-05-18; 2026-05-25; 2026-06-01; 2026-06-08; 2026-06-15; 2026-06-22; 2026-06-29; 2026-07-06; 2026-07-13; 2026-07-20
Helpers | 2026-04-27: 1; 2026-05-04: 4; 2026-05-11: 4; 2026-05-18: 5; 2026-05-25: 5; 2026-06-01: 4; 2026-06-08: 5; 2026-06-15: 5; 2026-06-22: 5; 2026-06-29: 4; 2026-07-06: 3; 2026-07-13: 2; 2026-07-20: 2; 2026-07-27: 1
AIB ELECTRICAL MANPOWER
Electrician technician | 2026-05-18: 2; 2026-05-25: 2; 2026-06-01: 4; 2026-06-08: 5; 2026-06-15: 5; 2026-06-22: 5; 2026-06-29: 4; 2026-07-06: 4; 2026-07-13: 3; 2026-07-20: 3; 2026-07-27: 2; 2026-08-03: 2; 2026-08-24: 2; 2026-08-31: 1; 2026-09-07: 1
Helpers | 2026-05-18: 4; 2026-05-25: 4; 2026-06-01: 2; 2026-06-08: 1; 2026-06-15: 1; 2026-06-22: 1; 2026-06-29: 1; 2026-07-06: 1; 2026-07-13: 1; 2026-07-20: 1; 2026-07-27: 1; 2026-08-03: 1; 2026-08-24: 1; 2026-08-31: 1; 2026-09-07: 1
AIB OPERATORS
Operator | 2026-08-24: 4; 2026-08-31: 4; 2026-09-07: 4; 2026-09-14: 4; 2026-09-21: 4; 2026-09-28: 4; 2026-10-05: 4; 2026-10-12: 4; 2026-10-19: 4; 2026-10-26: 4; 2026-11-02: 4; 2026-11-09: 4
BP TECHNICIANS
Site manager | bar: 2026-04-27; 2026-05-04; 2026-05-11; 2026-05-18; 2026-05-25; 2026-06-01; 2026-06-08; 2026-06-15; 2026-06-22; 2026-06-29; 2026-07-06; 2026-07-13; 2026-07-20; 2026-07-27; 2026-08-03; 2026-08-24; 2026-08-31; 2026-09-07; 2026-09-14; 2026-09-21; 2026-09-28; 2026-10-05; 2026-10-12; 2026-10-19; 2026-10-26; 2026-11-02; 2026-11-09; 2027-01-25
Assembler supervisor | bar: 2026-05-04; 2026-05-11; 2026-05-18; 2026-05-25; 2026-06-01; 2026-06-08; 2026-06-15; 2026-06-22; 2026-06-29; 2026-07-06; 2026-07-13; 2026-07-20; 2026-07-27; 2026-08-03; 2026-08-24; 2026-08-31; 2026-09-07; 2026-09-14
Hydraulic supervisor | bar: 2026-06-29; 2026-07-06
BP ELECTRICAL MANPOWER
Electrician supervisor | bar: 2026-05-18; 2026-05-25; 2026-06-01; 2026-06-08; 2026-06-15; 2026-06-22; 2026-06-29; 2026-07-06; 2026-07-13; 2026-07-20; 2026-07-27; 2026-08-03
BP SOFTWARE MANPOWER
Software Engineering | 2026-07-20: 1; 2026-07-27: 2; 2026-08-03: 2; 2026-08-24: 2; 2026-08-31: 2; 2026-09-07: 1; 2026-09-14: 1; 2026-09-21: 1; 2026-09-28: 1; 2026-10-05: 1; 2026-10-12: 1; 2026-10-19: 1; 2026-10-26: 1
TOTAL: | 2026-03-16: 0; 2026-03-23: 0; 2026-03-30: 0; 2026-04-06: 0; 2026-04-13: 0; 2026-04-20: 0; 2026-04-27: 5; 2026-05-04: 13; 2026-05-11: 11; 2026-05-18: 23; 2026-05-25: 25; 2026-06-01: 26; 2026-06-08: 27; 2026-06-15: 28; 2026-06-22: 27; 2026-06-29: 26; 2026-07-06: 25; 2026-07-13: 18; 2026-07-20: 18; 2026-07-27: 15; 2026-08-03: 12; 2026-08-10: 0; 2026-08-17: 0; 2026-08-24: 12; 2026-08-31: 11; 2026-09-07: 10; 2026-09-14: 7; 2026-09-21: 6; 2026-09-28: 6; 2026-10-05: 6; 2026-10-12: 6; 2026-10-19: 6; 2026-10-26: 6; 2026-11-02: 5; 2026-11-09: 5; 2026-11-16: 0; 2026-11-23: 0; 2026-11-30: 0; 2026-12-07: 0; 2026-12-14: 0; 2026-12-21: 0; 2026-12-28: 0; 2027-01-04: 0; 2027-01-11: 0; 2027-01-18: 0; 2027-01-25: 1; 2027-02-01: 0 | 23160
LINE 3+4 | 2026-03-16: Weeks 2026; 2027-01-04: Weeks 2027
AIB MECHANICAL MANPOWER | 2026-03-16: 12; 2026-03-23: 13; 2026-03-30: 14; 2026-04-06: 15; 2026-04-13: 16; 2026-04-20: 17; 2026-04-27: 18; 2026-05-04: 19; 2026-05-11: 20; 2026-05-18: 21; 2026-05-25: 22; 2026-06-01: 23; 2026-06-08: 24; 2026-06-15: 25; 2026-06-22: 26; 2026-06-29: 27; 2026-07-06: 28; 2026-07-13: 29; 2026-07-20: 30; 2026-07-27: 31; 2026-08-03: 32; 2026-08-10: 33; 2026-08-17: 34; 2026-08-24: 35; 2026-08-31: 36; 2026-09-07: 37; 2026-09-14: 38; 2026-09-21: 39; 2026-09-28: 40; 2026-10-05: 41; 2026-10-12: 42; 2026-10-19: 43; 2026-10-26: 44; 2026-11-02: 45; 2026-11-09: 46; 2026-11-16: 47; 2026-11-23: 48; 2026-11-30: 49; 2026-12-07: 50; 2026-12-14: 51; 2026-12-21: 52; 2026-12-28: 53; 2027-01-04: 1; 2027-01-11: 2; 2027-01-18: 3; 2027-01-25: 4; 2027-02-01: 5
Foreman | bar: 2026-06-29; 2026-07-06; 2026-07-13; 2026-07-20; 2026-07-27; 2026-08-03; 2026-08-10; 2026-08-17; 2026-08-24; 2026-08-31; 2026-09-07; 2026-09-14; 2026-09-21; 2026-09-28; 2026-10-05; 2026-10-12; 2026-10-19; 2026-10-26
Assembler junior | 2026-06-29: 1; 2026-07-06: 3; 2026-07-13: 3; 2026-07-20: 3; 2026-07-27: 3; 2026-08-03: 4; 2026-08-10: 4; 2026-08-17: 4; 2026-08-24: 4; 2026-08-31: 4; 2026-09-07: 3; 2026-09-14: 2; 2026-09-21: 1; 2026-09-28: 1; 2026-10-05: 1
Assembler senior | 2026-06-29: 1; 2026-07-06: 3; 2026-07-13: 1; 2026-07-20: 1; 2026-07-27: 1; 2026-08-03: 2; 2026-08-10: 3; 2026-08-17: 3; 2026-08-24: 3; 2026-08-31: 3; 2026-09-07: 3; 2026-09-14: 3; 2026-09-21: 3; 2026-09-28: 2; 2026-10-05: 2
Technician specialized in machine alignment | bar: 2026-07-20; 2026-07-27; 2026-08-03
Construction worker | bar: 2026-07-27; 2026-08-17; 2026-09-07
Hydraulic technician | 2026-07-20: 2; 2026-07-27: 3; 2026-08-03: 4; 2026-08-10: 4; 2026-08-17: 4; 2026-08-24: 4; 2026-08-31: 4; 2026-09-07: 4; 2026-09-14: 2; 2026-09-21: 2; 2026-09-28: 2
Assembler senior Welder | bar: 2026-07-20; 2026-07-27; 2026-08-03; 2026-08-10; 2026-08-17; 2026-08-24; 2026-08-31; 2026-09-07; 2026-09-14; 2026-09-21
Helpers | 2026-06-29: 1; 2026-07-06: 4; 2026-07-13: 4; 2026-07-20: 5; 2026-07-27: 5; 2026-08-03: 4; 2026-08-10: 5; 2026-08-17: 5; 2026-08-24: 5; 2026-08-31: 4; 2026-09-07: 3; 2026-09-14: 2; 2026-09-21: 2; 2026-09-28: 1
AIB ELECTRICAL MANPOWER
Electrician technician | 2026-07-20: 2; 2026-07-27: 2; 2026-08-03: 4; 2026-08-10: 5; 2026-08-17: 5; 2026-08-24: 5; 2026-08-31: 4; 2026-09-07: 4; 2026-09-14: 3; 2026-09-21: 3; 2026-09-28: 2; 2026-10-05: 2; 2026-10-12: 2; 2026-10-19: 1; 2026-10-26: 1
Helpers | 2026-07-20: 4; 2026-07-27: 4; 2026-08-03: 2; 2026-08-10: 1; 2026-08-17: 1; 2026-08-24: 1; 2026-08-31: 1; 2026-09-07: 1; 2026-09-14: 1; 2026-09-21: 1; 2026-09-28: 1; 2026-10-05: 1; 2026-10-12: 1; 2026-10-19: 1; 2026-10-26: 1
AIB OPERATORS
Operator | 2026-10-12: 4; 2026-10-19: 4; 2026-10-26: 4; 2026-11-02: 4; 2026-11-09: 4; 2026-11-16: 4; 2026-11-23: 4; 2026-11-30: 4; 2026-12-07: 4; 2026-12-14: 4; 2027-01-04: 4; 2027-01-11: 4; 2027-01-18: 4
BP TECHNICIANS | bar: 2027-01-25
Site manager | bar: 2026-06-29; 2026-07-06; 2026-07-13; 2026-07-20; 2026-07-27; 2026-08-03; 2026-08-24; 2026-08-31; 2026-09-07; 2026-09-14; 2026-09-21; 2026-09-28; 2026-10-05; 2026-10-12; 2026-10-19; 2026-10-26; 2026-11-02; 2026-11-09; 2026-11-16; 2026-11-23; 2026-11-30; 2026-12-07; 2026-12-14; 2027-01-04; 2027-01-11; 2027-01-18
Assembler supervisor | bar: 2026-07-06; 2026-07-13; 2026-07-20; 2026-07-27; 2026-08-03; 2026-08-24; 2026-08-31; 2026-09-07; 2026-09-14; 2026-09-21; 2026-09-28; 2026-10-05; 2026-10-12; 2026-10-19; 2026-10-26; 2026-11-02
Hydraulic supervisor | bar: 2026-08-31; 2026-09-07
BP ELECTRICAL MANPOWER
Electrician supervisor | bar: 2026-07-20; 2026-07-27; 2026-08-03; 2026-08-24; 2026-08-31; 2026-09-07; 2026-09-14; 2026-09-21; 2026-09-28; 2026-10-05; 2026-10-12; 2026-10-19; 2026-10-26
BP SOFTWARE MANPOWER
Software Engineering | 2026-09-21: 1; 2026-09-28: 2; 2026-10-05: 2; 2026-10-12: 2; 2026-10-19: 2; 2026-10-26: 1; 2026-11-02: 1; 2026-11-09: 1; 2026-11-16: 1; 2026-11-23: 1; 2026-11-30: 1; 2026-12-07: 1; 2026-12-14: 1
TOTAL: | 2026-03-16: 0; 2026-03-23: 0; 2026-03-30: 0; 2026-04-06: 0; 2026-04-13: 0; 2026-04-20: 0; 2026-04-27: 0; 2026-05-04: 0; 2026-05-11: 0; 2026-05-18: 0; 2026-05-25: 0; 2026-06-01: 0; 2026-06-08: 0; 2026-06-15: 0; 2026-06-22: 0; 2026-06-29: 5; 2026-07-06: 13; 2026-07-13: 11; 2026-07-20: 23; 2026-07-27: 25; 2026-08-03: 26; 2026-08-10: 24; 2026-08-17: 25; 2026-08-24: 27; 2026-08-31: 26; 2026-09-07: 25; 2026-09-14: 18; 2026-09-21: 18; 2026-09-28: 15; 2026-10-05: 12; 2026-10-12: 13; 2026-10-19: 12; 2026-10-26: 11; 2026-11-02: 7; 2026-11-09: 6; 2026-11-16: 6; 2026-11-23: 6; 2026-11-30: 6; 2026-12-07: 6; 2026-12-14: 6; 2026-12-21: 0; 2026-12-28: 0; 2027-01-04: 5; 2027-01-11: 5; 2027-01-18: 5; 2027-01-25: 1; 2027-02-01: 0 | 23280
TOTAL MANPOWER | 2026-03-16: Weeks 2026; 2027-01-04: Weeks 2027
| 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49 |  | 50 |  | 51 |  | 52 |  | 53 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5
TOTAL: | 2026-03-16: 3; 2026-03-23: 3; 2026-03-30: 0; 2026-04-06: 0; 2026-04-13: 0; 2026-04-20: 0; 2026-04-27: 5; 2026-05-04: 13; 2026-05-11: 11; 2026-05-18: 23; 2026-05-25: 25; 2026-06-01: 26; 2026-06-08: 27; 2026-06-15: 28; 2026-06-22: 27; 2026-06-29: 31; 2026-07-06: 38; 2026-07-13: 29; 2026-07-20: 41; 2026-07-27: 40; 2026-08-03: 38; 2026-08-10: 24; 2026-08-17: 25; 2026-08-24: 39; 2026-08-31: 37; 2026-09-07: 35; 2026-09-14: 25; 2026-09-21: 24; 2026-09-28: 21; 2026-10-05: 18; 2026-10-12: 19; 2026-10-19: 18; 2026-10-26: 17; 2026-11-02: 12; 2026-11-09: 11; 2026-11-16: 6; 2026-11-23: 6; 2026-11-30: 6; 2026-12-07: 6; 2026-12-14: 6; 2026-12-21: 0; 2026-12-28: 0; 2027-01-04: 5; 2027-01-11: 5; 2027-01-18: 5; 2027-01-25: 2; 2027-02-01: 0 | 46440
WEEKS |  |  | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5
|  |  | 3 | 3 | 0 | 0 | 0 | 0 | 5 | 13 | 11 | 23 | 25 | 26 | 27 | 28 | 27 | 31 | 38 | 29 | 41 | 40 | 38 | 24 | 25 | 39 | 37 | 35 | 25 | 24 | 21 | 18 | 19 | 18 | 17 | 12 | 11 | 6 | 6 | 6 | 6 | 6 | 0 | 5 | 5 | 5 | 2 | 0

## Organization Chart
PROJECT NUMBER:00-2400000
BRUNO PRESEZZI
INSERTEC´S ORGANIZATION CHART AT SITE
[5 empty] | PROJECT MANAGER (Paolo Aime) | ERECTION& COMMISSIONING MANAGER (Claudio Cagliani + Emilio Villa)
SITE MANAGER
| EXTERNAL TECHNICIANS (RFI, RIA…) |  |  | MECHANICAL SUPERVISORS |  | ELECTRICAL SUPERVISORS | HYDRAULIC SUPERVISORS |  |  | COMMISIONING SUPERVISORS
BRUNO PRESEZZI STAFF at HEADQUARTER OFFICES
|  |  | BRUNO PRESEZZI at SITE |  |  |  |  | HIERARCHIC DEPENDENCE
|  |  | AL INVEST TECHNICIANS |  |  |  |  | FUNCTIONAL DEPENDENCE
NOTES:
- The Site Manager may perform the functions of mechanical or commissioning responsible
- The supervisors will be on site on the dates on which the specific works applicable to their specialty are carried out.

## no valido (hidden)
[77 empty] | ACTUALIZADO: |  |  |  | 2026-05-12
PLANIFICACION ALINVEST (KOLDO)
|  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49 |  | 50 |  | 51 |  | 52 |  | 1 |  | 2 |  | 3 |  | 4
| EQUIPO | 2026-04-06 | 2026-04-12 | 2026-04-13 | 2026-04-19 | 2026-04-20 | 2026-04-26 | 2026-04-27 | 2026-05-03 | 2026-05-04 | 2026-05-10 | 2026-05-11 | 2026-05-17 | 2026-05-18 | 2026-05-24 | 2026-05-25 | 2026-05-31 | 2026-06-01 | 2026-06-07 | 2026-06-08 | 2026-06-14 | 2026-06-15 | 2026-06-21 | 2026-06-22 | 2026-06-28 | 2026-06-29 | 2026-07-05 | 2026-07-06 | 2026-07-12 | 2026-07-13 | 2026-07-19 | 2026-07-20 | 2026-07-26 | 2026-07-27 | 2026-08-02 | 2026-08-03 | 2026-08-09 | 2026-08-10 | 2026-08-16 | 2026-08-17 | 2026-08-23 | 2026-08-24 | 2026-08-30 | 2026-08-31 | 2026-09-06 | 2026-09-07 | 2026-09-13 | 2026-09-14 | 2026-09-20 | 2026-09-21 | 2026-09-27 | 2026-09-28 | 2026-10-04 | 2026-10-05 | 2026-10-11 | 2026-10-12 | 2026-10-18 | 2026-10-19 | 2026-10-25 | 2026-10-26 | 2026-11-01 | 2026-11-02 | 2026-11-08 | 2026-11-09 | 2026-11-15 | 2026-11-16 | 2026-11-22 | 2026-11-23 | 2026-11-29 | 2026-11-30 | 2026-12-06 | 2026-12-07 | 2026-12-13 | 2026-12-14 | 2026-12-20 | 2026-12-21 | 2026-12-27 | 2026-12-28 | 2027-01-03 | 2027-01-04 | 2027-01-10 | 2027-01-11 | 2027-01-17 | 2027-01-18 | 2027-01-24
Fase 1
| Stirring 1 |  |  |  | MECANICO | [15 empty] | E
| Holder 1 |  |  |  | M |  |  |  |  | R | [5 empty] | M/E | [6 empty] | COLD |  |  | DRY OUT
| Fusor 1 | [14 empty] | R | [9 empty] | M/E | [6 empty] | COL |  |  | DRY OUT
| Fusor 2 | [14 empty] | M | [5 empty] | R | [9 empty] | M/E | [6 empty] | COLD |  |  | DRY OUT
Regueras
RFI
Skimming 1
Charging 1
Fase 2 | Stirring 2 | [20 empty] | COLD
| Stirring 3 | [20 empty] | COLD
| Stirring 4 | [20 empty] | COLD
| Holder CH1 |  |  |  | M | [11 empty] | M/E | [6 empty] | COLD |  |  | DRY OUT
Melter CM1
Regueras CH1-CM1
Holder CH2
Melter CM2
Regueras CH2-CM2
RFI 2
RFI 3
Skimming 2
Charging 2
Fase 3 | Holder CH3
Melter CM3
Regueras CH3-CM3
Holder CH4
Melter CM4
Regueras CH4-CM4
RFI 4
RFI 5
PT