Attachment No. 5 to the Call

**Requirements on Time Schedule**

1. As a part of his Offer the Tenderer shall submit a **proposal of detailed scope and time schedule of works (structured to individual calendar days) for the implementation of construction works and material deliveries.** Such schedule shall realistically reflect presumed progress of implementation of individual works performed by the Tenderer if his Offer is successful, with brief description of main activities, sequence and time flow, and it will present the proposal of the Tenderer to perform work, i.e. material delivery and performance of works on K1 and K2 boilers, from site takeover till commissioning of K1 and K2 boilers and optimization of incineration process of K1 and K2 boilers. Tenderer shall submit proposal of the time schedule of works for each boiler separately. If the scope and time schedule of works does not correspond to the project documentation, the Buyer will call upon the Tenderer to match the time schedule to the project documentation within a period no longer than 5 days. If the Tenderer within this period fails to submit a schedule in compliance with the project documentation it will be considered by the Buyer as not meeting the Tender requirements of the Buyer and such price quotation will be excluded. **Failure to submit the proposal of time schedule according to the requirements of the Buyer shall mean the Offer of the Tenderer is incomplete and does not meet the Tender requirements of the Buyer.**