## Asr info
CEF | Transport
Action Code | 2016-SK-TMC-0220-S
Exercise Year | 2024
Version | 1
Actual Action Start Date | 07/02/2017
Actual Action End Date | 31/12/2024
A. Maximum EU contribution (Art. 3) | €4,737,050.00
B. Pre-financing rate (Art. 4.1.2) | 50%
C. Maximum pre-financing payment (Art. 4.1.2) (=B*A) | €2,368,525.00
D. Maximum ceiling for the sum of pre-financing and interim payments (Art 4.1.3) (=80%*A) | €3,789,640.00
E. Sum of Previous Pre-financing Payments | €2,075,062.50
F. Sum of Interim Payments | €481,002.50
G. Sum of pre-financing and interim payments (E+F) | €2,556,065.00

## Eligible costs (€)
Update of the indicative breakdown of estimated eligible costs of the Action 2016-SK-TMC-0220-S (€)
|  |  | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
| 1 Preliminary and detailed/executive design | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 925000 | 925000 | 1500000 | 1500000 | 0 | 0 | 2455000 | 29600 | 580000 | 2455000
Total for activity 1
| 2 Project management and public procurement | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 0 | 110500 | 0
Total for activity 2
Total eligible costs
1 | Železnice Slovenskej republiky
Total cumulated eligible costs
1 | Železnice Slovenskej republiky

## Financing needs (€)
Financing needs of the Action 2016-SK-TMC-0220-S (€)
|  |  | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
1 Preliminary and detailed/executive design
1 | Železnice Slovenskej republiky
Totals for activity 1
2 Project management and public procurement
1 | Železnice Slovenskej republiky
Totals for activity 2
Total financing needs
1 | Železnice Slovenskej republiky
Total cumulated financing needs
1 | Železnice Slovenskej republiky

## Progress Overview
Progress Overview of the Action 2016-SK-TMC-0220-S (at accumulated level)
| 2017 |  |  | 2018 |  |  | 2019 |  |  | 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024
| Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress
Activity name | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR
Activity 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 17 | 19 | 27 | 44 | 49 | 29 | 44 | 49 | 31 | 89 | 50 | 62 | 100 | 100 | 100
Activity 2 | 0 | 0 | 37 | 0 | 0 | 85 | 0 | 0 | 95 | 0 | 0 | 95 | 0 | 0 | 95 | 2 | 100 | 95 | 2 | 100 | 95 | 100 | 100 | 100
For the Action | 0 | 0 | 7 | 0 | 0 | 17 | 0 | 0 | 20 | 17 | 19 | 41 | 44 | 49 | 42 | 44 | 49 | 44 | 88 | 50 | 69 | 100 | 100 | 100