## Asr info
CEF | Transport
Action Code | 2016-SK-TMC-0220-S
Exercise Year | 2024
Version | 1
Actual Action Start Date
Actual Action End Date
A. Maximum EU contribution (Art. 3) | €4,737,050.00
B. Pre-financing rate (Art. 4.1.2) | 50%
C. Maximum pre-financing payment (Art. 4.1.2) (=B*A) | €2,368,525.00
D. Maximum ceiling for the sum of pre-financing and interim payments (Art 4.1.3) (=80%*A) | €3,789,640.00
E. Sum of Previous Pre-financing Payments | €2,075,062.50
F. Sum of Interim Payments | €481,002.50
G. Sum of pre-financing and interim payments (E+F) | €2,556,065.00

## Eligible costs (€)
Update of the indicative breakdown of estimated eligible costs of the Action 2016-SK-TMC-0220-S (€)
|  |  | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
| 1 Preliminary and detailed/executive design | 85
1 | Železnice Slovenskej republiky |  | 0 |  | 0 |  | 0 | 0 | 925000 | 925000 | 1500000 | 1500000 | 0 | 0 | 2455000 | 29600 | 580000 | 2455000 | 5460000 | 4909600 | -10.08%
|  | Total for activity 1 | 0 | 0 | 0 | 0 | 0 | 0 | 925000 | 925000 | 1500000 | 1500000 | 0 | 0 | 2455000 | 29600 | 580000 | 2455000 | 5460000 | 4909600 | -10.08%
| 2 Project management and public procurement | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 0 | 110500 | 0 | 113000 | 2500 | -97.79%
|  | Total for activity 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2500 | 2500 | 0 | 0 | 110500 | 0 | 113000 | 2500 | -97.79%
| Total eligible costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 925000 | 925000 | 1500000 | 1500000 | 2500 | 2500 | 2455000 | 29600 | 690500 | 2455000 | 5573000 | 4912100 | -11.86%
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 925000 | 925000 | 1500000 | 1500000 | 2500 | 2500 | 2455000 | 29600 | 690500 | 2455000 | 5573000 | 4912100 | -11.86%
| Total cumulated eligible costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 925000 | 925000 | 2425000 | 2425000 | 2427500 | 2427500 | 4882500 | 2457100 | 5573000 | 4912100 | 5573000 | 4912100 | -11.86%
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 925000 | 925000 | 2425000 | 2425000 | 2427500 | 2427500 | 4882500 | 2457100 | 5573000 | 4912100 | 5573000 | 4912100 | -11.86%

## Financing needs (€)
Financing needs of the Action 2016-SK-TMC-0220-S (€)
|  |  | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
| 1 Preliminary and detailed/executive design | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 786250 | 786250 | 1275000 | 1275000 | 0 | 0 | 2086750 | 25160 | 493000 | 2086750 | 4641000 | 4173160 | -10.08%
|  | Totals for activity 1 | 0 | 0 | 0 | 0 | 0 | 0 | 786250 | 786250 | 1275000 | 1275000 | 0 | 0 | 2086750 | 25160 | 493000 | 2086750 | 4641000 | 4173160 | -10.08%
| 2 Project management and public procurement | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2125 | 2125 | 0 | 0 | 93925 | 0 | 96050 | 2125 | -97.79%
|  | Totals for activity 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2125 | 2125 | 0 | 0 | 93925 | 0 | 96050 | 2125 | -97.79%
| Total financing needs |  | 0 | 0 | 0 | 0 | 0 | 0 | 786250 | 786250 | 1275000 | 1275000 | 2125 | 2125 | 2086750 | 25160 | 586925 | 2086750 | 4737050 | 4175285 | -11.86%
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 786250 | 786250 | 1275000 | 1275000 | 2125 | 2125 | 2086750 | 25160 | 586925 | 2086750 | 4737050 | 4175285 | -11.86%
| Total cumulated financing needs |  | 0 | 0 | 0 | 0 | 0 | 0 | 786250 | 786250 | 2061250 | 2061250 | 2063375 | 2063375 | 4150125 | 2088535 | 4737050 | 4175285 | 4737050 | 4175285 | -11.86%
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 786250 | 786250 | 2061250 | 2061250 | 2063375 | 2063375 | 4150125 | 2088535 | 4737050 | 4175285 | 4737050 | 4175285 | -11.86%

## Progress Overview
Progress Overview of the Action 2016-SK-TMC-0220-S (at accumulated level)
| 2017 |  |  | 2018 |  |  | 2019 |  |  | 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024
| Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress
Activity name | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR
Activity 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 17 | 38 | 27 | 44 | 100 | 29 | 44 | 100 | 31 | 89 | 100 | 62 | 100 | 100 | 100
Activity 2 | 0 | 0 | 37 | 0 | 0 | 85 | 0 | 0 | 95 | 0 | 0 | 95 | 0 | 0 | 95 | 2 | 100 | 95 | 2 | 100 | 95 | 100 | 100 | 100
For the Action | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 38 | 0 | 44 | 100 | 0 | 44 | 100 | 0 | 88 | 100 | 0 | 100 | 100 | 100