## ALSE
[79 empty] | UPDATED: |  |  |  | 2025-06-30
ALINVEST SCHEDULE FOR CONSTRUCTION AND COMMISSIOING SUBCONTRACT - PRELIMINARY MANPOWER HISTOGRAMM (ONLY FOR REFERENCE)
|  | Weeks 2026 | [77 empty] | Weeks 2027
|  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49 |  | 50 |  | 51 |  | 52 |  | 1 |  | 2 |  | 3 |  | 4 |  | 5
EQUIPMENT | time axis 2026-03-30 to 2027-01-31
FIRST PHASE | Unloading materials | bar: 2026-04-05 to 2026-05-31
| Stirring 1 | 2026-05-03: M; 2026-07-19: E; 2026-08-09: COLD
| Holder 35Ton -1 | 2026-05-03: M; 2026-05-25: R; 2026-06-15: M/E; 2026-07-26: COLD; 2026-08-10: DRY OUT
| Melter 35Ton- 1 | 2026-05-03: M; 2026-05-25: R; 2026-06-29: M/E; 2026-07-26: COLD; 2026-08-10: DRY OUT
| Melter 35Ton- 2 | 2026-05-25: M; 2026-06-21: R; 2026-07-20: M/E; 2026-08-16: COLD; 2026-08-24: DRY OUT
| Launders | 2026-08-17: COLD; 2026-08-24: DRY OUT
| RFI | 2026-07-27: M; 2026-08-03: E; 2026-08-23: COLD
| Skimming 1 | 2026-05-31: M; 2026-07-27: E; 2026-08-23: COLD
| Charging 1 | 2026-05-31: M; 2026-07-27: E; 2026-08-23: COLD
Initial operation | bar: 2026-09-20 to 2026-10-05
SECOND PHASE | Unloading materials | bar: 2026-04-05 to 2026-05-31
| Stirring 2 | 2026-05-17: M; 2026-07-19: E; 2026-08-09: COLD
| Stirring 3 | 2026-05-31: M; 2026-07-19: E; 2026-08-02: E; 2026-08-09: COLD
| Stirring 4 | 2026-06-14: M; 2026-07-19: E; 2026-08-02: E; 2026-08-09: COLD
| Holder CH1 -25tons | 2026-05-10: M; 2026-05-25: R; 2026-06-21: M/E; 2026-07-20: COLD; 2026-08-16: DRY OUT
| Melter CM1 -25tons | 2026-06-15: R; 2026-07-19: M/E; 2026-08-17: COLD; 2026-08-31: DRY OUT
| Launders CH1-CM1 | 2026-08-24: COLD; 2026-08-31: DRY OUT
| Holder CH2 -25tons | 2026-05-25: 0; 2026-06-21: R; 2026-07-19: M/E; 2026-08-10: COLD; 2026-08-30: DRY OUT
| Melter CM2 -25tons | 2026-06-29: R; 2026-08-02: M/E; 2026-08-17: COLD; 2026-08-31: DRY OUT
| Launders CH2-CM2 | 2026-08-24: COLD; 2026-08-31: DRY OUT
| RFI 2 | 2026-08-24: COLD
| RFI 3 | 2026-08-24: COLD
| Skimming 2 | 2026-06-15: M; 2026-08-03: E; 2026-08-17: COLD; 2026-08-24: COLD
| Charging 2 | 2026-06-15: M; 2026-08-03: E; 2026-08-17: COLD; 2026-08-24: COLD
Initial operation | bar: 2026-09-27 to 2026-10-18
THIRD PHASE | Unloading materials | bar: 2026-05-11 to 2026-07-27
| Holder CH3 | 2026-07-06: R; 2026-09-07: COLD; 2026-10-04: DRY OUT
| Melter CM3 | 2026-07-06: M; 2026-07-27: R; 2026-09-06: M/E; 2026-09-28: COLD; 2026-10-12: DRY OUT
| Launders CH3-CM3 | 2026-10-12: DRY OUT
| Holder CH4 | 2026-07-06: M; 2026-08-02: R; 2026-09-06: M/E; 2026-09-28: COLD; 2026-10-18: DRY OUT
| Melter CM4 | 2026-07-20: M; 2026-08-10: R; 2026-09-20: M/E; 2026-10-05: COLD; 2026-10-19: DRY OUT
| Launders CH4-CM4 | 2026-10-19: DRY OUT
| RFI 4 | 2026-10-05: COLD; 2026-10-12: COLD
| RFI 5 | 2026-10-05: COLD; 2026-10-12: COLD
Initial operation | bar: 2026-11-22 to 2026-12-13
PT | bar: 2026-10-05 to 2027-01-31
MANPOWER OF INDIRECT MECHANICAL AND ELECTRICAL SUPERVISOR
|  | Weeks 2026 | [77 empty] | Weeks 2027
MECHANICAL MANPOWER |  | 2026-03-30: 14; 2026-04-06: 15; 2026-04-13: 16; 2026-04-20: 17; 2026-04-27: 18; 2026-05-04: 19; 2026-05-11: 20; 2026-05-18: 21; 2026-05-25: 22; 2026-06-01: 23; 2026-06-08: 24; 2026-06-15: 25; 2026-06-22: 26; 2026-06-29: 27; 2026-07-06: 28; 2026-07-13: 29; 2026-07-20: 30; 2026-07-27: 31; 2026-08-03: 32; 2026-08-10: 33; 2026-08-17: 34; 2026-08-24: 35; 2026-08-31: 36; 2026-09-07: 37; 2026-09-14: 38; 2026-09-21: 39; 2026-09-28: 40; 2026-10-05: 41; 2026-10-12: 42; 2026-10-19: 43; 2026-10-26: 44; 2026-11-02: 45; 2026-11-09: 46; 2026-11-16: 47; 2026-11-23: 48; 2026-11-30: 49; 2026-12-07: 50; 2026-12-14: 51; 2026-12-21: 52; 2026-12-28: 1; 2027-01-04: 2; 2027-01-11: 3; 2027-01-18: 4; 2027-01-25: 5
3rd Ph | Team leader | bar: 2026-06-01; 2026-06-08; 2026-06-15; 2026-06-22; 2026-06-29; 2026-07-06; 2026-07-13; 2026-07-20; 2026-07-27; 2026-08-03; 2026-08-10; 2026-08-17; 2026-08-24; 2026-08-31; 2026-09-07; 2026-09-14; 2026-09-21; 2026-09-28; 2026-10-05; 2026-10-12; 2026-10-19; 2026-10-26; 2026-11-02; 2026-11-09; 2026-11-16
Fitter and pipers |  | 2026-06-01: 4; 2026-06-08: 4; 2026-06-15: 4; 2026-06-22: 4; 2026-06-29: 4; 2026-07-06: 4; 2026-07-13: 4; 2026-07-20: 4; 2026-07-27: 4; 2026-08-03: 4; 2026-08-10: 4; 2026-08-17: 4; 2026-08-24: 4; 2026-08-31: 4; 2026-09-07: 4; 2026-09-14: 4; 2026-09-21: 4; 2026-09-28: 4; 2026-10-05: 2
Welders | bar: 2026-06-01; 2026-06-08; 2026-06-15; 2026-06-22; 2026-06-29; 2026-07-06; 2026-07-13; 2026-07-20; 2026-07-27; 2026-08-03; 2026-08-10; 2026-08-17; 2026-08-24; 2026-08-31; 2026-09-07; 2026-09-14; 2026-09-21; 2026-09-28
| TOTAL: | 2026-03-30: 0; 2026-04-06: 0; 2026-04-13: 0; 2026-04-20: 0; 2026-04-27: 0; 2026-05-04: 0; 2026-05-11: 0; 2026-05-18: 0; 2026-05-25: 0; 2026-06-01: 6; 2026-06-08: 6; 2026-06-15: 6; 2026-06-22: 6; 2026-06-29: 6; 2026-07-06: 6; 2026-07-13: 6; 2026-07-20: 6; 2026-07-27: 6; 2026-08-03: 6; 2026-08-10: 6; 2026-08-17: 6; 2026-08-24: 6; 2026-08-31: 6; 2026-09-07: 6; 2026-09-14: 6; 2026-09-21: 6; 2026-09-28: 6; 2026-10-05: 3; 2026-10-12: 1; 2026-10-19: 1; 2026-10-26: 1; 2026-11-02: 1; 2026-11-09: 1; 2026-11-16: 1; 2026-11-23: 0; 2026-11-30: 0; 2026-12-07: 0; 2026-12-14: 0; 2026-12-21: 0; 2026-12-28: 0; 2027-01-04: 0; 2027-01-11: 0; 2027-01-18: 0; 2027-01-25: 0 | 7020
IMPORTANT NOTES: 1- Team leader and foreman can work as direct worker 2- Welders will be qualified according to EN 9606-01 3- All manpower shall certify with experience or training their knowledge and skill to work. 4- If any of the workers fail to comply with safety guidelines, they will be removed from the work site, without any compensation to the property. 5- 60 hours/week considered.
| WEEKS | 2026-03-30: 14; 2026-04-05: 15; 2026-04-06: 16; 2026-04-12: 17; 2026-04-13: 18; 2026-04-19: 19; 2026-04-20: 20; 2026-04-26: 21; 2026-04-27: 22; 2026-05-03: 23; 2026-05-04: 24; 2026-05-10: 25; 2026-05-11: 26; 2026-05-17: 27; 2026-05-18: 28; 2026-05-24: 29; 2026-05-25: 30; 2026-05-31: 31; 2026-06-01: 32; 2026-06-07: 33; 2026-06-08: 34; 2026-06-14: 35; 2026-06-15: 36; 2026-06-21: 37; 2026-06-22: 38; 2026-06-28: 39; 2026-06-29: 40; 2026-07-05: 41; 2026-07-06: 42; 2026-07-12: 43; 2026-07-13: 44; 2026-07-19: 45; 2026-07-20: 46; 2026-07-26: 47; 2026-07-27: 48; 2026-08-02: 49; 2026-08-03: 50; 2026-08-09: 51; 2026-08-10: 52; 2026-08-16: 1; 2026-08-17: 2; 2026-08-23: 3; 2026-08-24: 4; 2026-08-30: 5
| SUBCONTRACTO´S MANPOWER | 2026-03-30: 0; 2026-04-05: 0; 2026-04-06: 0; 2026-04-12: 0; 2026-04-13: 0; 2026-04-19: 0; 2026-04-20: 0; 2026-04-26: 0; 2026-04-27: 0; 2026-05-03: 6; 2026-05-04: 6; 2026-05-10: 6; 2026-05-11: 6; 2026-05-17: 6; 2026-05-18: 6; 2026-05-24: 6; 2026-05-25: 6; 2026-05-31: 6; 2026-06-01: 6; 2026-06-07: 6; 2026-06-08: 6; 2026-06-14: 6; 2026-06-15: 6; 2026-06-21: 6; 2026-06-22: 6; 2026-06-28: 6; 2026-06-29: 6; 2026-07-05: 3; 2026-07-06: 1; 2026-07-12: 1; 2026-07-13: 1; 2026-07-19: 1; 2026-07-20: 1; 2026-07-26: 1; 2026-07-27: 0; 2026-08-02: 0; 2026-08-03: 0; 2026-08-09: 0; 2026-08-10: 0; 2026-08-16: 0; 2026-08-17: 0; 2026-08-23: 0; 2026-08-24: 0; 2026-08-30: 0

## Organization Chart
PROJECT NUMBER: E- 2551
ALINVEST
INSERTEC´S ORGANIZATION CHART AT SITE
[5 empty] | PROJECT MANAGER (Aitor Egusquiza) | ERECTION& COMMISSIONING MANAGER (Jon Arteaga)
SITE MANAGER
| EXTERNAL TECHNICIANS (RFI, RIA…) |  |  | MECHANICAL RESPONSIBLE |  | ELECTRICAL&AUTOMATION RESPONSIBLE | REFRACTARY SUPERVISOR |  |  | COMMISIONING RESPONSIBLE
|  |  |  | MECHANICAL SUPERVISORS |  | ELECTRICAL SUPERVISORS |  |  |  | COMMISIONING SUPERVISORS
INSERTEC STAFF AT HEADQUARTER OFFICES
|  |  | INSERTEC STAFF AT SITE |  |  |  |  | HIERARCHIC DEPENDENCE
|  |  | EXTERNAL TECHNICIANS TO BE MOBILIZED AT SITE WHEN THEY ARE NEEDED. |  |  |  |  | FUNCTIONAL DEPENDENCE
NOTES:
- The Site Manager may perform the functions of mechanical or commissioning responsible
- The supervisors will be on site on the dates on which the specific works applicable to their specialty are carried out.

## no valido (hidden)
[77 empty] | ACTUALIZADO: |  |  |  | 2026-05-12
PLANIFICACION ALINVEST (KOLDO)
|  | 15 |  | 16 |  | 17 |  | 18 |  | 19 |  | 20 |  | 21 |  | 22 |  | 23 |  | 24 |  | 25 |  | 26 |  | 27 |  | 28 |  | 29 |  | 30 |  | 31 |  | 32 |  | 33 |  | 34 |  | 35 |  | 36 |  | 37 |  | 38 |  | 39 |  | 40 |  | 41 |  | 42 |  | 43 |  | 44 |  | 45 |  | 46 |  | 47 |  | 48 |  | 49 |  | 50 |  | 51 |  | 52 |  | 1 |  | 2 |  | 3 |  | 4
| EQUIPO | 2026-04-06 | 2026-04-12 | 2026-04-13 | 2026-04-19 | 2026-04-20 | 2026-04-26 | 2026-04-27 | 2026-05-03 | 2026-05-04 | 2026-05-10 | 2026-05-11 | 2026-05-17 | 2026-05-18 | 2026-05-24 | 2026-05-25 | 2026-05-31 | 2026-06-01 | 2026-06-07 | 2026-06-08 | 2026-06-14 | 2026-06-15 | 2026-06-21 | 2026-06-22 | 2026-06-28 | 2026-06-29 | 2026-07-05 | 2026-07-06 | 2026-07-12 | 2026-07-13 | 2026-07-19 | 2026-07-20 | 2026-07-26 | 2026-07-27 | 2026-08-02 | 2026-08-03 | 2026-08-09 | 2026-08-10 | 2026-08-16 | 2026-08-17 | 2026-08-23 | 2026-08-24 | 2026-08-30 | 2026-08-31 | 2026-09-06 | 2026-09-07 | 2026-09-13 | 2026-09-14 | 2026-09-20 | 2026-09-21 | 2026-09-27 | 2026-09-28 | 2026-10-04 | 2026-10-05 | 2026-10-11 | 2026-10-12 | 2026-10-18 | 2026-10-19 | 2026-10-25 | 2026-10-26 | 2026-11-01 | 2026-11-02 | 2026-11-08 | 2026-11-09 | 2026-11-15 | 2026-11-16 | 2026-11-22 | 2026-11-23 | 2026-11-29 | 2026-11-30 | 2026-12-06 | 2026-12-07 | 2026-12-13 | 2026-12-14 | 2026-12-20 | 2026-12-21 | 2026-12-27 | 2026-12-28 | 2027-01-03 | 2027-01-04 | 2027-01-10 | 2027-01-11 | 2027-01-17 | 2027-01-18 | 2027-01-24
Fase 1
| Stirring 1 |  |  |  | MECANICO | [15 empty] | E
| Holder 1 |  |  |  | M |  |  |  |  | R | [5 empty] | M/E | [6 empty] | COLD |  |  | DRY OUT
| Fusor 1 | [14 empty] | R | [9 empty] | M/E | [6 empty] | COL |  |  | DRY OUT
| Fusor 2 | [14 empty] | M | [5 empty] | R | [9 empty] | M/E | [6 empty] | COLD |  |  | DRY OUT
Regueras
RFI
Skimming 1
Charging 1
Fase 2 | Stirring 2 | [20 empty] | COLD
| Stirring 3 | [20 empty] | COLD
| Stirring 4 | [20 empty] | COLD
| Holder CH1 |  |  |  | M | [11 empty] | M/E | [6 empty] | COLD |  |  | DRY OUT
Melter CM1
Regueras CH1-CM1
Holder CH2
Melter CM2
Regueras CH2-CM2
RFI 2
RFI 3
Skimming 2
Charging 2
Fase 3 | Holder CH3
Melter CM3
Regueras CH3-CM3
Holder CH4
Melter CM4
Regueras CH4-CM4
RFI 4
RFI 5
PT