**Annex No. 5**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Milestone** | **Action** | **Action description** | **Completion deadline** | **Payment schedule** |
|  |  |  |  |  |
| **1** | **Acceptance of the Site:** | means the moment when the Client hands over the Site to the Contractor and the Contractor takes over the Site from the Client; | at latest within 7 calendar days from delivery of the Client’s written request to commence performance under Art. 3.1.1 of the Agreement | ----------------- |
| **2** | **Commencement of Work:** | means the moment when the Contractors commences performance of the Work | at latest within 14 calendar days from takeover of the Site, unless agreed otherwise in writing | Payment of 40% of the Price for the given work item (given store) after delivery of the panels/inverters, DC distributors / supporting structure and commencement of installation (at the given store) under Annex No. 12 to the Agreement |
| **3** | **Performance of Work:** | means the moment when the Contractor completes all construction works on the Work and duly demonstrates that the Work is fully functional as a whole | at latest within 4 weeks from the date of takeover of the Site, unless agreed otherwise in writing (*to be completed by the participant based on their bid. The Contracting Authority requires the period of work implementation to be maximally 8 weeks from the date of takeover of the Site.)* | ----------------- |
| **4** | **Procurement of official approval:** | means the moment when the approval and/or other consent required for the use of the Work comes into legal force, and if does not come into legal force, then when it becomes effective  | no later than 21 days after the date after the performance of the Work pursuant to Milestone 3 | Payment of 25% of the price of the relevant item of Work (relevant store) as per Annex No. 12 to the Contract. |
| **5** | **Procurement of the approval of the distributor and first parallel connection:** | means procuring a consenting opinion for the connection of the PV plant by the entity authorised to issue such consent and after the first parallel connection to the distribution grid | no later than 30 days after the date after the performance of the Work pursuant to Milestone 3 | ----------------- |
| **6** | **Handover of the Work to the Client:** | has the meaning set forth in Art. 5.1.1 of this Contract. | no later than the 3rd day after obtaining the distributor’s consent and the first parallel connection to the distribution grid according to Milestone No. 5  | Payment of 35% of the price of the relevant item of Work (relevant store) as per Annex No. 12 to the Contract. |

 Schedule for Work performance - applicable to each individual item of Work (individual store)

The Client shall send a written invitation to the Contractor to commence performance of the relevant item of Work (relevant store)