## Hárok1
Type | Name of the activity | Start | End | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
|  |  |  | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII.
A1 | Public procurement, authorisation procedures and detailed design | 2017-03-02 | 2024-10-31
M1 | Activity 1 - Start of the preparation of the tender documentation for the selection of the design contractor |  | 2017-03-02 |  |  | M1
M2 | Activity 1 - Public procurement procedure for a detailed design contractor published |  | 2018-01-20 | [12 empty] | M2
M3 | Activity 1 - Contract signed for a design contractor |  | 2018-10-15 | [21 empty] | M3
M4 | Activity 1 - Start of the detailed design |  | 2018-10-17 | [21 empty] | M4
M5 | Activity 1 - Territorial decision and State expertise issued |  | 2020-03-17 | [38 empty] | M5
M6 | Activity 1 - Public procurement procedure for construction works published |  | 2022-07-29 | [66 empty] | M6
M7 | Activity 1 - Public procurement procedure for a construction works supervision published |  | 2022-11-25 | [70 empty] | M7
M8 | Activity 1 - Contract signed for construction works |  | 2023-03-22 | [74 empty] | M8
M9 | Activity 1 - Contract signed for external project management and audit support |  | 2020-07-07 | [54 empty] | M9 | [11 empty] | M9
M10 | Activity 1 - Contract signed for construction works supervision |  | 2023-07-03 | [78 empty] | M10
M11 | Activity 1 - Contract signed for temporary billboards |  | 2023-08-21 | [79 empty] | M11
M12 | Activity 1 - Detailed design completed and approved |  | 2021-10-29 | [57 empty] | M12
M13 | Activity 1 - Contract signed for commemorative plaques |  | 2024-10-31 | [93 empty] | M13
A2 | Construction works and author supervision | 2023-07-05 | 2025-06-30
M14 | Activity 2 - Start of the Construction works supervision |  | 2023-07-05 | [78 empty] | M14
M15 | Activity 2 - First interim supervision report on construction works completed |  | 2024-01-15 | [84 empty] | M15
M16 | Activity 2 - Second interim supervision report on construction works completed |  | 2024-07-14 | [90 empty] | M16
M17 | Activity 2 - Completion of construction works supervision |  | 2025-06-30 | [101 empty] | M17
M18 | Activity 2 - Completion of author supervision |  | 2024-12-31 | [95 empty] | M18
M19 | Activity 2 - Taking Over certificate issued |  | 2024-12-31 | [95 empty] | M19
A3 | Construction works | 2023-04-12 | 2024-12-31
M20 | Activity 3 - Start of the construction works on the Varín - Košice - Čierna nad Tisou section |  | 2023-04-12 | [76 empty] | M20
M21 | Activity 3 - Interoperability Constituents conformity |  | 2023-07-31 | [78 empty] | M21
M22 | Activity 3 - Tests completed |  | 2024-09-01 | [92 empty] | M22
M23 | Activity 3 - Subsystem verification of the Varín - Košice - Čierna nad Tisou section |  | 2024-10-01 | [93 empty] | M23
M24 | Activity 3 - Authorisation of the Varín - Košice - Čierna nad Tisou state border section by a competent authority |  | 2024-12-31 | [95 empty] | M124
M25 | Activity 3 - As-built documentation completed |  | 2024-12-31 | [95 empty] | M25
A4 | Project management and communication | 2021-01-29 | 2025-06-30
M26 | Activity 4 - Communication plan approved |  | 2021-01-29 | [48 empty] | M26
M27 | Activity 4 - Final event organised |  | 2025-06-30 | [101 empty] | M27