## Milestones
Implementation of GSM-R into ŽSR infrastucture, section of Varín - Košice - Čierna nad Tisou state border (2016-SK-TMC-0218-W)
Table 1 Indicative completion dates of the milestones and technical progress
Milestone number | Milestone description | Indicative completion date | [7 empty] | Means of verification | Technical progress1 (%)
|  | GA | ASR 2017 | ASR 2018 | ASR 2019 | ASR 2020 | ASR 2021 | ASR 2022 | ASR 2023
1 | Activity 1 - Start of the preparation of the tender documentation for the selection of the design contractor | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | 2017-03-02 | Confirmation from the Beneficiary | 1 | 100 | 30 | 100
2 | Activity 1 - Public procurement procedure for a detailed design contractor published | 2017-10-30 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | 2018-01-20 | Contract Notice published on Office for Public Procurement and OJEU | 7
3 | Activity 1 - Contract signed for a design contractor | 2018-07-31 | 2018-10-31 | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15 | Award Notice published | 7
4 | Activity 1 - Start of the detailed design | 2018-08-01 | 2018-11-01 | 2018-10-17 | 2018-10-17 | 2018-10-17 | 2018-10-17 | 2018-10-17 | 2018-10-17 | Confirmation from the Beneficiary | 1
5 | Activity 1 - Territorial decision and State expertise issued | 2019-09-30 | 2020-01-01 | 2020-01-01 | 2020-03-17 | 2020-03-17 | 2020-03-17 | 2020-03-17 | 2020-03-17 | Territorial decision issued by a competent authority | 21
6 | Activity 1 - Public procurement procedure for construction works published | 2020-11-30 | 2020-11-30 | 2020-11-30 | 2020-11-30 | 2021-07-31 | 2022-03-30 | 2022-07-29 | 2022-07-29 | Contract Notice published on Office for Public Procurement and OJEU | 9
7 | Activity 1 - Public procurement procedure for a construction works supervision published | 2020-12-31 | 2020-12-31 | 2020-12-31 | 2020-12-31 | 2021-07-31 | 2022-04-30 | 2022-11-25 | 2022-11-25 | Contract Notice published on Office for Public Procurement and OJEU | 6
8 | Activity 1 - Contract signed for construction works | 2021-09-30 | 2021-09-30 | 2021-09-30 | 2021-09-30 | 2022-04-30 | 2022-10-31 | 2023-03-22 | 2023-03-22 | Award Notice published | 9
9 | Activity 1 - Contract signed for external project management and audit support | 2021-09-30 | 2021-09-30 | 2021-09-30 | 2021-09-30 | 2020-07-07 | 2020-07-07 | 2020-07-07 | 2020-07-07 | Award Notice published | 2
10 | Activity 1 - Contract signed for construction works supervision | 2021-09-30 | 2021-09-30 | 2021-09-30 | 2021-09-30 | 2022-04-30 | 2022-10-31 | 2023-05-31 | 2023-07-03 | Award Notice published | 6
11 | Activity 1 - Contract signed for temporary billboards | 2021-09-30 | 2021-09-30 | 2021-09-30 | 2021-09-30 | 2022-04-30 | 2022-10-31 | 2023-05-31 | 2023-08-21 | Award Notice published | 2
12 | Activity 1 - Detailed design completed and approved | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-03-31 | 2021-08-31 | 2021-10-29 | 2021-10-29 | 2021-10-29 | Confirmation from the Beneficiary | 27
13 | Activity 1 - Contract signed for commemorative plaques | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-12-31 | 2024-04-30 | 2024-10-31 | 2024-10-31 | Award Notice published | 2
14 | Activity 2 - Start of the Construction works supervision | 2021-10-01 | 2021-10-01 | 2021-10-01 | 2021-10-01 | 2022-05-01 | 2022-11-01 | 2023-06-01 | 2023-07-24 | Confirmation from the Beneficiary | 1 | 100 | 20
15 | Activity 2 - First interim supervision report on construction works completed | 2021-12-31 | 2021-12-31 | 2021-12-31 | 2021-12-31 | 2022-10-31 | 2023-05-01 | 2023-12-01 | 2024-01-15 | First interim report | 2
16 | Activity 2 - Second interim supervision report on construction works completed | 2022-12-31 | 2022-12-31 | 2022-12-31 | 2022-12-31 | 2023-05-31 | 2023-12-01 | 2024-07-01 | 2024-07-14 | Second interim report | 50
17 | Activity 2 - Completion of construction works supervision | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-12-31 | 2024-12-31 | 2025-06-30 | 2025-06-30 | Final supervision report and confirmation from the beneficiary | 45
18 | Activity 2 - Completion of author supervision | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-12-31 | 2024-06-30 | 2024-12-31 | 2024-12-31 | Confirmation from the Beneficiary | 1
19 | Activity 2 - Taking Over certificate issued | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-12-31 | 2024-06-30 | 2024-12-31 | 2024-12-31 | Taking Over certificate | 1
20 | Activity 3 - Start of the construction works on the Varín - Košice - Čierna nad Tisou section | 2021-10-31 | 2021-10-31 | 2021-10-31 | 2021-10-31 | 2022-05-01 | 2022-11-01 | 2023-03-28 | 2023-04-12 | Confirmation from the Beneficiary | 1 | 100 | 45
21 | Activity 3 - Interoperability Constituents conformity | 2022-02-28 | 2022-02-28 | 2022-02-28 | 2022-02-28 | 2022-07-31 | 2023-02-01 | 2023-07-01 | 2024-07-31 | EC declaration of conformity for the Interoperability Constituents and EC certificates | 17
22 | Activity 3 - Tests completed | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2023-09-30 | 2024-04-01 | 2024-09-01 | 2024-09-01 | Test description and report | 70
23 | Activity 3 - Subsystem verification of the Varín - Košice - Čierna nad Tisou section | 2023-07-31 | 2023-07-31 | 2023-07-31 | 2023-07-31 | 2023-10-31 | 2024-05-01 | 2024-10-01 | 2024-10-01 | EC declaration of verification of the subsystem and EC certificates | 9
24 | Activity 3 - Authorisation of the Varín - Košice - Čierna nad Tisou state border section by a competent authority | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-12-31 | 2024-06-30 | 2024-12-31 | 2024-12-31 | Authorisation requested | 1
25 | Activity 3 - As-built documentation completed | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-09-30 | 2023-12-31 | 2024-06-30 | 2024-12-31 | 2024-12-31 | Copy of as-built documentation | 2
26 | Activity 4 - Communication plan approved | 2021-01-01 | 2021-01-01 | 2021-01-01 | 2021-01-01 | 2021-01-29 | 2021-01-29 | 2021-01-29 | 2021-01-29 | Acceptance letter from the beneficiary | 60 | 100 | 5
27 | Activity 4 - Final event organised | 2023-12-31 | 2023-12-31 | 2023-12-31 | 2023-12-31 | 2023-12-31 | 2024-12-31 | 2025-06-30 | 2025-06-30 | Media reports | 40
1 The percentage rating of technical progress is assigned to every milestone within each activity.