## Sheet1
Content note: a. X means means the beginning of the Implementation on the first day of the stated month and/or the end of the implementation on the last day of the stated month | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01
0.0 Platform
GUI
User rights
Mobile application for the residents
Tablet application for the crews
Reporting | bar: 2023-02-01; 2023-04-01; 2023-06-01; 2023-08-01; 2023-10-01
1.0 Module Electronic Evidence
Data analysis | bar: 2023-01-01
Data cleansing before Import | bar: 2023-01-01 to 2023-02-01
Creating data schemes | bar: 2023-02-01
Integration | bar: 2023-02-01
Data Import | bar: 2023-02-01 to 2023-03-01
Bin Storage system | bar: 2023-03-01 to 2023-04-01
Inventory control and passport | bar: 2023-05-01 to 2023-06-01
Lebel printing | bar: 2023-02-01
Change and lifecycle managment | bar: 2023-07-01
Trainnings | bar: 2023-03-01; 2023-05-01; 2023-07-01
2.0 Module Fleet Management
Module Implementation | bar: 2023-01-01 to 2023-03-01
Installation, configuration and activation of Monitoring units on LKW vehicles | 2023-01-01: 35; 2023-02-01: 35; 2023-03-01: 35
Installation, configuration and activation of Monitoring units on PKW vehicles | 2023-04-01: 15
Functionality of Bin collection confirmation via RFID | bar: 2023-03-01
PKW driving evidence | bar: 2023-06-01 to 2023-08-01
aSTAS - electronic evidence of LKW regular operation | bar: 2023-09-01 to 2023-11-01
Reporting | bar: 2023-02-01; 2023-04-01; 2023-06-01; 2023-08-01; 2023-10-01; 2023-12-01
Trainings | bar: 2023-03-01; 2023-05-01; 2023-07-01; 2023-11-01
3.0 Module Planning
Implementation of Planning module | bar: 2023-04-01
Plans creation - Manual | bar: 2023-05-01 to 2023-07-01
Plans creation - Automat | bar: 2023-12-01 to 2024-03-01
Waste collection Evaluation for Planning purposes | bar: 2023-12-01 to 2024-02-01
Planning mode - Rebeka | bar: 2024-02-01 to 2024-04-01
Planning mode - Delivery/Return/Exchange of Bins | bar: 2023-06-01 to 2023-07-01
Planning mode OLO TAXI | bar: 2024-04-01 to 2024-06-01
Planning mode VKK (High-capacity container) | bar: 2023-09-01 to 2023-11-01
Planning mode Free Style | bar: 2023-07-01 to 2023-09-01
4.0 Integration interfaces
NORIS | bar: 2024-01-01 to 2024-02-01
Softip - SQL | bar: 2023-11-01 to 2023-12-01
Protank - SQL | bar: 2023-01-01 to 2023-03-01
Passport & bin delivery (Android App - API) | bar: 2023-05-01 to 2023-06-01
Stand passport, Health & Safety app | bar: 2023-09-01 to 2023-10-01
eSTAS | bar: 2023-11-01 to 2023-12-01
RON - SQL | bar: 2023-04-01 to 2023-05-01
MS Sharepoint | bar: 2023-09-01 to 2023-10-01
Venzeo
CRM (MS Dynamics) | bar: 2024-01-01 to 2024-02-01
Vehicle maintenance software | bar: 2023-11-01 to 2023-12-01
Hemak Scalis (Weighbridge software) - SQL
MS PowerBI + reports creation | bar: 2023-04-01; 2023-06-01; 2023-08-01; 2023-10-01; 2023-12-01
Waze
Infopanels
Handheld Chainway RFID UHF 2D Sled - Android APP Bluetooth Integration | bar: 2023-05-01 to 2023-06-01
Xstation (Gas Station) - SQL | bar: 2023-03-01 to 2023-04-01
Google maps | bar: 2023-03-01 to 2023-04-01
Mapy CZ - API | bar: 2023-02-01 to 2023-03-01
ArcGIS | bar: 2023-12-01 to 2024-02-01
Samsung Android 10" Tablet | bar: 2023-04-01 to 2023-06-01