## Hárok1
ORIENTAČNÝ HARMONOGRAM
Aktivita (v mesiacoch) | T | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
1 PODPIS ZMLUVY
2 ODOVZDANIE PROJEKTOVEJ DOKUMENTÁCIE
3 ZABEZPEČENIE OBJEDNANIA MATERIÁLU, TECHNOLÓGIE, NÁHRADNÝCH DIELOV A ZABEZPEČENIE VÝROBNÝCH KAPACÍT NA MONTÁŽ*
4 VÝZVA NA ZAHÁJENIE MONTÁŽE DIELA NA MIESTE PLNENIA (HANISKA)
5 REALIZÁCIA/ MONTÁŽ ŽERIAVOV NA MIESTE PLNENIA (HANISKA)**
* V uvedenej lehote musí byť zo strany dodávateľa objednané všetko potrebné na to, vrátane výrobných kapacít, aby mohlo byť dielo konštruované na mieste plnenia (vrátane náhradných dielov).
** Čas medzi 3. a 5. mesiacom (10. až 20. mesiacom) slúži na prípravu za účelom efektívnej montáže žeriavov na mieste plnenia (Haniska).
INDICATIVE SCHEDULE
Activity (in months) | T | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26
1 CONTRACT SIGNATURE
2 FINALIZATION OF PROJECT DOCUMENTATION
3 SECURING OF MATERIAL, TECHNOLOGY, SPARE PARTS AND PRODUCTION CAPACITIES FOR INSTALATION*
4 INVITATION TO START OF WORKS IN HANISKA
5 REALISATION/ INSTALLATION OF CRANES IN HANISKA**
* Within the specified period, the supplier must order everything necessary for the installation of cranes in Haniska (including material, technology, production capacities, spare parts).
** The time between the 3rd and 5th month (10th and 20th month) is isued for preparation for the efficient installation of cranes in Haniska.