Contract for the Provision of Services and Performance of Construction Manager Activities for the Project “Modernisation and Greening of the WtEP OLO”

concluded pursuant to the provisions of Section 269(2) of Act No. 513/1991 Coll., Commercial Code, as amended

The Contract will be subject to negotiation and the final extent / content of the Contract will be the result of the negotiation.

Client:

Business name: 	Odvoz a likvidácia odpadu a.s., abbreviated name: OLO a.s.

Registered office:   		Ivanská cesta 22, 821 04 Bratislava

ID:   		00 681 300

TAX ID:   		2020318256

VAT reg. no.:  	SK2020318256

Managing Director:     Ing. Mgr. Ivan Sokáč , PhD., MBA - Chairman of the Board of Directors

Ing. Vladimír Lukáč - member of the Board of Directors

registered in the Commercial Register of the City Court Bratislava III, Section: Sa, File no.: 482 / B

(hereinafter referred to as the “Client”)

and

Provider:

Business name:

Registered office:

ID:

TAX ID:

VAT reg. no.:

Managing Director:

Bank connection:

Account number:

registered in

e-mail:

(hereinafter referred to as the “Provider”)

(the Client and the Provider are hereinafter also collectively referred to as the “Parties” or each individually as the “Party”)

PREAMBLE

IN VIEW OF THE FACT THAT:

  - the Client is interested in implementing the project “Modernisation and Greening of the WtEP OLO” and for the purpose of implementation of the said project to use the services of the Provider as the construction manager;

  - the Provider has become the winning / successful tenderer for the position of the construction manager in the public procurement procedure titled: “Engineering and Construction / Technological Supervision of the Modernisation and Greening of the WtEP” in accordance with the Public Procurement Act;

  - The Provider is interested in providing services and performing construction manager activities for the project “Modernisation and Greening of the WtEP OLO” for the Client during the entire period of realisation / implementation of the project “Modernisation and Greening of the WtEP OLO”;

the Parties enter into this Contract on the provision of services and performance of construction manager activities for the construction project “Modernisation and Greening of the WtEP OLO” as a result of the public procurement procedure pursuant to Section 94 of the Public Procurement Act (hereinafter referred to as the “Contract”) in the following wording:

Article I

DEFINITIONS

In the interpretation of the Contract, unless otherwise stated in the Contract or unless the context of the Contract indicates otherwise:

- terms and definitions shall have the meaning given to them throughout the Contract unless the context requires otherwise;

- terms and definitions shall apply equally to both the singular and the plural of the relevant defined term;

- references to articles, paragraphs or annexes shall be understood as references to an articles, paragraphs or annexes of the Contract;

- headings and tables of contents are included for convenience of reference only and shall have no bearing on the interpretation of the Contract.

The following capitalised words shall have the meanings indicated in the Contract:

“WtEP OLO site” - the site / area where the WtEP is located and at the same time the construction site of the Project, at Vlčie hrdlo 72, 821 04 Bratislava

“BIM model” - the information model of the Project Building to be created by the Construction Contractor using the BIM software tool for each stage of the Construction Contractor's Documentation (DBP / Construction Design, IPD, DAE)

“Confidential Information” - the meaning is set forth in Article XIII of this Contract

“DBP / Building Design” - means:

  - design documentation for the Building Permit Procedure (Building Act) or

  - certified construction design of the Project Building (Construction Act);

prepared / drawn up by the Construction Contractor depending on which applicable / effective Building Code legislation will apply / will be applied to the situation

“DAE” - documentation of the actual execution / construction of the Project after proper / complete completion of the Project Building, with the plotting of all the changes that have been made during the construction of the Project Building, prepared / drawn up by the Construction Contractor, which is the basis for the issuance of the Final Building Approval Decision / Certificate

“Construction Contractor's Documentation” - means collectively the DBP, IPD, ID, DAE, ATD as well as other documentation / documents directly related to the Project Building / installation / commissioning of the Project, prepared / drawn up by the Construction Contractor, including Permits to be provided by the Construction Contractor for the Client exclusively in Slovak language (if these documents are necessary for official purposes), in other cases primarily in Slovak or Czech language

“Provider's Documentation” - means collectively the DLU / Construction Plan, tender documentation for the public procurement procedure for the selection of the Construction Contractor, Land-Use Decision / Building Permit as well as other documentation / documents directly related to the provision / performance of the Provider's Services / Activities, including the Permits to be provided by the Provider for the Client exclusively in Slovak language (if these documents are necessary for official purposes), in other cases primarily in Slovak or Czech language

“DLU / Construction Plan” - documentation for the land-use procedure / building location procedure for the issuance of a land-use decision under the Building Act, or documentation of the construction plan under the Construction Act prepared / drawn up by the Provider

“EIA” - assessment of the Project from the point of view of its environmental impacts, in particular pursuant to Act No. 24/2006 Coll. on Environmental Impact Assessment and on amendments and the decision on the impact assessment within the framework of the inquiry procedure issued by the competent environmental authority

“Stage” - the relevant area (type) of provision of Services / Activities under this Contract

“Expert” - any of the Key Persons

“FIDIC” - the terms and conditions of the International FIDIC Contract Standards according to the FIDIC Yellow Book “Design and Build” under which the Construction Contractor shall be responsible for both the design and construction of the Project Building, as required by the Client

“Inflation” - represents the average annual (for the relevant calendar year) rate of inflation announced by the Statistical Office of the Slovak Republic in the form of the so-called core inflation

“Key Person” - a person of expertise within the Provider's company / establishment (in particular the statutory body, an employee) and / or Subcontractor:

  - who meets the technical / professional competence to provide / perform certain selected Services / Activities by the Provider under the Contract;

  - through / using whose technical / professional capacities the Provider will provide / perform certain selected Services / Activities within the meaning of the Contract; or

  - through whom technical / professional competence has been demonstrated by the Provider in the framework of the PP;

a list of whom is set out in Annex 3 to the Contract, as well as a new person not listed in Annex 3 to the Contract (if, during the term of the Contract, it becomes necessary to deploy such a person)

“Building Approval Decision / Certificate” - all necessary final decisions on the permission to use the completed Project Building / on the certification of the construction and technical suitability of the Project Building for the designed purpose issued by the competent building authority in accordance with the Building Code and related applicable legislation, depending on which applicable / effective legislation of the Building Code will apply / will be applied to the situation in question

“Commercial Code” - Act No. 513/1991 Coll., Commercial Code, as amended

“Remuneration” - shall have the meaning defined in Article V of this Contract

“Permits” - any and all permits / decisions of public authorities for the purpose of the Project Building / use of the constructed Project Building at any stage (including preparation), including the related file documentation within the meaning of the Building Code

“Substantial Milestone” - a binding time-frame / deadline for the implementation / performance of the Services / Activities for the Provider set by the Client in the Minutes of Consultation

“Building Code” - (i) generally binding legislation in force which forms part of the legal order of the Slovak Republic; and / or (ii) legislation of the European Union which is in force and effect in the Slovak Republic

“Project” - the process of preparation and implementation of the Project Building “Modernisation and Greening of the WtEP OLO” and commissioning of the completed project, which will modernise and greenise the Waste-to-Energy Plant (WtEP) by installing a new K3 boiler and a new common condensing turbo generator for the K2 (K1) and K3 boilers with an air-cooled condenser, which will include modification of the K1 and K2 boilers to be able to burn higher calorific value waste and at the same time installation of two separate systems (one common for K1 and K2 boilers and the other for the new K3 boiler) for dry cleaning of flue gases and installation of selective non-catalytic reduction supplemented by the selective catalytic reduction method and extension of the existing waste storage tank

“Takeover / Handover Protocol” - a written protocol signed by the Parties after the complete and proper provision / performance of all Services / Activities by the Provider for the Client in relation to the relevant Stage

“ID” - documentation of the Construction Contractor's organisational / technical / technological / control procedures for the purpose of the Project Building (in particular, the Construction Organisation Plan, the Technical Specifications, the Technological Installation Procedure, the Inspection and Testing Plan, etc.) prepared by the Construction Contractor

"Budget” - the total amount of remuneration offered by the Provider in the public procurement procedure for the total volume of Services / Activities under the Contract (i.e. ........................... EUR excluding VAT)

“Stage Budget” - the portion of the total Budget amount that is initially reserved / set for the relevant Stage as per the PP / Annex 2 to the Contract

“IPD” - Implementation Project Documentation / Project Building Execution Project prepared / drawn up by the Contractor

“Services / Activities” - the Services / Activities that the Provider is obliged to provide / perform for the Client according to the Description of the Subject of the Contract in terms of the PP “Engineering and Construction and Technological Supervision of the Modernisation and Greening of the WtEP”, for the purposes of the Project Building/ implementation, divided into Stages and defined / specified in terms of Annex 1 of the Contract and Article II of the Contract

“Building Permit” - all necessary final decisions on permitting the Project Building issued by the competent construction authority in accordance with the Building Code and related applicable legal regulations

“Building Code” - the Building Act (in the relevant material / temporal scope of validity / effectiveness in relation to the implementation for the Project / Contract) and / or the Construction Act (in the relevant material / temporal scope of validity / effectiveness in relation to the implementation for the Project / Contract)

“Building Act” - Act No. 50/1976 Coll. on Land-Use Planning and Building Regulations (Building Act), as amended

“ATD” - accompanying technical / operational documentation (in particular documents on construction modifications and maintenance of the building and its equipment) for the Project Building prepared by the Project Construction Contractor

“Subcontractors” - the persons / entities, as contractual partners of the Provider, through whom the Provider will provide / perform the selected Services / Activities under the Contract, some of whom will / may simultaneously provide / perform the selected Services / Activities through (i) Key Persons, as per Annex 5 of the Contract (including specification of the Services / Activities / Stages to be performed by the Provider through them)

“Stage Completion” - fulfilment of the conditions for the completion of the relevant Stage under Article III of the Contract (in particular for the purpose of invoicing the Remuneration)

“Land-Use Decision / Building Permit" - means:

  - final decision on the location of the Project Building issued by the competent construction authority in accordance with the Building Act, the EIA and related legislation, which (i) is in accordance with the DPR and which (ii) enables to obtain a valid Building Permit for the purpose of implementation / construction of the Project; or

  - final decision on the permission of the Project Building which is the result of a construction plan procedure in accordance with the Construction Act;

depending on what valid / effective legislation of the Building Code will apply / will be applied to the situation.

“PP” - public procurement for the Project Construction Manager within the scope of the contract “Engineering and Construction / Technological Supervision of the Modernisation and Greening of the WtEP”

“VAT Act” - Act No. 222/2004 Coll. on Value Added Tax, as amended

“Construction Act” - Act No 201 / 2022 Coll. on Construction, which is to enter into force on 01.04.2024 and which is to replace the Building Act

“Construction Contractor” - the general contractor for the construction of the Project selected by the Client in a separate public procurement process

"Contract” - this Contract for the provision of services and performance of construction manager activities for the project “Modernisation and Greening of the WtEP OLO”

“PPA” - Act No. 343/2015 Coll. on Public Procurement and on Amendments and Supplements to Certain Acts, as amended

“WtEP” - the waste-to-energy plant of the Client

Article II

SUBJECT AND PURPOSE OF THE CONTRACT

  - The subject of this Contract is:

  - setting the terms and conditions on the basis of which the Provider will provide / perform the Project Construction Manager Services / Activities for the Client;

  - the Provider's obligation to provide / perform the Project Construction Manager Services / Activities for the Client based on the terms and conditions of this Contract as well as the Client's requirements / instructions;

  - the Client's obligation to pay the Provider the Remuneration for the proper provision / performance of the Project Construction Manager Services / Activities in accordance with the relevant provisions of the Contract.

  - The purpose of the Contract is in particular the provision of expert support as well as construction and technical supervision of the construction by the Provider to the Client in the process of implementation / construction of the Project Building aimed at achieving the highest possible quality and efficiency of the Project Building and its subsequent operation. The Client expects and requires the Provider to contribute, by providing / performing the Services / Activities, to proper and successful implementation and completion of the Project and, within the framework of the foregoing, at the same time to contribute / strive at all times for the most efficient solution in terms of construction / implementation of the Project, inter alia by, in particular,

- proactively coordinating the design preparation and implementation / construction of the Project;

- being able to identify risks associated with the implementation / construction of the Project and effectively prevent them;

- responsibly assessing and addressing any potential changes to the implementation / construction of the Project;

- providing the Client with all necessary information on the progress of the preparation and implementation / construction of the Project in an appropriate manner and to the extent necessary;

- using persons with appropriate education, professional / expertise and managerial skills for the implementation.

  - The Provider undertakes to provide Project Construction Manager Services / Activities for the Client at his own expense / risk in accordance with the content / description of the subject of the Contract within the framework of the PP, the terms of this Contract, the instructions of the Client as well as the applicable legal regulations, in particular (but not exclusively) in the following stages and their extent, which are specified in Annex 1 to the Contract:

    - Stage No. 1 - Preparation of documentation to the extent necessary for the land-use decision / decision on the construction plan and representation of the investor in communication with the authorities in the process of obtaining the necessary permits

To be negotiated and the final extent / content (including Annex 1 of the Contract) will be the result of the negotiation process

    - Stage 2 - Provision of advisory and consultancy services to the investor in the preparation of the public procurement for the selection of the general contractor for the construction and preparation of tender documentation

To be negotiated and the final extent / content (including Annex 1 of the Contract) will be the result of the negotiation process

    - Stage 3 - Participation in the public procurement for the general construction contractor Design & Build

To be negotiated and the final extent / content (including Annex 1 of the Contract) will be the result of the negotiation process

    - Stage 4 - Review and approval of design documentation submitted by the general contractor at the DBP / Project Building, IPD design phases. Inspection and approval of the implementation documentation submitted by the general contractor

To be negotiated and the final extent / content (including Annex 1 of the Contract) will be the result of the negotiation process

    - Stage 5 - Performance of construction and technical supervision of the builder over the implementation of the construction, performance of independent professional technical inspection and activities of the safety and health protection at work coordinator

To be negotiated and the final extent / content (including Annex 1 of the Contract) will be the result of the negotiation process

    - Stage 6 - Review and approval of the accompanying technical documentation (ATD) submitted by the general contractor and review and approval of the design documentation submitted by the general contractor in the DAE design phases

To be negotiated and the final extent / content (including Annex 1 of the Contract) will be the result of the negotiation process

    - Stage 7 - Supervision of post-assembly cleaning operations, functional tests, commissioning of construction equipment for permanent operation and optimisation of technology, active participation in the take-over of the work from the general construction contractor

To be negotiated and the final extent / content (including Annex 1 of the Contract) will be the result of the negotiation process

    - Stage 8 - Advice and technical support during the first three years of operation

Represents the extent / content of support Services / Activities to the subject of this Contract that:

    - the Client is entitled (but not obliged) to additionally order from the Provider; and

    - the Provider is obliged to carry out / perform for the Client based on the order / request of the Client,

if the Client subsequently determines during the term of this Contract that they need to be performed/executed by the Provider (Client's option), subject to the following conditions:

- Extent / content of support Services / Activities:

Follows from Annex 1 of the Contract, wherein, however, the actual specification of the extent / content of the required support Services / Activities shall be as per the respective purchase order of the Client.

- The Client is entitled to order support Services / Activities from the Provider:

  - in their entire extent / content, as follows from point 1 / Annex 1 of the Contract, or only in some part thereof;

  - not later than 1 month before the expiry of the anticipated basic duration of the Contract as defined in Article XIV, paragraph 14.1 of the Contract.

- The Client shall order the support Services / Activities from the Provider via written order containing at least the following:

- Contract number

- Order number

- Client identification - business name, registered office, ID number

- Provider identification - business name, registered office, ID number

- Identification of the support Services / Activities

- Date of implementation of the support Services / Activities

- Date of issue of the order

- Identification and signatures of the authorised persons of the Client

- The price of the support Services / Activities, or the method of its creation / calculation

Determined in accordance with the unit hourly prices set out in Annex 2 of the Contract corresponding to Stage 5 of the Contract.

- Dates of performance of the support Services / Activities

Total duration of this stage not exceeding 3 (three) years.

- Other details in relation to the support Services / Activities not further specified in this Stage of the Contract shall be dealt with in the same / similar manner in terms of the relevant provisions of the Contract.

The extent / content of the Services / Activities within the meaning of this paragraph of the Contract / Annex 1 of the Contract is only demonstrative, on the basis of which the Provider is obliged, in addition to the specification of the Services / Activities specified in this article of the Contract, respectively in Annex 1 of the Contract, to simultaneously perform any other supporting / related Services / Activities necessary for the proper provision / performance of the Services / Activities as well as to achieve the object / purpose of this Contract, in particular on the basis of normal market practices, respectively the requirements / instructions of the Client.

  - The Provider acknowledges that:

  - in connection with the implementation of the Project Building, a digital BIM model of the Project Building will be created / updated by the Construction Contractor and, at the same time, all of the Construction Contractor's documentation for the Project in relation to BIM (DBP / IPD / DAE) will be prepared in accordance with the requirements of the BIM Building Information Modelling. Thus, based on the above, the Provider undertakes to provide / perform all relevant Services / Activities using BIM;

  - The Client is entitled to narrow the extent of performance in accordance with this Contract / Annex 1 to the Contract at any time, whereby the Provider shall inform the Client of this fact in advance in writing (by e-mail is sufficient) at least 30 days in advance - in the said context, no claims (in particular for damages, etc.) shall arise against the Client.

Article III

DEADLINES / IMPLEMENTATION SCHEDULE

  - The provision of the Services / Activities under this Contract shall be spread over the individual Stages, while the dates / schedule represent only the planned / anticipated dates for the performance of the Services / Activities under the Stages, which are defined in Annex 1 to the Contract, and are set out as planned / anticipated dates as follows:

Stage 1:

Planned / anticipated duration - 6 months or until the issuance of the Land-Use Decision (Building Act) or the Building Permit (Construction Act)

Completion of Stage 1 means that all of the conditions below have been met:

  - issuance of the Land-Use Decision (Building Act) or the Building Permit (Construction Act)

  - delivery of the Land-Use Permit (Building Act) or the Building Permit (Building Act) to the Client

  - fulfilment of the conditions pursuant to Article VII, paragraph 7.2, letter h) of the Contract

  - signing of the Takeover / Handover Protocol by the Parties

Stage 2:

Planned / anticipated duration - 6 months (Stage 2 will run concurrently with Stage 1), or until the announcement of a public procurement for the selection of the Construction Contractor

Completion of Stage 2 means that all of the conditions below have been met:

  - full completion of the public procurement preparation process (including the Design & Build tender documentation) and announcement of the public procurement for the Construction Contractor

  - fulfilment of the conditions pursuant to Article VII, paragraph 7.2, letter h) of the Contract

  - signing of the Takeover / Handover Protocol by the Parties

Stage 3:

Planned / anticipated duration - 12 months (depending on tenderers' objections during the public procurement process for the selection of the Construction Contractor) - Stage 3 will follow directly after Stage 2

Completion of Stage 3 means that all of the conditions below have been met:

  - full completion of the public procurement process for the Construction Contractor (including signing / conclusion of the relevant contract for the construction of the Project Building by the Client with the successful tenderer)

  - fulfilment of the conditions pursuant to Article VII, paragraph 7.2, letter h) of the Contract

  - signing of the Takeover / Handover Protocol by the Parties

Stage 4:

Planned / anticipated duration - 12 months

Completion of Stage 4 means that all of the conditions below have been met:

  - complete preparation / execution and approval of the final DBP, including issuance and delivery of the Building Permit (Building Act) to the Client, or complete preparation / execution and approval of the final Construction Design, including verification of the Construction Design and its delivery to the Client (Construction Act)

  - complete preparation / execution and approval of the final IPD

  - fulfilment of the conditions pursuant to Article VII, paragraph 7.2, letter h) of the Contract

  - signing of the Takeover / Handover Protocol by the Parties

Stage 5:

Planned / anticipated duration - 24 months (including K1 and K2 upgrades) - the start of this stage will overlap with Stage 4

Completion of Stage 5 means that all of the conditions below have been met:

  - complete execution of the Project Building (including the removal of any defects and imperfections pointed out during the takeover procedure) in accordance with the relevant Project construction contract with the Construction Contractor;

  - issuance and delivery of the Approval Decision / Certificate to the Client;

  - fulfilment of the conditions pursuant to Article VII, paragraph 7.2, letter h) of the Contract

  - signing of the Takeover / Handover Protocol by the Parties

Stage 6:

Planned / anticipated duration - 6 months - will run concurrently with Stage 5 (depending on the implementation of the Project Building and the takeover of the completed construction objects and operational files)

Completion of Stage 6 means that all of the conditions below have been met:

  - complete preparation / execution and approval of the final ATD and DAE

  - fulfilment of the conditions for Completion of Stage 5

  - fulfilment of the conditions pursuant to Article VII, paragraph 7.2, letter h) of the Contract

  - signing of the Takeover / Handover Protocol by the Parties

Stage 7:

Planned / anticipated duration - 6 months - will run concurrently with Stage 5 and / or Stage 6 (depending on the implementation of the Project Building and the takeover of the completed construction objects and operational files)

Completion of Stage 7 means that all of the conditions below have been met:

- fulfilment of the conditions for Completion of Stage 6

- issuance and delivery of the Approval Decision / Certificate to the Client;

- complete execution / completion of the executed Project Building by the Construction Contractor, including final takeover of the executed Project Building from the Construction Contractor without any defects or imperfections (after elimination of all identified / pointed out defects / imperfections of the Project Building)

- fulfilment of the conditions pursuant to Article VII, paragraph 7.2, letter h) of the Contract

- signing of the Takeover / Handover Protocol by the Parties

Stage 8:

Planned / anticipated duration - 3 years after completion of Stage 7 of the Contract, or after final takeover of the completed work of the Project Building as a whole from the Construction Contractor and commissioning

Completion of Stage 8 shall mean:

3 years after the completion of Stage 7 of the Contract, or after the final takeover of the completed Project Building as a whole from the Construction Contractor and commissioning

  - The Provider acknowledges that the performance of the Services / Activities under certain Stages will run concurrently as per this article of the Contract / Annex 1 of the Contract, whereupon the Provider shall be obliged to provide the Services / Activities as per the Contract in accordance with the above procedures.

  - The Provider is fully aware that the fulfilment of the deadlines / schedule of the Stages (even individually) of the Contract is mainly dependent on:

- the proper / timely performance / execution of activities on the Project by other contractors / contractual partners of the Client (in particular the Construction Contractor);

- the length of administrative proceedings of individual public administration bodies, in particular (but not exclusively) in relation to the proceedings on the location of the Project Building / land-use proceedings and the issuance of the Land-Use Decision (or the proceedings on the construction plan and the issuance of the decision on the construction plan), the proceedings on the issuance of the building permit, including the issuance of the Building Permit, as well as the proceedings on the permission to use the Project construction, including the issuance of the Final Building Approval / Certificate;

whereupon:

- the schedule for the provision / performance of the Services / Activities under each Stage may be extended (even unexpectedly);

- the Provider undertakes to provide / perform the Services / Activities for the Client throughout the duration of each Stage (irrespective of their duration), until due achievement / completion of the Stage as well as the actual implementation of the Project using the Provider's Services / Activities;

- the foregoing is not / cannot be a reason for termination or suspension of the provision / performance of the Services / Activities by the Provider;

- the deadlines for the provision / performance of the Services by the Provider under the individual Stages shall be reasonably extended, taking into account:

- possible delay in the provision of proper assistance by the Client - in the aforementioned context, if the Provider finds that he has not been supplied all the necessary documents / documentation by the Client to the extent necessary for the proper provision / performance of the Services / Activities, the Provider is obliged to immediately (within 24 hours) inform the Client of the said fact in writing (by e-mail is sufficient), including proper proof of the facts and requesting the necessary / essential assistance, otherwise he shall be liable for the damage caused thereby; for the period from the receipt of the Provider's written request to the Client to provide objectively necessary / essential assistance to the provision of such requested assistance by the Client to the Provider (by e-mail is sufficient), the deadline set for the performance of the Services / Activities by the Provider shall be extended; or

- delay of third parties within the meaning of points a), b) of this paragraph of the Contract;

if they have a direct impact on the proper provision / performance of the Services / Activities by the Provider.

  - For the provision / performance of the Services / Activities by the Provider within the timeframe of each Stage within the meaning of Paragraph 3.1 of this article of the Contract, the Provider shall be entitled to the remuneration solely within the meaning of Article V of the Contract, i.e. the Provider shall not be entitled to any additional remuneration / additional costs for the provision / performance of the Services / Activities and / or any other activities within the meaning of the Contract.

  - For the purpose of counting / commencement of the deadlines for the performance of the Stages, the Parties agree as follows:

  - the performance dates for Stages 1 and 2 shall commence on the day following the effective date of this Contract;

  - the performance dates for Stages 3-8 shall commence only upon prior written (by e-mail is sufficient) instruction of the Client delivered to the Provider (at least 30 days prior to the dates of commencement of the respective Stage) to commence the provision / performance of the Services / Activities; however, at the same time, until such instruction is given by the Client, the Provider shall inform the Client in writing (by e-mail is sufficient) of any potential impending damage or other delay in the performance of the Project that may arise as a result of the Client's failure to give an instruction pursuant to this paragraph of the Contract.

To rule out any doubt, the Parties agree that the Provider shall not be entitled to any Remuneration / Reimbursement for any fees or costs for the provision / performance of the Services / Activities for the commencement of which he has not received written instructions from the Client (except for Stages 1 and 2).

  - The dates for the performance of the relevant Services / Activities under each Stage shall be determined by the Client within the Minutes of Consultation which shall be binding on the Provider.

Article IV

PLACE OF PERFORMANCE

  - The place of performance of the Services / Activities shall be, according to their nature, in particular (but not exclusively):

- the registered office of the Provider or another place designated by the Provider;

- the registered office of the Client;

- the Project Building construction site / WtEP OLO site;

- the seats of public authorities (in particular in relation to the Land-Use Procedure, Building Permission Procedure, Final Approval Procedure);

- registered offices / operations of third parties, as contractors / contractual partners of the Client within the Project;

- for the provision of the Services / performance of activities during Stage 5 et seq. the location designated by the Client within a radius of 2 km (radius as the crow flies) from the WtEP OLO site, or the location designated by the Provider pursuant to clause 4.2.2. of this Article for the purpose of providing support activities (in particular administration) of the Provider in relation to the Services / Activities.

The Provider is obliged from Stage 5 onwards to ensure the performance of the Services / Activities through the physical presence of the Key Persons at the Project Building construction site / WtEP OLO site within the allocation of hours as per Annex 2 of the Contract, unless otherwise agreed by the Parties (in particular at the Consultations).

  - For the purpose of providing support activities (in particular administration) of the Provider in the provision / performance of the Services / Activities by the Provider during Stage 5 et seq., the Parties agree as follows:

    - The Client shall provide the Provider, at his own expense, with office space within a radius of 2 km (radius as the crow flies) from the WtEP OLO site to the following anticipated extent / content:

    - total floor area of approx. 100 m²;

    - office furniture;

    - sanitary facilities (toilet + shower);

(hereinafter also referred to as “Office Premises”), no later than 60 days before the commencement of Stage 5.

    - The Client shall invite the Provider in writing (by e-mail is sufficient) to take over the Office Premises within the period specified in clause 4.2.1 of this article of the Contract, and the Provider undertakes to take over the Office Premises from the Client within 15 days of receipt of the Client's invitation and to use them during the provision / performance of the Services / Activities. However, the Provider shall not be obliged to take over the Office Premises if he informs and duly proves to the Client in writing (by e-mail is sufficient) within the period for taking over the Office Premises within the meaning of the preceding sentence that he has himself (and at his own expense) arranged for his own Office Premises, which are located closer to the WtEP OLO site than the Office Premises - in this case, the conditions set out in clauses 4.2.3-4.2.7 below shall not apply.

    - The takeover / handover of the Office Premises shall be confirmed by the Parties in a written protocol, which shall include in particular:

- identification and condition of the premises;

- identification and condition of the equipment;

- identification and condition of the sanitary facilities;

- conditions of use of the premises, equipment, sanitary facilities (identical / similar to those set by the lessor of the Office Premises to the Client)

- conditions of access to the premises / movement around the area where the Office Premises are located (set by the owner of the Office Premises / area where the Office Premises are located);

- signatures of the representatives of the Parties;

(hereinafter also referred to as the “Protocol on the Office Premises”). Each Party shall receive one (1) signed copy of the Protocol on the Office Premises. The Protocol on the Office Premises will subsequently form an annex to this Contract.

    - The Provider shall be fully responsible for:

- the use of the Office Premises, entry to the premises / movement around the area where the Office Premises are located, in accordance with the Protocol on the Office Premises, and he shall be liable in full / undertakes to pay in full to the Client any claims (in particular for contractual penalty, damage, etc.) made against the Client by the owner of the Office Premises / the area where the Office Premises are located in the aforementioned connection;

- for any damage caused by the Provider (persons whom the Provider has allowed to use the Office Premises) to the Office Premises.

    - The Provider shall be obliged to use the Office Premises / arrange for the use of the Office Premises by the Key Persons / Subcontractors until termination of the Contract.

    - The Provider shall comply with the obligations set out in the Protocol on the Office Premises.

    - The Provider shall be obliged to hand over the Office Premises to the Client in a state of normal wear and tear within 30 days of the termination of the Contract and a written protocol signed by the Parties shall be drawn up on the handover / takeover of the Office Premises, where each Party shall receive one (1) signed copy.

Article V

REMUNERATION, ENTITLEMENT TO REMUNERATION, AMOUNT OF REMUNERATION AND METHOD OF PAYMENT

  - Remuneration

    - The Parties agree that the Provider shall be entitled to remuneration for duly and timely rendered / performed Services / Activities under the Contract, calculated / determined in accordance with Annex 2 to the Contract, which shall be in the nature of:

- lump sum / fixed total remuneration - this type of remuneration shall apply to Stage 1 and Stage 2

- hourly remuneration (for the actual number of hours of Services / Activities performed / worked) - this type of remuneration shall apply to Stage 3 - Stage 8;

(hereinafter also referred to as “Remuneration”). The statutory rate of VAT will be added to the Remuneration.  However, the maximum amount of the Remuneration under the Contract shall in no case exceed / will not exceed the Budget, whereupon the Provider shall not be entitled to the total / cumulative amount of the Remuneration under this Contract exceeding the total amount of the Budget.  In the event of a change of Key Person, the Remuneration relating to the relevant Key Person may be reduced in accordance with Article VI, paragraph 6.4, clause 6.4.2 of the Contract.

      - The remuneration may be changed / reduced due to a change in the Key Person / Key Persons in accordance with Article VI, paragraph 6.4, clause 6.4.2 of the Contract according to the procedure in accordance with Annex no. 6 of the Contract.

      - The Changed Remuneration will also be considered a Remuneration if the conditions for changing the Remuneration to the Changed Remuneration are met in accordance with Article VI, paragraph 6.4, clause 6.4.2 of the Contract.

    - The Remuneration shall include all / any costs / expenses of the Provider related to the provision / performance of the Services / Activities of the Provider under this Contract, including in particular (but not limited to):

- remuneration of Subcontractors, Key Persons;

- remuneration / fee for granting permissions / licenses to perform works related to the copyright work;

- labour costs;

- transport costs;

and the Provider shall not be entitled to payment of any amount in excess of the agreed Remuneration - the contractual Remuneration shall thus not be affected by any economic factors, in particular inflation, changes in exchange rates, interest rates, changes in the amount of costs caused by changes in legislation, unless otherwise expressly provided for in this Contract.

    - However, the Remuneration does not include any possible administrative fees (in particular in connection with administrative proceedings ), which shall be borne in their entirety by the Client - however, these shall be quantified and duly evidenced solely by the Provider and shall be subject to agreement of the Parties (by e-mail is sufficient) in advance. Subject to the Client's approval of the fees, the Client will pay the fees separately directly to the relevant entities / authorities concerned.

    - The Parties agree that the Budget will be increased once per calendar year only if the following conditions are met:

- the subject of the increase shall be the unit prices of the items in the Budget (in the given year, as currently stated in the Budget), exclusively by the inflation rate for the previous calendar year, if the inflation rate in the given period exceeded 5%, but by not more than 10% (even if the actual rate of inflation exceeded 10%), rounded down to the nearest euro (if the unit price of the Budget item increased by inflation will represent a sum with euro cents up to and including 49 euro cents) or rounded up to the nearest euro (if the unit price of the Budget item increased by inflation will represent a sum with euro cents up to and including 50 euro cents);

- the increase in the unit prices of the items in the Budget will be effective from March 1 of the respective calendar year;

- The Provider shall request the Client in writing to increase the unit prices of the items in the Budget by the rate of inflation always no later than February 20 of the calendar year in question;

- the increase shall apply / be applied exclusively to the unit prices of the items in the Budget under Stage 3. - Stage 8. Contracts, i.e. the unit prices of the items in the Budget relating to Stage 1 and Stage 2 shall be fixed and unchanged.

In the event that all of the above conditions are not met, there shall be no increase in the currently applicable unit prices of the items in the Budget within the relevant calendar year.

      - The Provider shall be entitled to request the Client to increase the unit prices of the items in the Budget no earlier than in the calendar year 2025 by the rate of annual inflation for the period of the calendar year 2024.

      - To rule out any doubt, the Parties acknowledge that the increase in the unit prices of the items in the Budget by the inflation rate shall apply only to the unit prices of the items in the Budget for the Services / Activities to be performed by the Provider after March 1 of the relevant calendar year in which the increase of the Remuneration by the inflation rate has occurred.

    - The Remuneration or prices determined in accordance with Annex 2 of the Contract shall be fixed and unchangeable for the duration of the Contract, unless the Contract expressly provides otherwise.

    - The Remuneration shall be due to the Provider only for the Services / Activities duly performed by him. However, the foregoing shall not apply to the Remuneration under Stage 3 - Stage 7, pursuant to which the Client guarantees the Provider's entitlement to Remuneration in the total / aggregate amount of 30% of the total / aggregate budget amount pertaining to the respective Stage (hereinafter also referred to as the “Guaranteed Remuneration”) even if, based on the volume of the total Services provided / performed by the Provider within the respective Stage, the Provider would be entitled to Remuneration in a lower amount / % than the Guaranteed Remuneration.

    - The remuneration shall be paid / provided by the Client under the respective Stage from the Budget / Stage Budget.  However, the Client shall be entitled in respect of the Budget / individual Stage Budgets (Stage 3 - Stage 7) as per his requirements:

- to transfer the unspent amounts of the Stage Budgets to the following / subsequent Stages, whereby the amount of the Stage Budgets of the following / subsequent Stages may be accumulated / increased;

- transfer the amounts of the Stage Budgets between the different Stages, i.e. from later Stages to earlier Stages.

Each Takeover / Handover Report at the completion of a Stage shall include a financial accounting of the Stage Budget, particularly for the purpose of identifying the spent / unspent Stage Budget, including transfers of Stage Budget amounts, etc. and the impact on the total amount of the Budget.

  - Payment terms

    - The Parties agree that the Client shall pay the Provider the Remuneration (part of the Remuneration) for duly provided / performed Services / Activities on the basis of the respective partial invoices of the Provider upon fulfilment of the following conditions:

      - Stage 1 and Stage 2

The Provider shall issue a total of three (3) invoices for the amount of the Remuneration relating to the relevant Stage / within the relevant Stage as follows:

      - The 1st and 2nd invoice will be issued for the period of two (2) calendar months of the provision / performance of the Services / Activities by the Provider within the Stage, always by the 15th day of the calendar month following the respective 2-month period to which the invoiced Services / Activities relate, but only when / after the following conditions are met:

- the invoice will be issued for 30% of the total amount of the Remuneration for the Stage in question as per the Stage Budget

Example: The total amount of 100% of the Stage Remuneration is EUR 1 million of which 30% is EUR 300 000. 10% of EUR 300 000 is EUR 30 000. The amount invoiced will therefore be EUR 270 000, i.e. 90% of EUR 300 000.

- A list of all Services / Activities, including their identification (as well as the identification of the Key Persons / Subcontractors by whom they were actually performed and the extent of performance) for the relevant 2-month period (hereinafter also referred to as the “Inventory of Services / Activities”), shall be submitted by the Provider to the Client (by e-mail is sufficient) by the 5th day of the next calendar month following the relevant 2-month period;

- the Inventory of Services / Activities for the relevant 2-month period submitted by the Provider shall be approved by the Client in writing (by e-mail is sufficient) - in the above context:

- The Client shall, within a period of 10 working days, review the Inventory of Services / Activities submitted by the Provider, on the basis of which:

- he will approve it - the condition will be fulfilled - the Parties agree that approval shall also be understood as a situation where the Client does not comment on the submitted Inventory of Services / Activities within the specified period; or

- he will not approve it and will send to the Provider in writing (by e-mail is sufficient) reasoned comments / reservations;

- if the Client does not approve the Inventory of Services / Activities submitted by the Provider, the Provider shall, within 5 working days, correct / modify the Inventory of Services / Activities taking into account the comments / reservations of the Client and send it to the Client in writing (by e-mail is sufficient) for reconsideration / comment;

- the procedure under this clause of the Contract shall be repeated until the Inventory of the Services / Activities has been approved by the Client - the Client shall not be entitled to refuse to approve the Schedule of Services / Activities without good reason;

(hereinafter also referred to as the “2-Month Invoice”);

      - The Provider shall issue, no earlier than after the expiry of the 1st calendar month following the calendar month in which the overall completion of the relevant Stage has occurred, a final 3rd invoice relating to the remaining 40% of the total amount of the Award for the relevant Stage as per the Stage Budget (hereinafter also referred to as the “Final Invoice”).

      - Stage 3 - Stage 8

The Provider shall issue invoices for the Remuneration for the Services / Activities provided / performed under the relevant Stage as follows:

    - The Provider shall issue an invoice for the Remuneration relating to the performance of the Services / Activities for the previous calendar month by the 15th day of each calendar month, but not before the following conditions have been met:

- the invoice will be issued for 90% of the total amount of the Remuneration as defined in the Monthly Inventory of Services / Activities (e.g. the entitlement to the Remuneration will be EUR 100,000, but the Provider will issue an invoice for EUR 90,000, i.e. 90%) for the preceding calendar month;

- A list of all Services / Activities, including their identification (as well as the identification of the Key Persons / Subcontractors by whom they were actually performed and the extent of performance) for the relevant 2-month period (hereinafter also referred to as the “Inventory of Services / Activities”), shall be submitted by the Provider to the Client (by e-mail is sufficient) by the 5th day of the next calendar month following the relevant 2. month period;

- the Monthly Inventory of Services / Activities for the previous calendar month submitted by the Provider shall be approved by the Client in writing (by e-mail is sufficient) in full (i.e. those that will be subject to a partial monthly invoice of 90% as well as those that will be subject to a final invoice after the conditions of Stage completion have been met in relation to the relevant Stage to the extent of the remaining 10%) - in the context set out above:

- The Client shall, within a period of 10 working days, review the Monthly Inventory of Services / Activities submitted by the Provider, on the basis of which he:

- he will approve it - the condition will be fulfilled - the Parties agree that approval shall also be understood as a situation where the Client does not comment on the submitted Inventory of Services / Activities within the specified period; or

- he will not approve it and will send to the Provider in writing (by e-mail is sufficient) reasoned comments / reservations;

- if the Client does not approve the Monthly Inventory of Services / Activities submitted by the Provider, the Provider shall, within 5 working days, correct / modify the Monthly Inventory of Services / Activities taking into account the comments / reservations of the Client and send it to the Client in writing (e-mail is sufficient) for reconsideration / comment;

- the procedure under this clause of the Contract shall be repeated until the Monthly Inventory of the Services / Activities has been approved by the Client - the Client shall not be entitled to refuse to approve the Monthly Inventory of Services / Activities without good reason;

(hereinafter also referred to as the “Monthly Invoice”);

    - The Provider shall issue, at the earliest after 1 calendar month following the calendar month in which the overall completion of the relevant Stage has been achieved, a separate final billing invoice relating to:

- an aggregate balance of 10% of the total amount of the Remuneration under the relevant Stage (to which the Provider shall only be entitled upon fulfilment of the conditions under this clause of the Contract - including for tax / accounting purposes):

- to which the Provider is entitled in terms of all Monthly Inventories of Services / Activities under the relevant Stage;

- which has not been invoiced in terms of the Monthly Invoices relating to the Monthly Inventory of Services / Activities under the relevant Stage;

- the amount representing the difference between the total / aggregate amount of the Remuneration (which is due to the Provider for the Services / Activities provided / performed under the relevant Stage) and the Guaranteed Remuneration - in the event that the total / aggregate amount of the Provider's Remuneration is less than the Guaranteed Remuneration ;

(hereinafter also referred to as the “Final Stage Invoice”).

  - Each invoice issued by the Provider shall include:

- all the essentials of a tax document as laid down under the relevant legislation (in particular Art. 222 / 2004 Coll. on Value Added Tax, as amended, and Act No. 431/2002 Coll. on Accounting, as amended);

- possibly:

- 2-month invoice and a copy of the Inventory of Services / Activities agreed by the Client;

- Monthly Invoice and a copy of the Monthly Inventory of Services / Activities agreed by the Client;

- Final Invoice and information as to what part of the total Remuneration has already been invoiced by the date of the Final Invoice in terms of the 2-monthly invoices;

- Final Invoice and information as to what portion of the total Remuneration has already been invoiced in terms of the Monthly Invoices by the date of the Final Invoice;

as otherwise the Client shall have the right to return the invoice without payment to the Provider, whereby during the period between the return of the invoice to the Provider and the delivery of the corrected invoice to the Client, the invoice due date shall not expire / shall be interrupted.

  - The due date of any invoice duly and lawfully issued by the Provider shall be 30 days from the date of its delivery to the Client. In relation to the issue of invoices, the Parties agree as follows:

- Electronic invoicing, whereby the electronic format of the invoices shall be PDF (hereinafter also referred to as “Electronic Invoice”);

- Electronic invoices will be sent to the Client electronically to the e-mail address: faktury@olo.sk.

The Client grants the Provider consent and authorisation under Section 71(1)(b) of the VAT Act to invoice the provision of Services / Activities under this Contract by means of an Electronic Invoice. The Contractor shall acquire the authority to issue an Electronic Invoice to the Client for the provision of the Services / Activities under this Contract and the Electronic Invoice shall fully substitute a paper invoice. To rule out any doubt, by sending an Electronic Invoice, the Contractor shall not be obliged to send paper invoices to the Client.

Article VI

SUBCONTRACTORS / KEY PERSONS

  - The Provider undertakes to provide / perform the Services / Activities under this Contract:

- independently; and / or

- through Subcontractors; and / or

- through Key Persons.

  - In the event of the Provider performing the Services / Activities through Subcontractors and / or Key Persons:

- The Provider shall be liable to the Client for the proper provision / performance of the Services / Activities in their entirety as if he was providing / performing them independently;

- The Provider is obliged to ensure that his Subcontractors / Key Persons do not claim against him a reservation of title to the provision / performance of the Services / Activities performed by them, otherwise he shall be liable to the Client for the damage caused thereby in its entirety.

- The Provider shall comply with the supply chain management measures submitted by the Provider to demonstrate compliance with the conditions for participation in the PP, as further described in Annex 4 to this Contract. This information is subject to the Provider's trade secrets, which the Client acknowledges. The Client shall be entitled to request information from the Provider in the above context at any time (by e-mail is sufficient) to demonstrate compliance with the supply chain management measures and the Provider shall provide it (by e-mail is sufficient) to the Client within 5 working days of receipt of the Client's request.

  - The Client is entitled to request at any time in writing (by e-mail is sufficient) the Provider to replace the Subcontractor in case of reasonably imminent non-fulfilment of the purpose of this Contract (part thereof) or delay of the deadlines for the fulfilment of the Stages, in particular due to the Subcontractor's failure to provide / perform the Services / Activities within the meaning of this Contract (to be provided / performed by the Subcontractor) in a proper and timely manner. Upon the Client's request, the Provider shall:

- propose to the Client another suitable company in place of the Subcontractor;

- replace the Subcontractor with another suitable entity after prior approval (by e-mail is sufficient) by the Client - the Client is not entitled to reject the proposed substitute other entity in place of the Subcontractor without reasonable objections / comments;

within 30 days of receipt of the Client's request to replace the Subcontractor.

    - The Provider is obliged to ensure that each of the Subcontractors is registered in the Register of Public Sector Partners (hereinafter also referred to as “PSP”), if the Subcontractor is subject to this obligation under the law (in particular, the Act on Public Procurement, Act No. 315/2016 Coll. on the RPSP) throughout the duration of the Contract, otherwise he shall be liable to the Client for any damage caused thereby.

6.3.2	The Provider shall, within 15 days from the date of entry into force of this Contract:

- set up at his own expense a so-called transparent bank account in a competent bank for the purpose of controlling the observance of correct relations in the supply chain with his Subcontractors in connection with the provision / performance of the Services / Activities within the meaning of the Contract, in particular in relation to the payment terms / control of the Provider's payments to his Subcontractors for the Services / Activities performed for the Provider within the meaning of the Contract, in order to protect / ensure the proper payments / reimbursements by the Provider to the Subcontractors (hereinafter also referred to as the “Transparent Account”); and at the same time

- grant the Client access to consult this bank account.

      - The Transparent Account shall constitute a bank account of the Provider established exclusively for payment transactions related to the provision / performance of the Services / Activities under the Contract and shall provide information that:

- the Client has made the Remuneration payments to the Provider in accordance with the relevant invoices; and that

- the Provider has reimbursed the Subcontractors for the relevant portion of the Remuneration paid to the Provider by the Client pursuant to (a) above in terms of the relevant Subcontractors' invoices.

      - The Provider shall provide the Client with a Transparent Account statement (by e-mail is sufficient) upon written request by the Client (by e-mail is sufficient) within 5 (five) days of the date of receipt of the request by the Provider, which shall contain at least the following information in relation to outgoing / debit transactions:

- amount of the payment transaction;

- date of the payment transaction;

- identification of the payment recipient - name / business name, bank account number.

      - The Contractor shall make all payments to his Subcontractors within 30 days of the date of credit of the relevant Remuneration payment to the Transparent Account by the Contracting Entity in accordance with clause 6.3.2.1 of this article of the Contract.

    - In accordance with Section 41(7) of the TSA, the Parties expressly agree as follows:

- If the Provider fails to fulfil his financial obligations towards the Subcontractor(s), i.e. fails to make payments of individual invoices for the Services / Activities performed for him by the Subcontractors known to the Client, and at the same time the Subcontractors request the Client to make direct payment for the Services / Activities rendered / performed duly and without defects, the Client shall ask (by e-mail is sufficient) the Provider to make the following payment within 7 days from the receipt of the request:

- duly demonstrate to the Client that he has no outstanding liabilities / invoices to his Subcontractors for the Services / Activities performed; or

- take corrective action and pay to the Subcontractors the required payables / invoices due for the Services / Activities performed.

- Until the Provider has duly fulfilled any of the Provider's obligations under paragraph (a) of this clause of the Contract, the Client shall be entitled to withhold / suspend payment of the Provider's outstanding receivables / invoices to the Client, whereupon the Client shall not be in default in the payment of his monetary obligations to the Provider and the Provider shall not have any claims against the Client in respect of the same.

- In the event of failure by the Provider to perform any of the Provider's obligations under sub-clause (a) of this clause of the Contract within the stipulated time, the Client shall be entitled, but not obliged, to satisfy the Subcontractor's claim against the Provider directly, whereupon the Client shall have a claim / claim against the Provider.   The basis for making direct payment to the Subcontractor shall be a written statement of approval by the responsible representative of the Client (the Client's Project Manager) of the duly rendered / performed Services / Activities which form the subject of the Subdelivery by the Subcontractor and direct payment to the Subcontractor. In the above context:

- the fact that the Client will make payment directly to the Subcontractor, the Client shall notify the Provider (by e-mail is sufficient) at least 5 days in advance - the Provider's right to payment of the Fee up to the amount of the payment made by the Client directly to the Subcontractor shall cease on the date of such payment by the Client to the Subcontractor, to which the Provider expressly agrees;

- in the event that the subject of direct payment by the Client to the Subcontractor is part of the Remuneration already invoiced by the Provider and paid to the Provider by the Client, the Client shall be entitled to claim / receive from such performance by set-off against another claim of the Provider against the Client (even outstanding) under the Contract or a security title within the meaning of Clause 9.6 of Article IX of the Contract.

- The Provider shall not set off against the Subcontractors' claims for the provision / performance of the Services / Activities under the Contract any claims arising from other contractual relationships between the Provider and the Subcontractors.

  - The Provider is obliged to ensure the provision / performance of selected Services / Activities in the performance of the Contract directly by the Key Persons:

- through whom technical / professional competence has been demonstrated by the Provider:

- in the framework of the PP (qualitative criterion K2: the recognized quality of the Key Person's previous experience and, in the case of the Project's Principal Engineer, his Qualities and Skills), or

- during the term of this Contract pursuant to clause 6.4.3 or 6.4.4 of this article of the Contract;

- who have been authorised to perform such Services / Activities under specific regulations, in terms of number, experience and professional qualifications in accordance with the qualification requirements set out in:

- in the PP documentation, or the requirements set out in Schedule 3 of the Contract - for the Key Persons identified in Schedule 3 of the Contract;

- the requirements set by the Client - for new Key Persons not identified in Annex 3 of the Contract;

during the term of the Contract starting:

- as per the Key Persons time schedules relating to the Key Persons under Clause 1. Annex 3 of the Contract;.

- as per the Key Persons time schedules relating to the Key Persons under Clause 2. Annex 3 of the Contract, as defined / specified by the Client in terms of this article of the Contract;

- within the terms of the time schedules, new Key Persons (if the need for a new Key Person arises later) not specified in Schedule 3 of the Contract, as defined / determined by the Client in terms of this article of the Contract.

    - The Provider undertakes to ensure that the Key Persons comply throughout the duration of the Contract with:

- qualifications requirements (technical / professional competence) to the extent as demonstrated by the Provider:

- in the framework of the PP (qualitative criterion K2: the recognized quality of the Key Person's previous experience and, in the case of the Project's Principal Engineer, his Qualities and Skills), or

- additionally within the meaning of clauses 6.4.3 and 6.4.4 of this article of the Contract;

- legal requirements (authorisations, certificates, licences, trades, etc.);

for the purpose of proper performance of the Services / Activities under this Contract.

    - Any changes to Key Persons may only be made on the basis of the following procedures:

      - in the event of interest / need to change the Key Person, the Provider shall send a written request for change of the Key Person to the Client containing at least the following:

- the reasons for the proposed change in the Key Person;

- a proposal for a new Key Person;

- proof of fulfilment of:

- all qualification requirements on the part of the newly proposed Key Person in full, as stated in the PP documents respectively as listed in Annex no. 3 of this contact (including originals or officially certified copies of documents proving the above facts) and at the same time:

- provision of documents for the evaluation of recognized quality (qualitative criterion K2: recognized quality of the previous experience of the Key Person and, in the case of the Project's Principal Engineer of the project, also his Properties and abilities in the same scope and manner as in the PP process) on the part of the newly proposed Key Person;

in relation to the Key Persons under point 1. Annex 3 of the Contract;.

- all technical competence / experience / professional competence within the meaning of Annex 3 of the Contract - in relation to the Key Persons under Point 2. Annex 3 of the Contract;.

- all technical competence / experience / professional competence required by the Client - Key Persons other than those specified in Annex 3 of the Contract;

(hereinafter also referred to as the “Proposal for Key Person Change”). At the same time, in the event that the original Key Person loses during the term of the Contract the legal prerequisites, i.e., ceases to meet the qualification requirements (technical / professional competence) within the meaning of the PP documents for the proper provision / performance of the Services / Activities within the meaning of this Contract / the PP Documents or Annex 3 of the Contract or the Client's Requirements, the Provider shall:

- inform the Client of the above fact immediately (within 2 days) in writing (by e-mail is sufficient);

- deliver to the Client the Proposal for Change of Key Person within 30 days from the date of receipt of the information in accordance with the preceding indent.

      - The Client will assess the received Proposal for Change of Key Person within 10 working days, based on which:

- the change of the Key Person will be agreed in writing - the Proposal for Key Person Change will be deemed approved also in the event that the Client does not comment on the Proposal for Key Person Change within the specified time (this does not apply if it is a change of a Key Person whose recognized quality (qualitative criterion K2) was the subject of evaluation of the offer within the PP); or

- the change of the Key Person will not be agreed in writing and the Client will raise appropriate reasoned objections to it or rejects it (stating the reasons) - in the event of raising appropriate reasoned objections, the Provider shall be obliged to modify the Proposal for Key Person Change within 10 working days and resend it to the Client for approval, even repeatedly.

      - The change of the Key Person is possible only upon written approval by the Client - the Client is not entitled to refuse the change of the Key Person without any reason.

      - If:

- the Provider proposes in the Proposal for Key Person Change a new Key Person whose, recognized quality (qualitative criterion K2: recognized quality of the previous experience of the Key Person and, in the case of the Project's Principal Engineer of the project, also his Properties and abilities) are with lower criteria / lower number of points compared to those acquired by the Provider for the original Key Person in the qualitative evaluation of the Provider's bid in the PP process; and

- the Client agrees to the change of the Key Person, who receives a lower number of points in the qualitative evaluation compared to the number of points obtained by the original Key Person, only after the qualitative evaluation of the new Key Person, i.e. evaluation of the experience of the new Key Person (and in the case of the Project's Principal Engineer of the project, also an evaluation of his qualities and abilities), which will be carried out based on the rules for evaluating the offer in the PP process;

then the Provider undertakes within each invoice related to the Provider's Remuneration for the Services/activities provided/performed, issued pursuant to Art. V, paragraph 5.2. of the Contract and the one following the acceptance of the new Key Person by the Customer, to apply a discount from the Reward (i.e. the invoice will contain the original amount of the Reward, the discount from the Reward and the invoiced amount of the Reward for payment after applying the discount) calculated by the procedures according to Appendix no. 6 of the Contract (hereinafter also referred to as "Changed Remuneration") and the Customer will subsequently pay the Provider the Changed Remuneration for the provision / performance of Services / activities. For the avoidance of doubt, the mechanism described in this point shall only apply if the Provider proposes as a new Key Person a person whose recognised quality is lower than the recognised quality of the Key Person indicated in the evaluation of the tender in the PP process. In case of the recognised quality of the proposed new Key Person is equal to or higher than the recognised quality of the Key Person identified in the evaluation of the tender in the PP process, the mechanism in this point shall not apply.

6.4.3 	The use / deployment of a Key Person, as defined under clause 2 of Annex 3 of the Contract, will take place subject to the following conditions:

- the Client notifies the Provider of the requirement / need to use / deploy the Key Person in writing (by e-mail is sufficient) at least 2 months prior to the date requested by the Client for deployment of the Key Person for the provision / performance of the Services / Activities;

- the Provider is obliged to deliver to the Client a proposal of the requested Key Person within 30 days of receipt of the Client's request (including demonstration of the technical competence / experience / professional competence as per Annex 3 of the Contract) of the proposed Key Person);

- the Key Person shall be selected / appointed in accordance with paragraph 6.4, clause 6.4.2, sections 2) and 3) of this article of the Contract.

6.4.4 	In the event that, during the Contract Term, an additional unavoidable need arises to expand the number of Key Persons and to include a new Key Person beyond the scope of Annex 3 to the Contract, the Parties agree that there the number of Key Persons shall be expanded to include a new Key Person, provided the following conditions are met:

- The need for a new Key Person shall be discussed at the Consultation;

- The Client directs the Provider to provide a new Key Person in the Minutes of Consultation;

- The Provider shall deliver to the Client a proposal for a new Key Person within 30 days of the Consultation (including demonstration of the proposed Key Person's expertise / qualification / experience), whereupon the selection / appointment of the new Key Person shall be subject to the procedure set out in paragraph 6.4, clause 6.4.2 , sections 2) and 3) of this article of the Contract - to rule out any doubt, the new Key Person must always be agreed in advance by the Client;

- The remuneration for the new Key Person shall be primarily determined by hourly remuneration by price modus (the most frequently occurring hourly rate for the Services / Activities or Key Person within the relevant Stage) within the Stage in which the new Key Person will be deployed - if the above procedure cannot be applied, the remuneration for the new Key Person shall be determined by the median.

6.5 	The Provider shall promptly (within 2 working days) notify the Client in writing (by e-mail is sufficient) of any change to the details in relation to any Subcontractor / Key Person.

6.6 	In accordance with Section 33(3) of the PP, the Client shall require that the Provider and the person referred to in Section 33(2) of the PP (hereinafter referred to as the “Other Person”), whose resources have been used to demonstrate the Provider's financial and economic standing under the PP, shall be jointly liable for the performance of this Contract. To this end, the Provider undertakes to include in the contract concluded with the Other Person pursuant to Section 33(2) of the Contract, inter alia, a provision from which it shall be unquestionably clear that the Provider and the Other Person are jointly liable for the performance of this Contract. For the purpose of ensuring the above obligation, the Provider has submitted to the Client upon signing of this Contract a written Agreement on Acceding to the Obligations (in the wording that was included in the public procurement dossier within the framework of the PP) in three (3) copies signed by the Provider and the Other Person (hereinafter also referred to as the “Agreement on Acceding to the Obligations”). The Client shall sign all counterparts of the Agreement on Acceding to the Obligations within 10 days of the effective date of this Contract and deliver two (2) signed counterparts to the Provider.

Article VII

RIGHTS AND OBLIGATIONS OF THE PARTIES

  - The Provider declares / confirms, undertakes / warrants that he:

- has duly and properly acquainted himself with all the tender documents provided by the Client in the framework of the PP for the subject of the contract “Engineering and Construction and Technological Supervision of the Modernisation of the Combustion Boilers of the Incineration Plant , this Contract and its annexes as well as all the documents / dossier received from the Client for the purpose of provision / performance of the Services / Activities under the Contract, and has no objections / comments thereon;

- is aware of all technical, qualitative and other conditions necessary for the proper performance of his obligations arising from the Services / Activities under this Contract;

- has duly acquainted himself with the entire scope / content of the Services / Activities as per Article III as well as Annex 1 to the Contract and the same is clear and understandable to him;

- has sufficient / appropriate professional / specialist skills / knowledge and capacity (including Key Persons) required for the proper provision / performance of the Services / Activities under this Contract, also in relation to the technical / professional competence and capacity in the framework of the PP (Key Persons) demonstrated by him;

- possesses all necessary authorisations / permits for the purpose of proper provision / performance of the Services / Activities;

- there is no impediment of any kind preventing him from properly providing / performing the Services / Activities under this Contract;

- will provide / perform the Services / Activities properly, on time and to the required quality, in particular on the basis of:

- the Contract and its annexes;

- requirements and instructions of the Client;

- relevant STN / EN as well as Legal Regulations;

- occupational health and safety, fire protection and environmental protection regulations;

where the result of the performance of the Services / Activities will be properly provided / performed Services / Activities within the meaning of the Contract, proper performance / completion of the Stages as well as proper and complete performance / completion of the Project;

- in the performance / provision of the Services / Activities, no interference with the rights / legally protected interests of third parties (in particular the intellectual property rights of third parties related to intellectual creation) as well as no violation of generally binding applicable legal regulations will take place;

he is otherwise liable for the damage caused to the Client in its entirety. In the above context:

- in the event of any claims (in particular sanctions, fines, compensation for damages) made by a third party due to a violation of its rights / legally protected interests, or valid Legal Regulations, the Provider is obliged to immediately (within 24 hours) inform the Client of this fact in writing (by e-mail is sufficient) and at the same time to fully indemnify / protect the Client against any such claims of the third party, or to fully satisfy the claims of the third party independently, otherwise he shall be liable for the damages caused thereby;

- if the Client's instruction or request would be contrary to the legal regulations, the Provider is obliged to inform the Client of the said fact immediately (within 24 hours) in writing (by e-mail is sufficient).

  - In particular, the provider is obliged to:

  - provide / perform the Services / Activities properly and with due professional / expert care at his own cost and risk, in particular through Key Persons as well as other qualified persons;

  - provide / perform selected Services / Activities independently and / or through Subcontractors and / or through Key Persons - in case that the specifications of the PP or Annex 3 to the Contract or the Client's requirements imply that certain Services / Activities are to be provided / performed by Key Persons, the Provider is obliged to ensure the provision / performance of such Services / Activities exclusively through Key Persons in accordance with the terms of the Contract (in particular with regard to the content / scope / time);

  - provide and perform the Services / Activities under this Contract in accordance with the requirements / instructions of the Client and in accordance with the purpose to be achieved / pursued by the Services / Activities, unless this is contrary to legal regulations;

  - protect the goodwill / trade secrets and business interests of the Client known to him and act in accordance with this Contract;

  - inform the Client immediately (within 24 hours) in writing (by e-mail is sufficient) after he became aware (or could have become aware in the case of due professional care) of:

- material circumstances that may affect / have an impact on the proper performance of the Services / Activities;

- obstacles that prevent / may prevent him from properly performing the Services / Activities;

- material circumstances that may affect / have an impact on the interests of the Client in the performance of the Services / Activities;

- inappropriateness of the requirements / instructions of the Client given to the Provider in the performance of the Services / Activities which may have / have a negative impact on proper performance of the Services / Activities;

  - maintain confidentiality of all data / information obtained from the Client for the purpose of performance of the Services / Activities or in connection with the performance of the Services / Activities and not to use them for his own benefit or for the benefit of other persons;

  - act in such a way that no damage (especially to life, health, property, nature and environment) on the part of the Client or third parties is caused during the performance of the Services / Activities;

  - hand over to the Client at the end of the relevant Stage (as a condition of the completion of the Stage) all original Provider Documentation in connection with the performance of the Services / Activities under that Stage, in particular (but not limited to):

- LUD / Construction Plan;

- Land-use decision  / Building permit;

- tender dossier for the selection of the Construction Contractor;

- opinions drafted / drawn up by the Provider;

3x in paper form + in electronic form in editable format (doc;xlsm;dwg) as well as in .PDF format + on an information carrier (CD / Cloud / USB).

  - submit to the Client on an ongoing basis, for information purposes and in the manner agreed by the Parties (in particular, electronically or in paper form) the Provider's Documentation / Construction Contractor's Documentation relating to the implementation of the Project Building;

  - maintain a detailed list / schedule of the Services / Activities performed for agreement in relation to the calculation / invoicing of Remuneration;

  - at any time upon written (by e-mail is sufficient) request of the Client, provide the Client with any documents, information, data or other documentation that is in any way related to the provision / performance of the Services / Activities (e.g. analyses, budgets, graphs, tables with calculations, etc.);

  - not to allow the implementation of further phases of the Project (in particular the Project Building) without inspection and takeover of the part of the completed Project Building by the Client, in particular if such further activities would lead to the impossibility of inspecting the quality of the completed part of the completed Project Building (e.g. the part of the Project Building would be covered, etc.);

  - immediately (within 2 working days) notify the Client in writing (by e-mail is sufficient) of any breach / failure to properly perform / delay in the performance of the obligations of third parties (in particular the Client's contractual partners in relation to the implementation of the Project):

- the control / management of which is subject to the provision / performance of the Services / Activities by the Provider; and / or

- any failure / delay of which has / may have an impact on the proper provision / performance of the Services / Activities by the Provider under the Contract;

  - hand over to the Client without undue delay (not later than within 10 days) from the date of termination of this Contract, all items / dossier / documents / information, Provider Documentation, etc., received from the Client and / or procured by him for the Client during the term of the Contract; the handing over / takeover shall be evidenced by a report signed by the Parties, of which one (1) signed copy shall be given to each Party;

  - upon request (by e-mail is sufficient) of the Client delivered to the Provider at least 30 days in advance, the Provider is obliged to allow the Client to carry out an audit at the Provider in accordance with the methodology established by the Client 1x per calendar year (hereinafter also referred to as the “Provider Audit”) - the report with the results of the Provider Audit drawn up by the Client (hereinafter also referred to as the “Audit Report”) shall be delivered (by e-mail is sufficient) to the Provider and shall be binding for the Provider;

  - take corrective action as specified in the Audit Report within 60 days from the date of receipt of the Audit Report by the Provider.

  - The Client is obliged to:

  - hand over to the Provider all necessary / indispensable information / documentation / documents (including granting a power of attorney, if this is necessary for the proper performance of the Services / Activities, or a photocopy of the concluded contract with the Construction Contractor for the purpose of the Project Building) for the proper performance of the Provider's obligations under this Contract on the basis of written (by e-mail is sufficient) requests of the Provider;

  - pay Remuneration to the Provider duly and on time in accordance with the Contract.

  - The Client is entitled in particular (but not exclusively):

- to give instructions / assignments to the Provider in relation to the provision / performance of the Services / Activities under this Contract;

- to inspect the provision / performance of the Services / Activities for compliance or non-compliance with this Contract;

- to request the Provider to conduct an audit at the Provider in accordance with the methodology set by the Client 1x per calendar year.

  - The Provider shall participate 2x per calendar month in joint meetings / consultations with the Client regarding the progress of the Stages / Project as well as the provision / performance of the Services / Activities under this Contract (hereinafter also referred to as the “Consultations”). The date of each Consultation shall be notified by the Client (by e-mail is sufficient) to the Provider at least 5 days in advance, with information on whether the Client requires the presence of certain Key Persons at the Consultation (the Provider is obliged to arrange the presence of the relevant Key Person at the Consultation based on the Client's request). Based on the Consultation held:

- written minutes (including the attendance list of persons present) will be drawn up by the Provider within 3 days, which the Provider will send (by e-mail is sufficient) to the Client for approval - the Client will either approve the draft minutes or send (by e-mail is sufficient) to the Provider comments to the draft minutes, which the Provider will be obliged to incorporate and subsequently resend to the Client for approval - the minutes approved by the Client will be signed by the representatives of the Parties (hereafter also referred to as the “Minutes of the Meeting”;

- each Party shall receive one (1) copy of the Minutes of the Meeting;

- the Provider shall be obliged to comply with the following in the provision/performance of the Services / Activities:

- guidelines / conclusions;

- set deadlines for the provision / performance of the Services / Activities;

resulting from the Minutes of the Meeting, which are binding on the Provider.

    - The Provider is obliged to prepare and deliver to the Customer (by e-mail is sufficient) a weekly report (related to the previous calendar week) on the 1st working day of the calendar week containing at least the following information:

    - information on the progress / process of the Project as well as the individual Stages and the results of the control of the Project implementation;

    - information on the provision / performance of the Services / Activities;

  - a list of problems and deficiencies identified during the implementation of the Project and proposed measures to eliminate the identified problems and deficiencies;

  - the current status of the Client's financial performance in relation to the Project;

(also referred to as “Report on Activity” or “Weekly Report”). The weekly reports will also be the basis for the Consultations of the Parties.

If the Weekly Report does not contain the elements according to this paragraph, the Client is entitled to ask the Provider (by e-mail is sufficient) to correct it and the Provider is obliged to submit a revised Weekly Report to the Client within 2 working days. During the period of the Provider's delay in submitting a proper Weekly Report to the Client, the Client shall not be obliged to pay any invoice due to the Provider until a proper Weekly Report has been submitted.

  - Conflict of interest

The Provider declares / confirms, undertakes / guarantees that from the date of commencement of the evaluation of bids submitted within the framework of the public procurement for the selection of the Construction Contractor during Stage 3 and subsequently during the entire duration of the Contract, the Provider will not be involved in any direct (within the scope of performance of activities on the Project) or indirect (within the scope of performance of activities outside the Project) contractual relationship with the Construction Contractor and / or any contractual partner of the Construction Contractor (throughout the supply and subcontracting chain) in the provision / performance of activities on the Project.

Article VIII

LIABILITY FOR DEFECTS

  - The Provider shall be fully liable to the Client for improper / defective provision / performance of the Services / Activities under the Contract (including those provided / performed by Subcontractors / Experts) (hereinafter also referred to as "Defective Services / Activities”).

  - Defective Services / Activities are understood to be in particular (but not exclusively) those that:

    - are not / have not been provided / performed properly / on time according to this Contract (in particular in accordance with the Contract, generally binding applicable legal regulations of the Slovak Republic, relevant EN / STN, as well as justified requirements / instructions of the Client) and / or do not have the usual characteristics for the type / kind of Service / activity; and / or

    - damage or may damage the rights and legitimate interests of the Client and / or third parties; and / or

    - contain other defects that have / may have a negative impact on the implementation of the Project or the performance of the Client's other contractors under the Project and / or the fulfilment of the purpose of this Contract;

and which occur:

- during the performance of the Services / Activities;

- on completion of the Services / Activities and their handover to the Client as part of the handover / takeover procedure;

- upon completion of the Services / Activities within the warranty period in relation to the LUD.

  - The Client shall have the right to have the defects in the Services / Activities removed free of charge and the Provider shall be obliged to remove the defects in the Services / Activities free of charge.  The Provider is obliged to remove the defects of the Defective Activities at his own expense even if he does not recognize them, in which case, if it is later found and proven that the Provider is not responsible for the defect, the Client shall agree to reimburse the costs of such removal of defects in favour of the Provider.

  - The Provider is obliged to proceed with the rectification of the defects of the defective Services / Activities:

  - during the performance of the Services / Activities - within the deadline set by the Client in accordance with a written (by e-mail is sufficient) request for correction to the Provider;

  - on completion of the Services / Activities within the takeover / handover procedure - within the deadline (which shall not be less than 3 days) specified by the Client in the written takeover report signed by the Parties;

  - during the warranty period - within 5 days after receipt of a written (by e-mail is sufficient) complaint from the Client to the Provider.

If the Provider does not remove the defects of the defective Services / Activities within the deadline according to the previous sentence, the Client is entitled to remove the defects of the defective Services / Activities through a third party at the Provider's expense; this is without prejudice to the Client's entitlement to contractual penalties under the Contract or compensation for damages caused thereby.

  - The warranty period for the LUD / Construction Plan is 24 months, which begins to run:

- in the moment of issuance of the Land-Use Decision and does not expire before the issuance of the Building Permit - this procedure shall apply in the event that the Building Act is applied; or

- in the moment of issuance of the decision on the Construction Plan and will expiry with the issuance of the Building Permit / verification of the Project Building.

  - A complaint report signed by authorised representatives of both Parties shall be drawn up on the elimination of the claimed defects of the Services / Activities within the meaning of paragraph 6.4 (b) and (c) of this article of the Contract, whereby each Party shall receive one (1) copy signed by the Parties.

Article IX

LIABILITY FOR DAMAGES / COMPENSATION

  - The Party that breaches its obligation under this Contract shall be obliged to compensate the damage caused to the other Party, unless it proves that the breach of the obligation was caused by circumstances excluding liability within the meaning of the Commercial Code.

  - Damage shall also be deemed to be loss which the injured Party has suffered by having to incur costs as a result of the other Party's breach of its contractual obligations.

  - The Provider shall be liable to the Client for any and all damages incurred by the Client, in particular:

- in the performance of the Services / Activities or in connection with the performance of the Services / Activities under the Contract;

- In the following form:

- a sanction imposed on the Client by public authorities or other entities; or

- in the form of an obligation to fulfil the Provider's obligation on the part of the Client instead of the Provider,

in particular as a result of a breach of this Contract or binding legal regulations of the Slovak Republic (i) by the Provider, or (ii) by the Client in direct connection with a breach of the Contract or binding legal regulations of the Slovak Republic by the Provider.

  - The claim for damages shall be due within 30 days from the date of delivery of a written (by e-mail is sufficient) request from the injured Party to the injuring Party, including proper proof of the occurrence of damage in causal connection with the act / failure to act of the injuring Party.

  - Insurance

    - The Provider has submitted to the Client upon signing the Contract:

  - a general liability insurance certificate for bodily injury or property damage to another person with a limit of insurance benefits of ........................ EUR (in words: .......................... EUR) for one insured event within the meaning of the Insurance Contract No. ..................... Issued by the insurance company ............................. (which is authorised to carry out insurance activities in the territory of the Slovak Republic);

  - an insurance certificate for liability insurance in connection with the performance of business activities / selected activities (professional liability) with a limit of insurance benefits of  ........................ EUR (in words: .......................... EUR) for one insured event within the meaning of Insurance Contract No. ..................... Issued by the insurance company ............................. (which is authorised to carry out insurance activities in the territory of the Slovak Republic);

(hereinafter also collectively referred to as the “Insurance”). The Provider is obliged to arrange a change to the Insurance in relation to the increase of the limit of the insurance benefits:

- to the new amount	........................ EUR (in words: .......................... EUR) for one insured event in relation to the Insurance within the meaning of point (a) of this paragraph of the Contract;

- to the new amount	........................ EUR (in words: .......................... EUR) for one insured event in relation to the Insurance within the meaning of point (b) of this paragraph of the Contract;

at the latest on the date of conclusion of the contract for the construction of the Project Building between the Client and the Construction Contractor.

    - The Provider is obliged to:

  - maintain the Insurance in force until the expiry of the term of this Contract under the terms and conditions set out in this paragraph of the Contract - the above shall also apply in the event of renewal of the existing Insurance or the conclusion of a new Insurance;

  - upon the Client's request (by e-mail is sufficient), provide the Client with confirmation of the existence of the Insurance within 3 working days.

    - For the purposes of the Insurance, an insurance company authorised to carry out insurance activities in the territory of the Slovak Republic shall be understood within the meaning of Act No. 39/2015 Coll. on Insurance and on Amendments and Supplements to Certain Acts exclusively:

    - an insurance undertaking carrying on insurance business on the basis of an authorisation to carry on insurance business granted by the National Bank of Slovakia; or

    - an insurance undertaking from another Member State established in the territory of another Member State which is authorised to carry on insurance business in its home Member State; or

  - a branch of an insurance undertaking from another Member State as an organisational unit of an insurance undertaking from another Member State located in the territory of the Slovak Republic;

    - The Provider is obliged to submit to the Client at any time upon written request (by e-mail is sufficient) of the Client without undue delay (within 3 working days) a valid insurance contract in relation to the Insurance, or confirmation of the insurance company on the existence of an insurance contract for the sum insured and confirmation of the proper payment of the insurance premium.

  - Bank guarantee / security

    - For the purpose of ensuring:

    - proper provision / performance of the Provider's Services / Activities under the Contract as well as all of the Provider's obligations under the Contract;

    - claims / liabilities of the Client against the Provider arising from the Contract during the Contract period / as well as after the termination of the Contract (fulfilment of claims made during the Contract period) in connection with the Contract, in particular:

- for a contractual penalty;

- for damages;

- for the release of unjust enrichment;

- in connection with making direct payments by the Client to the Subcontractors in lieu of the Provider in accordance with clause 6.3.3 of the Contract;

on the date of signing of this Contract by the Parties the Provider:

      - deposited to the Client's bank account held in: .........................., account no. SK............................  a financial security in the total amount of EUR 800,000.00 (in words: eight hundred thousand euros) (hereinafter also referred to as “Financial Security”). The Client shall be entitled to satisfy from the Financial Security any of his claims / liabilities against the Provider arising out of the Contract, whereupon the Parties have agreed that:

  - the Client shall notify (by e-mail is sufficient) the Provider within 5 days that he has satisfied his claim / liability from the Financial Security and at the same time he is entitled to ask the Provider to supplement the Financial Security up to the specified amount of EUR 800,000.00;

  - the Provider is obliged to supplement the Financial Security up to the full amount of EUR 800,000.00 within 10 days from the date of receipt of the information / request of the Client under point a) of this clause of the Contract;

  - the Client shall return the remaining amount of the Financial Security to the Provider:

- within 90 days from the date of completion of Stage 7 and at the same time satisfying all claims / liabilities of the Client against the Provider arising from the Contract; or

- within 10 days from the date of submission of the Bank Guarantee by the Provider to the Client.

or

      - submitted a bank guarantee to the Client (with the content / wording agreed by the Client) containing the following essentials:

- bank guarantee issued by a bank / branch of a foreign bank operating on the Slovak market;

- irrevocable bank guarantee;

- personal bank guarantee issued only for the Client and not transferable to third parties;

- the Bank's obligation to pay to the Client at the Client's first written request and without objection any amount up to the maximum amount of the Bank Guarantee;

- the total amount of the bank guarantee in the amount of EUR 800,000.00 (in words: eight hundred thousand euros) (maintained / supplemented up to the specified amount even in case of continuous drawing of the amount of the bank guarantee by the Client);

- the duration of the Bank Guarantee for a minimum of 3 years;

- the bank guarantee shall be governed by the law of the Slovak Republic and the courts of the Slovak Republic shall be given exclusive jurisdiction to adjudicate disputes;

(hereinafter also referred to as the “Bank Guarantee”).  The Provider shall maintain the Bank Guarantee in force until the end of Stage 7 and for further 90 days from the end of Stage 7.

Art. X

CONTRACTUAL FINES / PENALTIES

  - The Parties agree that in the event of any breach of any of the Provider's obligations:

    - to provide / carry out the Services / Activities in time within the deadlines set out in the Minutes of Consultation under the Contract, the Client is entitled to demand from the Provider a contractual penalty in the amount of EUR 500.00 (in words: five hundred euros) for each day of delay and each breach of contractual obligation (including repeatedly);

    - to provide / perform the Services / Activities within the deadlines set in the Minutes of Consultation in accordance with the Contract, which will result in the interruption of the performance / delivery on the Project by other contractual partners of the Client (in particular the Construction Contractor in relation to the performance of his activities under the contract for the construction of the Project concluded with the Client), the Client is entitled to demand from the Provider a contractual penalty in the amount of EUR 1,500.00 (in words: one thousand five hundred euros) for each day of delay and each breach of contractual obligation (including repeatedly);

    - to remove the defects of the defective Services / Activities within the meaning of Article VIII, paragraph 8.4 of the Contract, the Client is entitled to demand from the Provider a contractual penalty in the amount of EUR 300.00 (in words:  three hundred euros) for each day of delay and each breach of contractual obligation (including repeatedly);

    - to remedy the defects of the defective Services / Activities in accordance with Article VIII, paragraph 8.4 of the Contract, which will result in the interruption of performances / deliveries on the Project by other contractual partners of the Client (in particular the Construction Contractor in relation to the performance of his activities under the contract for the construction of the Project concluded with the Client), the Client shall be entitled to demand from the Provider a contractual penalty in the amount of EUR 1,500.00 (in words: one thousand five hundred euros) for each day of delay and each breach of contractual obligation (including repeatedly);

    - within the meaning of Article IV, paragraph 4.1 of the Contract, i.e. from Stage 5 to ensure the performance of the Services / Activities through the physical presence of Key Persons at the Project construction site / WtEP OLO site within the allocation of hours as shown in Annex 2 to the Contract, the Client is entitled to demand from the Provider a contractual penalty in the amount of EUR 500.00 (in words:  five hundred euros) for each day of delay and each breach of contractual obligation (including repeatedly);

    - within the meaning of Article IV, paragraph 4.2 of the Contract:

  - which is calculated in days, the Client is entitled to demand from the Provider a contractual penalty of EUR 200.00 (in words:  two hundred euros) for each day of delay and each breach of contractual obligation (including repeatedly);

  - which is not calculated in days, the Client is entitled to demand from the Provider a contractual penalty in the amount of EUR 2,000.00 (in words: two thousand euros) for each breach of contractual obligation (including repeatedly);

    - within the meaning of Article VI (except paragraph 6.4) of the Contract:

- which is calculated in days, the Client is entitled to demand from the Provider a contractual penalty of EUR 500.00 (in words:  five hundred euros) for each day of delay and each breach of contractual obligation (including repeatedly);

- which is not calculated in days, the Client is entitled to demand from the Provider a contractual penalty in the amount of EUR 5,000.00 (in words: five thousand euros) for each breach of contractual obligation (including repeatedly);

    - to provide / perform selected Services / Activities through Key Persons within the meaning of Article VI, paragraph 6.4, or Article VII, paragraph 7.2, letter b) of the Contract, the Client is entitled to demand a contractual penalty from the Provider:

- in the amount of EUR 500.00 (in words:  five hundred euros) for each day of delay in fulfilling the contractual obligation and each breach of the contractual obligation (including repeatedly);

- in the amount of EUR 750.00 (in words:  seven hundred and fifty euros) for each day of delay in fulfilling the contractual obligation and each breach of the contractual obligation (including repeatedly) starting from the 1st day of the fifth month of continuous breach of the said contractual obligation (i.e. if the breach of the contractual obligation continues for 4 months or more);

- in the amount of 1.5-times the contractual penalty compared to the contractual penalty within the meaning of point (b) for each additional calendar month of continuous breach of the contractual obligation referred to in point (b), beyond the limit referred to in point (b), e.g.:

- EUR 1,125.00 (1,5-times the amount of 750 EUR) for each day of delay in fulfilling the contractual obligation and for each breach of the contractual obligation (including repeatedly) starting from the 1st day of the sixth month of continuous breach of the said contractual obligation (i.e. if the breach of the contractual obligation continues for 5 months or more on a continuous basis);

- EUR 1,687.50 (1,5-times the amount of 1,125.00 EUR) for each day of delay in fulfilling the contractual obligation and for each breach of the contractual obligation (including repeatedly) starting from the 1st day of the sixth month of continuous breach of the said contractual obligation (i.e. if the breach of the contractual obligation continues for 6 months or more on a continuous basis);

    - within the meaning of Article VII, paragraph 7.2, point o), the Client is entitled to demand from the Provider a contractual penalty in the amount of EUR 5,000.00 (in words: five thousand euros) for each breach of the contractual obligation (including repeatedly);

    - within the meaning of Article VII, paragraph 7.2, point p), the Client is entitled to demand from the Provider a contractual penalty in the amount of EUR 500.00 (in words: five hundred euros) for each day of delay and each breach of contractual obligation (including repeatedly);

    - within the meaning of Article VII, paragraph 7.5 of the Contract:

    - attend the Consultation; or

    - ensure the attendance of the required Key Person at the Consultation;

the Client is entitled to demand from the Provider a contractual penalty in the amount of EUR 2,500.00 (in words: two thousand five hundred euros) for each breach of contractual obligation (including repeatedly);

    - in accordance with Article VII, paragraph 7.5(c) of the Contract (to follow the instructions / conclusions of the Record of Consultation):

- which is calculated in days, the Client is entitled to demand from the Provider a contractual penalty of EUR 500.00 (in words:  five hundred euros) for each day of delay and each breach of contractual obligation (including repeatedly);

- which is not calculated in days, the Client is entitled to demand from the Provider a contractual penalty in the amount of EUR 5,000.00 (in words: five thousand euros) for each breach of contractual obligation (including repeatedly);

    - in relation to the Weekly Report within the meaning of Article VII, paragraph 7.5, clause 7.5.1 of the Contract, the Client is entitled to demand from the Provider a contractual penalty of EUR 300.00 (in words: three hundred euros) for each day of delay and each breach of contractual obligation (including repeatedly);

    - in relation to the conflict of interests within the meaning of Article VII, paragraph 7.6 of the Contract, the Client is entitled to demand from the Provider a contractual penalty in the amount of EUR 50,000.00 (in words: fifty thousand euros) for each breach of contractual obligation (including repeatedly);

    - under Article IX, paragraph 9.5, point 9.5.1 or Article IX, paragraph 9.5, point 9.5.2, letter b) of this Contract, the Client is entitled to demand from the Provider a contractual penalty in the amount of 500 EUR (in words: five hundred euros) for each day of delay and each breach of contractual obligation (including repeatedly);

    - within the meaning of Article IX, paragraph 9.5.2, point a) of this Contract, the Client is entitled to demand from the Provider a contractual penalty in the amount of EUR 5,000.00 (in words: five thousand euros) for each breach of contractual obligation (including repeatedly);

    - within the meaning of Article IX, paragraph 9.6, clause 9.6.1.2 of this Contract (to keep the Bank Guarantee valid for the specified period of time), the Client is entitled to demand from the Provider a contractual penalty in the amount of EUR 10,000.00 (in words: ten thousand euros) for each breach of the contractual obligation (including repeatedly);

    - in relation to Secrecy within the meaning of Article XIII of the Contract, the Client is entitled to demand from the Provider a contractual penalty in the amount of EUR 50,000.00 (in words: fifty thousand euros) for each breach of the contractual obligation (including repeatedly);

    - generally in accordance with the other provisions of the Contract (except as specifically provided in paragraphs 10.1.1-10.1.11 of this article of the Contract):

    - which is calculated in days, the Client is entitled to demand from the Provider a contractual penalty of  EUR 100.00 (in words:  one hundred euros) for each day of delay and each breach of contractual obligation (including repeatedly);

    - which is not calculated in days, the Client is entitled to demand from the Provider a contractual penalty in the amount of EUR 500 (in words: five hundred euros) for each breach of contractual obligation (including repeatedly);

    - to commence the provision / performance of the Services / Activities under Stage 8 on the basis of the Client's order, the Client shall be entitled to demand from the Provider a contractual penalty in the amount of EUR 1,000.00 (in words: one thousand euros) for each day of delay and each breach of contractual obligation (including repeatedly);

    - in case of breach of the Provider's obligation, on the basis of which the Client withdraws from the Contract pursuant to Article XIV, paragraph 14.2, point b) of the Contract, the Client is entitled to demand from the Provider a contractual penalty in the amount of EUR 500,000.00 (in words: five hundred thousand euros).

  - The exercise of the claim for the contractual penalty / payment of the contractual penalty is without prejudice to the Client's claim for damages against the Provider.

  - The contractual penalty is payable within 30 days from the date of receipt of a written request for its payment (by e-mail is sufficient) from the Client to the Provider.

  - In the event of the Client's delay in payment of the Fee on the basis of the submitted invoice, the Provider has the right to apply interest on late payment at the rate of 0.025% of the amount due for each day of delay.

Art. XI

CIRCUMSTANCES EXCLUDING LIABILITY / FORCE MAJEURE

  - Force majeure for the purposes of this Contract means an exceptional external event or fact:

- which could not have been foreseen prior to its occurrence and against which the Party could not have reasonably secured itself prior to the conclusion of the Contract;

- which is beyond the control of the Contracting Party;

- which, after its occurrence, could not reasonably have been avoided or averted by the Party;

- which cannot in principle be attributed to the other Party.

  - Force majeure may only involve exceptional events or circumstances if the conditions set out in paragraph 11.1 of this article of the Contract are met. Force majeure cases are mainly the following:

- pandemic of a dangerous disease;

- legislatively imposed conditions restricting the movement of people, such as quarantine obligations, area closures, bans on foreign nationals entering the country;

- declaration of an emergency situation or state of emergency, if the measures taken with their declaration have, or may have, an impact on the performance of the Provider's obligations;

- war, state of war (whether or not declared), invasion, other external hostilities, rebellion, terrorist action, revolution, riot, armed attacks, or civil war in a country, civil unrest, strike;

- exposure to war munition, explosive material, radioactive material, ionizing radiation, except when the use of these materials is attributable to the Provider;

- earthquakes, floods, volcanic activity, hurricane-force winds and other natural disasters with similar consequences or magnitude;

- change in the legal regulations which makes performance of the Contract, in whole or in part, impossible or unlawful.

  - If force majeure prevents or will prevent either Party from fulfilling its obligations under the Contract, that Party shall notify the other Party in writing (by e-mail is sufficient) without undue delay (within 24 hours). The Party affected by force majeure shall not be liable for breaches of its obligations for so long as it is prevented or hindered from performing them by force majeure. The time limit for the provision of Services / Activities by the Provider or the provision of assistance by the Client shall be extended by a mutually agreed period of time, but at least for the duration of the force majeure.

  - Force majeure shall not relieve the Party from liability for delay in the performance of its contractual obligations during the period prior to the occurrence of the circumstance excluding liability / force majeure. The effects of the exclusion of liability are limited only to the period during which the force majeure lasts.

Article XII

COPYRIGHT / LICENSE

  - The Parties are aware that in the performance of the Provider's Services / Activities for the Client under this Contract, works may be / will be created which shall be of the nature of the so-called copyright work within the meaning of the Act on Copyright. 185 / 2015 Coll. Copyright Act (in particular sections 65 et seq., 90, 91 et seq.), in particular in relation to the project for the Land-Use Decision (LUD) (hereinafter also collectively referred to as “Copyright Works”).

  - The Provider declares that:

- he (or his Subcontractors) is the sole holder and executor of the intellectual property rights (copyrights) to the Copyright Works;

- he is the authorised entity to grant the right to use / license the Copyright Works under this Contract;

- granting the right of use / licence to the Copyright Works in favour of the Client will not result in any damage / infringement of the intellectual property rights of a third party;

- he has not used any solutions, components and / or results of intellectual creative activity that are protected by intellectual property rights belonging to third parties to perform the Copyright Works; the foregoing does not apply to cases where the Provider holds relevant licenses from third parties, whereby the Provider declares that these licenses will also apply to the Customer in accordance with the purpose of the Copyright Works and this Contract.

  - The Provider undertakes:

- to ensure for the benefit of the Client continuous and uninterrupted exercise of the rights of use / licence to use the Copyright Works in accordance with the Contract;

- to indemnify the Client in full in the event that any third party claims any rights against the Client in connection with the Client's use of the Copyright Works under the Contract (in particular in relation to intellectual property rights).

  - The Provider grants to the Client an exclusive and unrestricted (with regard to territory, scope, manner, subject matter, time, personnel) permission to use the Copyright Works (hereinafter also referred to as “Licenses”) as follows:

- Unlimited scope - The Client is entitled to use the Copyright Works without limitation with regard to territory, time or personnel

- Unlimited manner - The Client is entitled to use the Copyright Works in an unlimited manner, in particular within the scope of Section 19 (4) of the Copyright Act, i.e.:

- processing of Copyright Works, their adaptation in any extent;

- combining the Copyright Works with other work(s);

- inclusion of Copyright Works in the database / databases, also pursuant to Section 131 of the Copyright Act;

- making copies of the Copyright Works;

- public distribution of originals or reproductions of the Copyright Works:

- by transfer of ownership

- by borrowing

- by hiring

- public presentation of the Copyright Works:

- by public display of the originals or reproductions of the Copyright Works;

- by public transmission of the Copyright Works.

but only for the purposes of the Project and its subsequent operation and maintenance;

- Unlimited time scope - The Client is entitled to use the Copyright Works for an unlimited period of time;

- Exclusivity - The Provider grants the Client Licenses to use the Copyright Works as exclusive Licenses.

  - The Provider undertakes not to grant any licenses / consents to third parties for the use of the Copyright Works and is obliged to refrain from exercising the property rights to the Copyright Works himself.

  - The Parties agree that the remuneration for the granting of the Licences to the Copyright Works is already included in the Remuneration and the Provider shall not incur any further claims against the Client in connection with the granting of the Licences.

  - The Provider grants the Client consent to grant Licences in favour of third parties to use the Copyright Works in the full scope of the Licences granted to the Client (hereinafter referred to as “Licenses”).

  - The Provider grants the Client consent to assign the Licenses to third parties (hereinafter referred to as the “Consent to General Assignment”).

  - The Client shall have the right to protect the Copyright Work for the duration of the Licences granted by all institutes of protection of intellectual property rights under the law of the Slovak Republic and on the territory of the Slovak Republic, or under the law of a third state / states and on the territory of a third state / states.

  - The property rights to the Copyright Works shall be exercised exclusively by the Client under his own name and on his own account. In the aforementioned context, the Provider also grants the Client consent to:

  - publish the Copyright Works;

  - label the Copyright Works with the name, trade name or title of the Client;

  - complete, make changes to, or otherwise interfere with the Copyright Works.

  - Upon termination of the Contract, the legal relations of the Parties with respect to the Copyright Works and the Licenses granted shall remain unaffected.

Article XIII

CONFIDENTIALITY

  - Confidential information for the purposes of this Contract shall mean:

  - any information of the Client, in particular of a commercial, legal, financial, manufacturing, technical, operational and other business nature (in particular information concerning suppliers and any business partners, technical, business and commercial information, information about employees and customers, business activities and business relationships, information about intellectual property / know-how, specifications, plans, sketches, models, samples, data, computer programs, software) in any form, whether or not captured in tangible or intangible form, which:

- are not publicly accessible;

- are to be treated, in the light of the circumstances known to the receiving Party at the time of disclosure, as confidential;

- have actual or at least potential material or immaterial value;

- are not commonly available in the relevant business circles are to be kept secret;

- disclosure of which, or the making accessible to third parties of which, could cause damage or other harm to the providing Party;

  - any and all information / dossier / documents provided by the Client to the Provider for the purpose of performance of the Services / Activities;

  - the results of the Provider's Services / Activities for the Client under the Contract, which are to be disclosed only to the Client and kept confidential by the Provider;

(hereinafter also referred to as "Confidential Information”).

  - The Provider agrees that during the term of this Agreement and after its termination for any reason he:

  - shall keep the Confidential Information secret / confidential and shall not use / misuse it for any purpose (both for its own benefit and for the benefit of any third party) other than the performance of its obligations under this Contract;

  - shall not disclose / provide the Confidential Information to any third party, except with the Client's prior written consent (e-mail is sufficient) or in accordance with paragraphs 13.3 of this article of the Contract;

  - shall not use / misuse the Confidential Information for any purpose (both for its own benefit and for the benefit of any third party) other than to perform his obligations under this Agreement;

  - shall not disclose the Confidential Information.

  - During the term of this Contract, the Provider may disclose Confidential Information to his employees, Subcontractors and other contractors (hereinafter referred to as the “Recipient”) to the extent such disclosure is absolutely necessary for the purposes of the Contract, in which case the Provider shall be liable for the Recipient's performance / breach of his obligations with respect to the Confidential Information in its entirety. However, prior to disclosing Confidential Information to a Recipient, the Receiving Party shall ensure that such Recipient is aware of and complies with the Receiving Party's confidentiality obligations under this Contract as if such Recipient were a party to this Contract.

  - The obligations of confidentiality within the meaning of paragraphs 13.1-13.3 of this article of the Contract shall not apply to Confidential Information that:

- are public knowledge; and / or

- are easily accessible to business entities operating in the Client's business area; and / or

- had been known to the Provider before they were disclosed by the Client; and / or

- are or become available to Provider in a different way than under this Agreement and without any restrictions on their use or disclosure; and / or

- have to be disclosed by law or by order of a court or authority having jurisdiction and competence in the matter.

In this case, the Provider is obliged to:

- provide Confidential Information only to the extent strictly necessary, in which case, prior to providing it, the Client must inform the Client in advance (by e-mail is sufficient) and agree with the Client on the scope of provision of the Confidential Information;

- take appropriate and meaningful measures to keep the Confidential Information disclosed as confidential as possible from unauthorised persons (e.g., by labelling the information disclosed as a trade secret, “confidential”, “top secret”, etc.).

  - In respect of any Confidential Information received from the Client, the Provider undertakes not to copy, reproduce, record in writing any part of it except where reasonably necessary.  Any originals, copies, reproductions, written or other records relating to the Confidential Information shall remain the property of the Client.

  - The provisions of the preceding paragraphs of this article of the Contract shall in no way limit the right to protection of trade secrets within the meaning of Section 17 et seq. Commercial Code.

  - The obligations of confidentiality with respect to Confidential Information under this Article of the Contract are for an unlimited period of time.

Article XIV

EXPECTED DURATION OF THE CONTRACT / TERMINATION OF THE CONTRACT

14.1	The Parties acknowledge that the duration of the Contract is:

- the basic period until the completion of Stage 7, but not less than the completion of the contractual relationship between the Client and the Construction Contractor for the construction of the Project (in particular the Contract for Works) - in the event that Stage 8 is not initiated;

- extended period until completion of Stage 8.

  - The Parties agree that the Contract shall terminate exclusively as follows:

- by written agreement of the Parties to terminate the Contract;

- by dissolution of one of the Parties without legal successor;

- by termination of the Contract by the Client, even without stating a reason, within a 3- month notice period, which shall begin on the 1st day of the following calendar month after the notice is delivered to the Provider;

- written withdrawal from the Contract by the Provider in the event that the Client is more than 60 days overdue on any invoice;

- written withdrawal from the Contract by the Client:

- if the Provider breaches any of his contractual obligations and fails to remedy them even within an additional period (not less than 10 working days) for remedy set by the Client in accordance with a written (by e-mail is sufficient) request of the Client delivered to the Provider;

- if the Provider assigns or transfers any of his rights / claims under this Contract to another person without the prior written consent of the Client;

- if the Provider loses his authorisation to carry out his business activities;

- if the Provider becomes insolvent or prolonged, or if any other situation arises on the Provider's side which, according to the applicable law, constitutes his bankruptcy;

- if a petition for restructuring or bankruptcy is filed against the Provider's assets or the court rejects the petition for bankruptcy due to the lack of assets to cover the costs of the bankruptcy;

- if the Provider enters into liquidation;

- if the Provider or an employee of the Provider demonstrably provides (directly or indirectly) a bribe, gift, gratuity, commission or other thing of value to anyone as an inducement or reward for doing or refraining from doing a certain act in connection with the Contract;

- if criminal prosecution and charges are initiated against the Provider or a member of the Provider's statutory body;

- if the Provider breaches any obligation of confidentiality under Article XIII of the Contract.

  - Withdrawal from the Contract shall be effective on the date of its delivery to the other Party.

  - Withdrawal from the Contract:

  - claims for payment of contractual penalties and compensation for damages arising from breach of the Contract shall not be affected;

  - all rights and obligations of the Parties under the Contract shall cease, except those specified in Section 351(1) of the Commercial Code;

  - Provider's claims to Remuneration for Services / Activities duly provided / performed under the Contract up to the date of termination of the Contract shall not be affected.

  - In the event of early termination of this Contract for any reason, the Provider shall provide / perform all Services / Activities to the extent necessary (which must not be delayed) so as not to delay the provision / performance of the Services / Activities and the related implementation of the Project until the third party designated by the Client as the new provider of the Services/Activities (hereinafter also referred to as the “New Provider”) is fully capable of replacing the Provider - however, the said Services / Activities may be provided / performed by the Provider only on the basis of the prior written (by e-mail is sufficient) instruction / consent of the Client.

    - In the event that the provision / performance of the Services / Activities is assigned to a New Provider, the Provider undertakes to provide to such person and the Client, at the Client's expense, all necessary / required assistance and to hand over all documents / dossier and information so as not to delay the provision / performance of the Services / Activities and the related implementation of the Project until the New Provider is duly qualified to replace the Provider in the provision / performance of the Services / Activities.

Article XV

DELIVERY AND CONTACT PERSONS

  - Withdrawal from the Contract, termination of the Contract, amendments to the Contract shall be made in writing (in paper form) and delivered to the other Party in person or sent by courier / post by registered mail, while other correspondence shall be sent between the Parties by e-mail communication. If:

  - the notice / correspondence has been delivered in person, it shall be deemed to have been delivered at the moment of its delivery to the addressee, or at the moment of refusal to receive it by the addressee;

  - the notice / correspondence has been delivered by courier, it shall be deemed to have been delivered at the moment of its delivery to the addressee, or at the moment of refusal to receive it by the addressee;

  - the notice / correspondence has been delivered by post, it shall be deemed to have been delivered on the day on which the addressee received it or refused to receive it, or on the third (3rd) day from the day on which the parcel was deposited at the post office, if the deposited parcel sent to the addressee's registered office address was returned to the sender;

  - the notice / correspondence has been sent by e-mail, it shall be deemed to have been received at the moment of transmission, in case of doubt on the next working day (to avoid any doubt, the Parties shall set their e-mail addresses to automatically send confirmation of receipt of each other's e-mail messages).

  - For the purposes of communication and delivery under the Contract, the Parties have appointed the following representatives of the Parties:

For the Client:

......................................., phone: ..................................., e-mail: ..................................

......................................., phone: ..................................., e-mail: ..................................

For the Provider:

......................................., phone: ..................................., e-mail: ..................................

......................................., phone: ..................................., e-mail: ..................................

The Parties are obliged to notify each other of any changes relating to their representatives. The Provider acknowledges and agrees that (i) communication between the Provider's representatives and the Client's representatives for the purposes of this Contract as well as (ii) all communications between the Provider, the Client and other entities involved in the Project (in particular the Construction Contractor) shall be made from e-mail addresses specifically established by the Client for the Provider as set forth in this clause of the Contract.

Article XVI

FINAL PROVISIONS

  - The contract enters into force on the date of its signing by both Parties and takes effect on the day following the date of its publication in the Central Register of Contracts within the meaning of Section 47a of Act No. 40/1964 Coll., the Civil Code, as amended, and Section 5a of Act No. 211/2000 Coll. on Free Access to Information and on Amendments and Supplements to Certain Acts (Act on Freedom of Information), as amended.

  - The Contract may only be amended by written amendments signed by the Parties in accordance with the relevant provisions of the LPA.

  - In case the subject of this Contract will be (co-)financed by a third party (EU funds), the Provider shall be obliged to tolerate the performance of any control / audit by the entity providing the subsidy for the financing of the subject of this Contract at any time during the validity of this Contract.

  - The Parties undertake to notify each other without undue delay of any changes concerning their identification and contact details specified in the Contract, the subject of activity, entering into liquidation or commencement of proceedings under Act No. 7/2005 Coll. on Bankruptcy and Restructuring and on Amendments and Supplements to Certain Acts, as amended. In the event of changes to the data specified in the header of the Contract and changes to the contact details, it is not necessary to conclude an amendment to the Contract. If any Party fails to comply with this obligation, it shall not be entitled to claim that it has not received any notice and shall be liable for any damage so caused.

  - The Provider is not entitled to:

  - set off his claims under the Contract with the Client's claims against the Provider;

  - assign any of his claims against the Client arising out of this Contract to a third party;

  - transfer the rights / obligations under the Contract to a third party;

without the prior written consent of the Client.

  - The Provider shall not be entitled to assign any of his rights or obligations under the Contract to third parties without the prior written consent of the Client.

  - This Contract and relations arising from or related to the Contract shall be governed by the Commercial Code and other generally binding legal regulations of the Slovak Republic.

  - All disputes arising out of or in connection with the Contract shall be resolved by the Parties primarily by mutual agreement. In the event of failure to reach an agreement or out-of-court settlement of the Parties, the courts of the Slovak Republic shall have jurisdiction to adjudicate disputes.

  - The Client, as the controller of personal data, hereby informs the Provider in accordance with Regulation (EU) 2016/679 of the European Parliament and of the Council of 27 April 2016 on the Protection of Natural Persons with Regard to the Processing of Personal Data and on the Free Movement of Such Data, repealing Directive 95/46/ EC (GDPR) and Act No.18/2018 Coll. on the Protection of Personal Data and on Amendments and Supplements to Certain Acts, that its personal data, or the personal data of its statutory body and contact persons under the present Contract as data subjects:

- are processed by him in the following scope: title, name, surname, function, signature, e-mail, phone number;

- are processes by him for the purpose of conclusion and performance of this Contract pursuant to Article 6(1)(b) GDPR, or Section 13(1)(b) of Act No. 18/2018 Coll. on the Protection of Personal Data and on Amendments and Supplements to Certain Acts.

- personal data may be disclosed to public authorities on the basis of special regulations; in other cases, personal data shall not be disclosed unless a special law provides otherwise or the data subject gives his or her voluntary consent;

- personal data will be processed and stored for the duration of the contractual relationship within the meaning of the Contract as well as until the expiry of the document retention period under the GDPR;

- personal data is not subject to profiling or automated decision-making;

- the transfer of personal data to a third country or to an international organisation does not take place;

- the person concerned has the right, upon written request or in person at the Client:

- to obtain confirmation as to whether personal data relating to him / her are being processed and, if so, the right to obtain access to those personal data relating to him / her;

- the right to rectification of incorrect personal data and / or the right to complete incomplete personal data;

- the right to have personal data erased (forgotten) if they are no longer necessary for the purposes for which they were collected or otherwise processed;

- the right to restrict the processing of personal data if:

- objects to the accuracy of the personal data during the period of verification of their accuracy;

- the processing is unlawful and objects to the erasure of the personal data and requests instead a restriction on its use;

- it is not necessary to further process the personal data but the data subject needs the personal data to prove, exercise or defend claims;

- the right to object to the processing of personal data by the controller;

- the right to obtain the personal data relating to him / her which he / she has provided to the controller, and also the right to transfer those data to another controller;

- the right to file a complaint with the Office for Personal Data Protection of the Slovak Republic, https://dataprotection.gov.sk, Hraničná 12, 820 07 Bratislava 27; phone: +421 /2/ 3231 3214; e-mail: statny.dozor@pdp.gov.sk,  if he / she believes that the processing of personal data by the controller is in breach of data protection legislation and his / her legal rights are therefore directly affected.

  - If any provision of the Contract becomes or is determined to be invalid, such invalidity shall not affect, to the fullest extent possible, the validity of the remaining provisions of the Contract. In such a case, the Parties shall promptly replace the invalid or unenforceable provision with a valid provision so as to achieve, to the maximum extent permitted by law, the same effect and result as was intended by the provision being replaced.

  - The Parties declare that the information provided in this Contract is in accordance with the actual situation as of the date of this Contract and that the persons signing this Contract on behalf of the Parties are the persons authorised to sign it.

  - The Provider agrees to ensure compliance with the “Rules of Conduct at the premises of OLO” published on the Client's website https://www.olo.sk/zasady-spravania-sa-v-areali-olo/.

  - The Provider shall, within seven (7) days from the date of signing of the Contract, sign and deliver to the Client's registered office the Anti-Corruption Clause published on the Client's website: https://www.olo.sk/profil-spolocnosti/integrovany-manazersky-system/.

  - The Contract shall be concluded in three (3) original copies, of which the Client shall receive two (2) original copies and the Provider one (1) original signed by the Parties.

  - The Parties declare that they have concluded the Contract on the basis of their free and serious will, and not under duress or on conspicuously unfavourable terms, and that they have duly acquainted themselves with its contents before signing and have understood it, in token of which they have affixed their handwritten signatures.

  - The following annexes form an integral part of the Contract:

Annex 1 –  Identification of services/activities (Description of the subject of the contract),

including the anticipated schedule for the performance of the services / activities

Annex 2 – Prices / price list for the provision of services / activities (Provider's

price offer)

Annex 3 –  List of Key Persons

Annex 4 –  Documents demonstrating the supply chain management

Annex 5 -   List of Subcontractors

Annex 6 – Formula for calculating reduced reward / discount from the reward

In Bratislava, date ......................    		In Bratislava, date ......................

Client:     				Provider:

_____________________________________   		_________________________________

Odvoz a likvidácia odpadu a.s.    			[Business name]

abbreviated form: OLO a.s.     				Name: [•]

Name: Ing. Mgr. Ivan Sokáč , PhD., MBA      	Position: [•]

Position: Chairman of the Board of Directors

_____________________________________

Odvoz a likvidácia odpadu a.s.

abbreviated form: OLO a.s.

Name: Ing. Vladimír Lukáč

Position: member of the Board of Directors