## Hárok1
Annex 2 to the Contract for the Provision of Services and Performance of Construction Manager Activities for the Project “Modernisation and Greening of the WtEP OLO” Prices / price list for the provision of services / activities (Provider's quotation)
Business name:
Registered office:
ID:
Contact person:
Contact person's cell phone number and email:
|  |  |  | Total hours of deployment: |  | 113664
Stage and manager's role in it | Key Experts | Estimated duration of the phase in months | Estimated number of working hours per month | Deployment coefficient of specialist | Hourly billing rate | Considered deployment in hours | Expert remuneration | Valuation requirement
1. Drawing up documentation to the extent necessary for the land-use decision and representation of the investor in communication with the authorities in the process of obtaining the necessary permits | Lead Specialist (Project's Principal Engineer [PPE]) | 6 | 160 | 0 |  | 0 |  | The stage shall be valued as price for the work
| Deputy Lead Specialist | 6 | 160 | 0 |  | 0
| Expert in complex architectural and engineering services | 6 | 160 | 0 |  | 0
| Expert in statics of building and load-bearing structures | 6 | 160 | 0 |  | 0
| Expert in civil infrastructure structures (engineer specialising in civil or engineering constructions) | 6 | 160 | 0 |  | 0
| Expert in technical, technological and energy equipment for buildings (engineer for technical, technological and energy equipment for buildings) | 6 | 160 | 0 |  | 0
| Boiler technology expert | 6 | 160 | 0 |  | 0
| Expert in mechanical engineering and technological processes | 6 | 160 | 0 |  | 0
| Expert in flue gas cleaning technology processes | 6 | 160 | 0 |  | 0
| Project manager | 6 | 160 | 0 |  | 0
| Expert in permitting procedures and legislation in the Slovak Republic | 6 | 160 | 0 |  | 0
| Expert in electrical and power engineering | 6 | 160 | 0 |  | 0
| Expert in MAR (I&C) | 6 | 160 | 0 |  | 0
|  |  | Total price for stage 1 |  | To be filled in by the contractor
2. Provision of advisory and consultancy services to the investor in the preparation and implementation of public procurement and preparation of tender dossier Design & Built | Lead Specialist (Project's Principal Engineer [PPE]) | 6 | 160 | 0 |  | 0 |  | The stage shall be valued as price for the work
| Deputy Lead Specialist | 6 | 160 | 0 |  | 0
| Expert in quality | 6 | 160 | 0 |  | 0
| HSE expert | 6 | 160 | 0 |  | 0
| Expert in civil infrastructure structures (engineer specialising in civil or engineering constructions) | 6 | 160 | 0 |  | 0
| Boiler technology expert | 6 | 160 | 0 |  | 0
| Expert in mechanical engineering and technological processes | 6 | 160 | 0 |  | 0
| Expert in flue gas cleaning technology processes | 6 | 160 | 0 |  | 0
| Project manager | 6 | 160 | 0 |  | 0
| Expert in permitting procedures and legislation in the Slovak Republic | 6 | 160 | 0 |  | 0
| Expert in electrical and power engineering | 6 | 160 | 0 |  | 0
| Expert in MAR (I&C) | 6 | 160 | 0 |  | 0
|  |  | Total price for stage 2 |  | To be filled in by the contractor
3. Participation in the Design & Built competition | Lead Specialist (Project's Principal Engineer [PPE]) | 12 | 160 | 0.5 | To be filled in by the contractor | 960 | #VALUE! | Valuation of the hourly rate of deployed experts
| Deputy Lead Specialist | 12 | 160 | 0.5 | To be filled in by the contractor | 960 | #VALUE!
| Expert in quality | 12 | 160 | 0.1 | To be filled in by the contractor | 192 | #VALUE!
| HSE expert | 12 | 160 | 0.1 | To be filled in by the contractor | 192 | #VALUE!
| Expert in civil infrastructure structures (engineer specialising in civil or engineering constructions) | 12 | 160 | 0.2 | To be filled in by the contractor | 384 | #VALUE!
| Boiler technology expert | 12 | 160 | 0.2 | To be filled in by the contractor | 384 | #VALUE!
| Expert in mechanical engineering and technological processes | 12 | 160 | 0.2 | To be filled in by the contractor | 384 | #VALUE!
| Expert in flue gas cleaning technology processes | 12 | 160 | 0.2 | To be filled in by the contractor | 384 | #VALUE!
| Project manager | 12 | 160 | 0.5 | To be filled in by the contractor | 960 | #VALUE!
| Expert in electrical and power engineering | 12 | 160 | 0.2 | To be filled in by the contractor | 384 | #VALUE!
| Expert in MAR (I&C) | 12 | 160 | 0.2 | To be filled in by the contractor | 384 | #VALUE!
4. Review and approval of design documentation submitted by the general contractor at the documentation for building permit, construction implementation documentation design phases. Inspection and approval of the implementation documentation submitted by the general contractor | Lead Specialist (Project's Principal Engineer [PPE]) | 12 | 160 | 0.8 | To be filled in by the contractor | 1536 | #VALUE! | Valuation of the hourly rate of deployed experts
| Deputy Lead Specialist | 12 | 160 | 0.8 | To be filled in by the contractor | 1536 | #VALUE!
| Expert in quality | 12 | 160 | 0.6 | To be filled in by the contractor | 1152 | #VALUE!
| HSE expert | 12 | 160 | 0.6 | To be filled in by the contractor | 1152 | #VALUE!
| Expert in civil infrastructure structures (engineer specialising in civil or engineering constructions) | 12 | 160 | 0.6 | To be filled in by the contractor | 1152 | #VALUE!
| Boiler technology expert | 12 | 160 | 0.6 | To be filled in by the contractor | 1152 | #VALUE!
| Expert in mechanical engineering and technological processes | 12 | 160 | 0.6 | To be filled in by the contractor | 1152 | #VALUE!
| Expert in flue gas cleaning technology processes | 12 | 160 | 0.6 | To be filled in by the contractor | 1152 | #VALUE!
| Project manager | 12 | 160 | 0.8 | To be filled in by the contractor | 1536 | #VALUE!
| Expert in electrical and power engineering | 12 | 160 | 0.6 | To be filled in by the contractor | 1152 | #VALUE!
| Expert in MAR (I&C) | 12 | 160 | 0.6 | To be filled in by the contractor | 1152 | #VALUE!
| Expert in statics of building and load-bearing structures | 12 | 160 | 0.6 | To be filled in by the contractor | 1152 | #VALUE!
| Expert in welding technology | 12 | 160 | 0.6 | To be filled in by the contractor | 1152 | #VALUE!
5. Performance of construction and technical supervision of the builder over the implementation of the construction, performance of independent professional technical inspection and activities of the safety and health protection at work coordinator | Lead Specialist (Project's Principal Engineer [PPE]) | 24 | 160 | 1 | To be filled in by the contractor | 3840 | #VALUE! | Valuation of the hourly rate of deployed experts
| Deputy Lead Specialist | 24 | 160 | 0.8 | To be filled in by the contractor | 3072 | #VALUE!
| Expert in quality | 24 | 160 | 0.8 | To be filled in by the contractor | 3072 | #VALUE!
| HSE expert | 24 | 160 | 0.8 | To be filled in by the contractor | 3072 | #VALUE!
| Expert in civil infrastructure structures (engineer specialising in civil or engineering constructions) | 24 | 160 | 0.8 | To be filled in by the contractor | 3072 | #VALUE!
| Boiler technology expert | 24 | 160 | 0.8 | To be filled in by the contractor | 3072 | #VALUE!
| Expert in mechanical engineering and technological processes | 24 | 160 | 0.8 | To be filled in by the contractor | 3072 | #VALUE!
| Expert in flue gas cleaning technology processes | 24 | 160 | 0.8 | To be filled in by the contractor | 3072 | #VALUE!
| Project manager | 24 | 160 | 1 | To be filled in by the contractor | 3840 | #VALUE!
| Expert in electrical and power engineering | 24 | 160 | 0.8 | To be filled in by the contractor | 3072 | #VALUE!
| Expert in MAR (I&C) | 24 | 160 | 0.8 | To be filled in by the contractor | 3072 | #VALUE!
| Expert in welding technology | 24 | 160 | 0.8 | To be filled in by the contractor | 3072 | #VALUE!
| Construction supervision | 24 | 160 | 1 | To be filled in by the contractor | 3840 | #VALUE!
| Machine supervision | 24 | 160 | 1 | To be filled in by the contractor | 3840 | #VALUE!
| Electrical supervision | 24 | 160 | 1 | To be filled in by the contractor | 3840 | #VALUE!
| I&C supervision | 24 | 160 | 1 | To be filled in by the contractor | 3840 | #VALUE!
| Construction part quality controller (OTK) | 24 | 160 | 1 | To be filled in by the contractor | 3840 | #VALUE!
| Machine part quality controller (OTK) | 24 | 160 | 1 | To be filled in by the contractor | 3840 | #VALUE!
| Electric and I&C part quality controller (OTK) | 24 | 160 | 1 | To be filled in by the contractor | 3840 | #VALUE!
6. Review and approval of the supporting technical documentation (ATD) submitted by the general contractor and review and approval of the design documentation submitted by the general contractor in the DAE design phases. | Lead Specialist (Project's Principal Engineer [PPE]) | 6 | 160 | 1 | To be filled in by the contractor | 960 | #VALUE! | Valuation of the hourly rate of deployed experts
| Deputy Lead Specialist | 6 | 160 | 0.8 | To be filled in by the contractor | 768 | #VALUE!
| Expert in quality | 6 | 160 | 0.8 | To be filled in by the contractor | 768 | #VALUE!
| HSE expert | 6 | 160 | 0.6 | To be filled in by the contractor | 576 | #VALUE!
| Expert in civil infrastructure structures (engineer specialising in civil or engineering constructions) | 6 | 160 | 0.8 | To be filled in by the contractor | 768 | #VALUE!
| Boiler technology expert | 6 | 160 | 0.8 | To be filled in by the contractor | 768 | #VALUE!
| Expert in mechanical engineering and technological processes | 6 | 160 | 0.8 | To be filled in by the contractor | 768 | #VALUE!
| Expert in flue gas cleaning technology processes | 6 | 160 | 0.8 | To be filled in by the contractor | 768 | #VALUE!
| Project manager | 6 | 160 | 1 | To be filled in by the contractor | 960 | #VALUE!
| Expert in electrical and power engineering | 6 | 160 | 0.8 | To be filled in by the contractor | 768 | #VALUE!
| Expert in MAR (I&C) | 6 | 160 | 0.8 | To be filled in by the contractor | 768 | #VALUE!
| Expert in welding technology | 6 | 160 | 0.6 | To be filled in by the contractor | 576 | #VALUE!
| Construction supervision | 6 | 160 | 0.6 | To be filled in by the contractor | 576 | #VALUE!
| Machine supervision | 6 | 160 | 0.6 | To be filled in by the contractor | 576 | #VALUE!
| Electrical supervision | 6 | 160 | 0.6 | To be filled in by the contractor | 576 | #VALUE!
| I&C supervision | 6 | 160 | 0.6 | To be filled in by the contractor | 576 | #VALUE!
| Construction part quality controller | 6 | 160 | 0.6 | To be filled in by the contractor | 576 | #VALUE!
| Machine part quality controller | 6 | 160 | 0.6 | To be filled in by the contractor | 576 | #VALUE!
| Electric and I&C quality controller | 6 | 160 | 0.6 | To be filled in by the contractor | 576 | #VALUE!
| Dedicated technical equipment quality controller | 6 | 160 | 0.6 | To be filled in by the contractor | 576 | #VALUE!
7. Supervision of start-up, post-assembly operations, functional tests and technology optimisation, active participation in the takeover of the work from the general contractor | Lead Specialist (Project's Principal Engineer [PPE]) | 6 | 160 | 0.8 | To be filled in by the contractor | 768 | #VALUE! | Valuation of the hourly rate of deployed experts
| Deputy Lead Specialist | 6 | 160 | 0.8 | To be filled in by the contractor | 768 | #VALUE!
| Expert in quality | 6 | 160 | 0.6 | To be filled in by the contractor | 576 | #VALUE!
| HSE expert | 6 | 160 | 0.6 | To be filled in by the contractor | 576 | #VALUE!
| Expert in civil infrastructure structures (engineer specialising in civil or engineering constructions) | 6 | 160 | 0.6 | To be filled in by the contractor | 576 | #VALUE!
| Boiler technology expert | 6 | 160 | 0.8 | To be filled in by the contractor | 768 | #VALUE!
| Expert in mechanical engineering and technological processes | 6 | 160 | 0.8 | To be filled in by the contractor | 768 | #VALUE!
| Expert in flue gas cleaning technology processes | 6 | 160 | 0.8 | To be filled in by the contractor | 768 | #VALUE!
| Project manager | 6 | 160 | 0.8 | To be filled in by the contractor | 768 | #VALUE!
| Expert in electrical and power engineering | 6 | 160 | 0.8 | To be filled in by the contractor | 768 | #VALUE!
| Expert in MAR (I&C) | 6 | 160 | 0.8 | To be filled in by the contractor | 768 | #VALUE!
| Expert in functional testing, commissioning and operation of complex power units | 6 | 160 | 1 | To be filled in by the contractor | 960 | #VALUE!
8. Advice and technical support for the first three years of operation (option only) | Lead Specialist (Project's Principal Engineer [PPE]) | 36 | 160 | 0.1 | To be filled in by the contractor | 576 | #VALUE! | Valuation of the hourly rate of deployed experts
| Deputy Lead Specialist | 36 | 160 | 0.1 | To be filled in by the contractor | 576 | #VALUE!
| Expert in quality | 36 | 160 | 0.05 | To be filled in by the contractor | 288 | #VALUE!
| HSE expert | 36 | 160 | 0.05 | To be filled in by the contractor | 288 | #VALUE!
| Expert in civil infrastructure structures (engineer specialising in civil or engineering constructions) | 36 | 160 | 0.05 | To be filled in by the contractor | 288 | #VALUE!
| Boiler technology expert | 36 | 160 | 0.05 | To be filled in by the contractor | 288 | #VALUE!
| Expert in mechanical engineering and technological processes | 36 | 160 | 0.05 | To be filled in by the contractor | 288 | #VALUE!
| Expert in flue gas cleaning technology processes | 36 | 160 | 0.05 | To be filled in by the contractor | 288 | #VALUE!
| Project manager | 36 | 160 | 0.05 | To be filled in by the contractor | 288 | #VALUE!
| Expert in electrical and power engineering | 36 | 160 | 0.05 | To be filled in by the contractor | 288 | #VALUE!
| Expert in MAR (I&C) | 36 | 160 | 0.05 | To be filled in by the contractor | 288 | #VALUE!
| Expert in functional testing, commissioning and operation of complex power units | 36 | 160 | 0.05 | To be filled in by the contractor | 288 | #VALUE!
[5 empty] | Total number of hours of deployment considered: | 113664
|  |  |  | Total cost: |  |  | #VALUE!
|  |  |  | Individual stage price checksum | Price for stage 1: |  | To be filled in by the contractor
[5 empty] | Price for stage 2: |  | To be filled in by the contractor
[5 empty] | Price for stage 3: |  | #VALUE!
[5 empty] | Price for stage 4: |  | #VALUE!
[5 empty] | Price for stage 5: |  | #VALUE!
[5 empty] | Price for stage 6: |  | #VALUE!
[5 empty] | Price for stage 7: |  | #VALUE!
[5 empty] | Price for stage 8: |  | #VALUE!