## Sheet1
Vysvetlivky: a. X znamená začiatok realizácie k prvému dňu v danom Mesiac (Month)i a/alebo ukončenie realizácie k poslednému dňu v danom Mesiac (Month)i b. prázdne polia budú upresnene počas prípravnej fázy projektu c. stanoveny harmonogram musi byt dodrzany, verejny obstaravatel umoznuje realizaciu danej polozky v harmonograme vo viacerych etapach za dodrzania zaciatku a konca danej polozky podla harmonogramu Content notes: a. X means the start of realisation on the first day of the stated month and/or the end of the realisation on the last day of the stated month b. blank fields will be specified in more detail during the preparation phase of the project c. the Schedule is fixed, Customer allow to start the realisation of a given item of the Schedule in several stages, but that the starting and finishing date of this item has to follow the Schedule | Mesiac (Month) 01 | Mesiac (Month) 02 | Mesiac (Month) 03 | Mesiac (Month) 04 | Mesiac (Month) 05 | Mesiac (Month) 06 | Mesiac (Month) 07 | Mesiac (Month) 08 | Mesiac (Month) 09 | Mesiac (Month) 10 | Mesiac (Month) 11 | Mesiac (Month) 12 | Mesiac (Month) 13 | Mesiac (Month) 14 | Mesiac (Month) 15 | Mesiac (Month) 16 | Mesiac (Month) 17 | Mesiac (Month) 18 | Mesiac (Month) 19 | Mesiac (Month) 20 | Mesiac (Month) 21 | Mesiac (Month) 22 | Mesiac (Month) 23 | Mesiac (Month) 24
0.0 Platforma (Platform)
GUI |  |  | X
Uživateľské oprávnenia (User rights) |  |  | X
Aplikácia na tabletoch pre Posádky (Tablet application for the crews) |  |  |  | X
Reporting |  | X |  | X |  | X |  | X |  | X
1.0 Modul Elektronická Evidencia (Electronic Registration Module)
Dátová / Funkčná analýza As Is & Future state + GAP (Data / Functional analysis As Is & Future state + GAP) | X | X | X
Čistenie údajov pred Importom (Data cleansing before Import) |  | X | X
Vytvorenie Dátovej štruktúry (Creation of Data model) |  |  | X
Integrácia (Integration) |  |  | X
Import údájov (Data import) |  |  | X | X
Skladový systém nádob (Bin/Containers Storage system) |  |  |  | X | X
Tlač nálepiek (Lebel printing) | [5 empty] | X
Zmenový a lifecycle management (Change and lifecycle managment) | [7 empty] | X
Školenie (Training) |  |  |  | X |  | X |  | X
2.0 Modul Fleet Management (Module Fleet Management)
Projektová príprava implementácie modulu (Project preparation of module implementation) | X
Implementácia modulu (Module implementation) |  | X | X | X
Instalácia, konfigurácia, aktivácia Monitorovacích jednotiek na LKW vozidla (Installation, configuration and activation of Monitoring units on LKW vehicles) |  | 25 | 25 | 25 | 25 | 25
Instalácia, konfigurácia, aktivácia Monitorovacích jednotiek na PKW vozidlá (Installation, configuration and activation of Monitoring units on PKW vehicles) |  |  |  |  | 15
Funkcionalita potvrdzovania výsypov cez RFID (Functionality of Bin collection confirmation via RFID) |  |  |  | X | X
Kniha jázd (PKW driving evidence - logbook) | [6 empty] | X | X | X
Elektronická STAS (eSTAS - electronic evidence of LKW regular operation - logbook) | [9 empty] | X | X | X
Reporting |  |  | X |  | X |  | X |  | X |  | X |  | X
Školenie (Training) |  |  |  | X |  | X |  | X |  |  |  | X
3.0 Modul Plánovanie (Module Collection Planning)
Projektová príprava implementácie modulu (project preparation of module implementation), requirements and real life operations on site audit |  |  |  | X | X
Implementácia modulu (Module implementation) | [5 empty] | X
Tvorba plánov - Manual (Plans creation - Manual) | [6 empty] | X | X | X
Tvorba plánov - Automat (Plans creation - Automat) | [13 empty] | X | X | X | X
Vyhodnotenie Zvozov pre plán (Waste collection Evaluation for Planning) | [13 empty] | X | X | X
Plánovací režim Rebeka (Planning regime - Rebeka) | [15 empty] | X | X | X
Plánovací režim Dodaj Odber Výmeny nádob (Planning regime - Delivery/Return/Exchange of Bins) | [7 empty] | X | X
Plánovací režim OLO TAXI (Planning regime OLO TAXI) | [17 empty] | X | X | X
Plánovací režim VKK (Planning regime VKK) | [10 empty] | X | X | X
Plánovací režim Free Style (Planning regime Free Style) | [8 empty] | X | X | X
4.0 Integračné rozhrania (Integration interfaces)
NORIS | [8 empty] | X | X
Stand passport, Health & Safety app | [8 empty] | X | X
CRM (MS Dynamics) | [12 empty] | X | X
Hemak Scalis (Weighbridge software) - SQL | [8 empty] | X | X
MS PowerBI + tvorba prvotnych reportov |  |  |  | X |  | X |  | X |  | X |  | X
Waze |  |  |  | X
Plus Codes |  |  | X | X
Google maps |  |  | X | X
Mapy CZ - API |  | X | X
ArcGIS | [8 empty] | X | X | X
Samsung Android 10" Tablet |  |  |  | X | X | X