## Asr info
CEF | Transport
Action Code | 2019-SK-TMC-0143-W
Exercise Year | 2024
Version | 1
Actual Action Start Date | 2020-03-05
Actual Action End Date | 2025-03-11
A. Maximum EU contribution (Art. 3) | €39,883,237.00
B. Pre-financing rate (Art. 4.1.2) | 50%
C. Maximum pre-financing payment (Art. 4.1.2) (=B*A) | €19,941,619.00
D. Maximum ceiling for the sum of pre-financing and interim payments (Art 4.1.3) (=80%*A) | €31,906,589.60
E. Sum of Previous Pre-financing Payments | €10,118,707.18
F. Sum of Interim Payments | €0.00
G. Sum of pre-financing and interim payments (E+F) | €10,118,707.18

## Eligible costs (€)
Update of the indicative breakdown of estimated eligible costs of the Action 2019-SK-TMC-0143-W (€)
|  |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | 2025 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
| 1 Public procurement and project management | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10000 | 10000 | 0 | 0 | 10000 | 10000 | 0%
|  | Total for activity 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 0 | 0 | 10000 | 10000 | 0%
| 2 Construction supervision and authorial supervision | 85
1 | Železnice Slovenskej republiky |  | 0 |  | 0 |  | 77862 | 77862 | 249295 | 249295 | 249978 | 249978 | 0 | 0 | 577135 | 577135 | 0%
|  | Total for activity 2 | 0 | 0 | 0 | 0 | 77862 | 77862 | 249295 | 249295 | 249978 | 249978 | 0 | 0 | 577135 | 577135 | 0%
| 3 Construction works | 85
1 | Železnice Slovenskej republiky |  | 0 |  | 0 |  | 1164 | 1164 | 8429894 | 6953216.82 | 37903262 | 39379939.18 | 0 | 0 | 46334320 | 46334320 | 0%
|  | Total for activity 3 | 0 | 0 | 0 | 0 | 1164 | 1164 | 8429894 | 6953216.82 | 37903262 | 39379939.18 | 0 | 0 | 46334320 | 46334320 | 0%
| Total eligible costs |  | 0 | 0 | 0 | 0 | 79026 | 79026 | 8679189 | 7202511.82 | 38163240 | 39639917.18 | 0 | 0 | 46921455 | 46921455 | 0%
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 79026 | 79026 | 8679189 | 7202511.82 | 38163240 | 39639917.18 | 0 | 0 | 46921455 | 46921455 | 0%
| Total cumulated eligible costs |  | 0 | 0 | 0 | 0 | 79026 | 79026 | 8758215 | 7281537.82 | 46921455 | 46921455 | 46921455 | 46921455 | 46921455 | 46921455 | 0%
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 79026 | 79026 | 8758215 | 7281537.82 | 46921455 | 46921455 | 46921455 | 46921455 | 46921455 | 46921455 | 0%

## Financing needs (€)
Financing needs of the Action 2019-SK-TMC-0143-W (€)
|  |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | 2025 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
| 1 Public procurement and project management | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | 8500 | 0 | 0 | 8500 | 8500 | 0%
|  | Totals for activity 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8500 | 8500 | 0 | 0 | 8500 | 8500 | 0%
| 2 Construction supervision and authorial supervision | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 66182.7 | 66182.7 | 211900.75 | 211900.75 | 212481.3 | 212481.3 | 0 | 0 | 490564.75 | 490564.75 | 0%
|  | Totals for activity 2 | 0 | 0 | 0 | 0 | 66182.7 | 66182.7 | 211900.75 | 211900.75 | 212481.3 | 212481.3 | 0 | 0 | 490564.75 | 490564.75 | 0%
| 3 Construction works | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 989.4 | 989.4 | 7165409.9 | 5910234.297 | 32217772.7 | 33472948.303 | 0 | 0 | 39384172 | 39384172 | 0%
|  | Totals for activity 3 | 0 | 0 | 0 | 0 | 989.4 | 989.4 | 7165409.9 | 5910234.297 | 32217772.7 | 33472948.303 | 0 | 0 | 39384172 | 39384172 | 0%
| Total financing needs |  | 0 | 0 | 0 | 0 | 67172.1 | 67172.1 | 7377310.65 | 6122135.047 | 32438754 | 33693929.603 | 0 | 0 | 39883236.75 | 39883236.75 | 0%
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 67172.1 | 67172.1 | 7377310.65 | 6122135.047 | 32438754 | 33693929.603 | 0 | 0 | 39883236.75 | 39883236.75 | 0%
| Total cumulated financing needs |  | 0 | 0 | 0 | 0 | 67172.1 | 67172.1 | 7444482.75 | 6189307.147 | 39883236.75 | 39883236.75 | 39883236.75 | 39883236.75 | 39883236.75 | 39883236.75 | 0%
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 67172.1 | 67172.1 | 7444482.75 | 6189307.147 | 39883236.75 | 39883236.75 | 39883236.75 | 39883236.75 | 39883236.75 | 39883236.75 | 0%

## Progress Overview
Progress Overview of the Action 2019-SK-TMC-0143-W (at accumulated level)
| 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024 |  |  | 2025
| Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress
Activity name | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR
Activity 1 | 0 | 0 | 12 | 0 | 0 | 75 | 0 | 0 | 95 | 0 | 0 | 95 | 100 | 0 | 100 | 100 | 0 | 100
Activity 2 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 100 | 50 | 57 | 100 | 60 | 100 | 100 | 98 | 100 | 100 | 100
Activity 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 15 | 18 | 100 | 53 | 100 | 100 | 100 | 100 | 100 | 100
For the Action | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 19 | 100 | 0 | 100 | 100 | 0 | 100 | 100 | 0