## Asr info
CEF | Transport
Action Code | 2019-SK-TMC-0143-W
Exercise Year | 2024
Version | 1
Actual Action Start Date | 05/03/2020
Actual Action End Date | 11/03/2025
A. Maximum EU contribution (Art. 3) | €39,883,237.00
B. Pre-financing rate (Art. 4.1.2) | 50%
C. Maximum pre-financing payment (Art. 4.1.2) (=B*A) | €19,941,619.00
D. Maximum ceiling for the sum of pre-financing and interim payments (Art 4.1.3) (=80%*A) | €31,906,589.60
E. Sum of Previous Pre-financing Payments | €10,118,707.18
F. Sum of Interim Payments | €0.00
G. Sum of pre-financing and interim payments (E+F) | €10,118,707.18

## Eligible costs (€)
Update of the indicative breakdown of estimated eligible costs of the Action 2019-SK-TMC-0143-W (€)
|  |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | 2025 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
| 1 Public procurement and project management | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000 | 10000 | 0 | 0
Total for activity 1
| 2 Construction supervision and authorial supervision | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 77862 | 77862 | 249295 | 249295 | 249978 | 249978 | 0 | 0
Total for activity 2
| 3 Construction works | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 1164 | 1164 | 8429894 | 6953216.82 | 37903262 | 39379939.18 | 0 | 0
Total for activity 3
Total eligible costs
1 | Železnice Slovenskej republiky
Total cumulated eligible costs
1 | Železnice Slovenskej republiky

## Financing needs (€)
Financing needs of the Action 2019-SK-TMC-0143-W (€)
|  |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | 2025 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
1 Public procurement and project management
1 | Železnice Slovenskej republiky
Totals for activity 1
2 Construction supervision and authorial supervision
1 | Železnice Slovenskej republiky
Totals for activity 2
3 Construction works
1 | Železnice Slovenskej republiky
Totals for activity 3
Total financing needs
1 | Železnice Slovenskej republiky
Total cumulated financing needs
1 | Železnice Slovenskej republiky

## Progress Overview
Progress Overview of the Action 2019-SK-TMC-0143-W (at accumulated level)
| 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024 |  |  | 2025
| Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress
Activity name | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR
Activity 1 | 0 | 0 | 12 | 0 | 0 | 75 | 0 | 0 | 95 | 0 | 0 | 95 | 100 | 100 | 100 | 100 | 100 | 100
Activity 2 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 13 | 50 | 57 | 57 | 60 | 100 | 100 | 98 | 100 | 100 | 100
Activity 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 18 | 15 | 53 | 100 | 100 | 100 | 100 | 100 | 100
For the Action | 0 | 0 | 12 | 0 | 0 | 30 | 0 | 0 | 50 | 19 | 16 | 70 | 100 | 100 | 98 | 100 | 100 | 100