## Hárok1
Type | Name of the activity | Start | End | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024 | [11 empty] | 2025
|  |  |  | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII.
A1 | Public procurement, authorisation procedures and detailed design | 2017-03-02 | 2024-10-31
M1 | Activity 1 - Start of the preparation of the tender documentation for the selection of the design contractor |  | 2017-03-02 | bar: 2017 III.
M2 | Activity 1 - Public procurement procedure for a detailed design contractor published |  | 2018-01-20 | bar: 2018 I.
M3 | Activity 1 - Contract signed for a design contractor |  | 2018-10-15 | bar: 2018 X,
M4 | Activity 1 - Start of the detailed design |  | 2018-10-17 | bar: 2018 X,
M5 | Activity 1 - Territorial decision and State expertise issued |  | 2020-03-17 | bar: 2020 III.
M6 | Activity 1 - Public procurement procedure for construction works published |  | 2022-07-29 | bar: 2022 VII.
M7 | Activity 1 - Public procurement procedure for a construction works supervision published |  | 2022-11-25 | bar: 2022 XI.
M8 | Activity 1 - Contract signed for construction works |  | 2023-03-22 | bar: 2023 III.
M9 | Activity 1 - Contract signed for external project management and audit support |  | 2020-07-07 | bar: 2021 VII.; 2022 VII.
M10 | Activity 1 - Contract signed for construction works supervision |  | 2023-07-03 | 2023 VII.: M10
M11 | Activity 1 - Contract signed for temporary billboards |  | 2023-08-21 | 2023 VIII.: M11
M12 | Activity 1 - Detailed design completed and approved |  | 2021-10-29 | 2021 X,: M12
M13 | Activity 1 - Contract signed for commemorative plaques |  | 2024-10-31 | 2024 X,: M13
A2 | Construction works and author supervision | 2023-07-05 | 2025-06-30
M14 | Activity 2 - Start of the Construction works supervision |  | 2023-07-05 | 2023 VII.: M14
M15 | Activity 2 - First interim supervision report on construction works completed |  | 2024-01-15 | 2024 I.: M15
M16 | Activity 2 - Second interim supervision report on construction works completed |  | 2024-07-14 | 2024 VII.: M16
M17 | Activity 2 - Completion of construction works supervision |  | 2025-06-30 | 2025 VI.: M17
M18 | Activity 2 - Completion of author supervision |  | 2024-12-31 | 2024 XII.: M18
M19 | Activity 2 - Taking Over certificate issued |  | 2024-12-31 | 2024 XII.: M19
A3 | Construction works | 2023-04-12 | 2024-12-31
M20 | Activity 3 - Start of the construction works on the Varín - Košice - Čierna nad Tisou section |  | 2023-04-12 | 2023 V.: M20
M21 | Activity 3 - Interoperability Constituents conformity |  | 2023-07-31 | 2023 VII.: M21
M22 | Activity 3 - Tests completed |  | 2024-09-01 | 2024 IX.: M22
M23 | Activity 3 - Subsystem verification of the Varín - Košice - Čierna nad Tisou section |  | 2024-10-01 | 2024 X,: M23
M24 | Activity 3 - Authorisation of the Varín - Košice - Čierna nad Tisou state border section by a competent authority |  | 2024-12-31 | 2024 XII.: M124
M25 | Activity 3 - As-built documentation completed |  | 2024-12-31 | 2024 XII.: M25
A4 | Project management and communication | 2021-01-29 | 2025-06-30
M26 | Activity 4 - Communication plan approved |  | 2021-01-29 | 2021 I.: M26
M27 | Activity 4 - Final event organised |  | 2025-06-30 | 2025 VI.: M27