## Asr info
CEF | Transport
Action Code | 2016-SK-TMC-0218-W
Exercise Year | 2024
Version | 1
Actual Action Start Date | 2017-03-02
Actual Action End Date | 2025-06-30
A. Maximum EU contribution (Art. 3) | €25,112,113.00
B. Pre-financing rate (Art. 4.1.2) | 50%
C. Maximum pre-financing payment (Art. 4.1.2) (=B*A) | €12,556,057.00
D. Maximum ceiling for the sum of pre-financing and interim payments (Art 4.1.3) (=80%*A) | €20,089,690.40
E. Sum of Previous Pre-financing Payments | €7,617,759.08
F. Sum of Interim Payments | €606,069.97
G. Sum of pre-financing and interim payments (E+F) | €8,223,829.05

## Eligible costs (€)
Update of the indicative breakdown of estimated eligible costs of the Action 2016-SK-TMC-0218-W (€)
|  |  | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | 2025 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
| 1 Public procurement, authorisation procedures and detailed design | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 731900 | 731900 | 335100 | 335100 | 512000 | 512000 | 21000 | 21000 | 56500 | 56500 | 451494 |  | 0 | 0 | 2107994 | 1656500 | -21.42%
|  | Total for activity 1 | 0 | 0 | 0 | 0 | 731900 | 731900 | 335100 | 335100 | 512000 | 512000 | 21000 | 21000 | 56500 | 56500 | 451494 | 0 | 0 | 0 | 2107994 | 1656500 | -21.42%
| 2 Construction works and author supervision | 85
1 | Železnice Slovenskej republiky |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 154996 | 141141.7 | 663752 | 310641.48 | 0 | 99361.26 | 818748 | 551144.44 | -32.68%
|  | Total for activity 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154996 | 141141.7 | 663752 | 310641.48 | 0 | 99361.26 | 818748 | 551144.44 | -32.68%
| 3 Construction works | 85
1 | Železnice Slovenskej republiky |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 16143442 | 9861633.1 | 10206478 | 29524425.91 | 0 | 0 | 26349920 | 39386059.01 | 49.47%
|  | Total for activity 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16143442 | 9861633.1 | 10206478 | 29524425.91 | 0 | 0 | 26349920 | 39386059.01 | 49.47%
| 4 Project management and communication | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 3500 | 0 | 0 | 7500 | 7500 | 0 |  | 256000 |  | 0 | 0 | 267000 | 11000 | -95.88%
|  | Total for activity 4 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 3500 | 0 | 0 | 7500 | 7500 | 0 | 0 | 256000 | 0 | 0 | 0 | 267000 | 11000 | -95.88%
| Total eligible costs |  | 0 | 0 | 0 | 0 | 731900 | 731900 | 338600 | 338600 | 512000 | 512000 | 28500 | 28500 | 16354938 | 10059274.8 | 11577724 | 29835067.39 | 0 | 99361.26 | 29543662 | 41604703.45 | 40.82%
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 731900 | 731900 | 338600 | 338600 | 512000 | 512000 | 28500 | 28500 | 16354938 | 10059274.8 | 11577724 | 29835067.39 | 0 | 99361.26 | 29543662 | 41604703.45 | 40.82%
| Total cumulated eligible costs |  | 0 | 0 | 0 | 0 | 731900 | 731900 | 1070500 | 1070500 | 1582500 | 1582500 | 1611000 | 1611000 | 17965938 | 11670274.8 | 29543662 | 41505342.19 | 29543662 | 41604703.45 | 29543662 | 41604703.45 | 40.82%
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 731900 | 731900 | 1070500 | 1070500 | 1582500 | 1582500 | 1611000 | 1611000 | 17965938 | 11670274.8 | 29543662 | 41505342.19 | 29543662 | 41604703.45 | 29543662 | 41604703.45 | 40.82%

## Financing needs (€)
Financing needs of the Action 2016-SK-TMC-0218-W (€)
|  |  | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | 2025 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
| 1 Public procurement, authorisation procedures and detailed design | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 622115 | 622115 | 284835 | 284835 | 435200 | 435200 | 17850 | 17850 | 48025 | 48025 | 383769.9 | 0 | 0 | 0 | 1791794.9 | 1408025 | -21.42%
|  | Totals for activity 1 | 0 | 0 | 0 | 0 | 622115 | 622115 | 284835 | 284835 | 435200 | 435200 | 17850 | 17850 | 48025 | 48025 | 383769.9 | 0 | 0 | 0 | 1791794.9 | 1408025 | -21.42%
| 2 Construction works and author supervision | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131746.6 | 119970.445 | 564189.2 | 264045.258 | 0 | 84457.071 | 695935.8 | 468472.774 | -32.68%
|  | Totals for activity 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 131746.6 | 119970.445 | 564189.2 | 264045.258 | 0 | 84457.071 | 695935.8 | 468472.774 | -32.68%
| 3 Construction works | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13721925.7 | 8382388.135 | 8675506.3 | 25095762.0235 | 0 | 0 | 22397432 | 33478150.1585 | 49.47%
|  | Totals for activity 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13721925.7 | 8382388.135 | 8675506.3 | 25095762.0235 | 0 | 0 | 22397432 | 33478150.1585 | 49.47%
| 4 Project management and communication | 85
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 2975 | 2975 | 0 | 0 | 6375 | 6375 | 0 | 0 | 217600 | 0 | 0 | 0 | 226950 | 9350 | -95.88%
|  | Totals for activity 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2975 | 2975 | 0 | 0 | 6375 | 6375 | 0 | 0 | 217600 | 0 | 0 | 0 | 226950 | 9350 | -95.88%
| Total financing needs |  | 0 | 0 | 0 | 0 | 622115 | 622115 | 287810 | 287810 | 435200 | 435200 | 24225 | 24225 | 13901697.3 | 8550383.58 | 9841065.4 | 25359807.2815 | 0 | 84457.071 | 25112112.7 | 35363997.9325 | 40.82%
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 622115 | 622115 | 287810 | 287810 | 435200 | 435200 | 24225 | 24225 | 13901697.3 | 8550383.58 | 9841065.4 | 25359807.2815 | 0 | 84457.071 | 25112112.7 | 35363997.9325 | 40.82%
| Total cumulated financing needs |  | 0 | 0 | 0 | 0 | 622115 | 622115 | 909925 | 909925 | 1345125 | 1345125 | 1369350 | 1369350 | 15271047.3 | 9919733.58 | 25112112.7 | 35279540.8615 | 25112112.7 | 35363997.9325 | 25112112.7 | 35363997.9325 | 40.82%
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 622115 | 622115 | 909925 | 909925 | 1345125 | 1345125 | 1369350 | 1369350 | 15271047.3 | 9919733.58 | 25112112.7 | 35279540.8615 | 25112112.7 | 35363997.9325 | 25112112.7 | 35363997.9325 | 40.82%

## Progress Overview
Progress Overview of the Action 2016-SK-TMC-0218-W (at accumulated level)
| 2017 |  |  | 2018 |  |  | 2019 |  |  | 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024 |  |  | 2025
| Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress
Activity name | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR
Activity 1 | 0 | 0 | 9 | 0 | 0 | 23 | 35 | 46 | 35 | 51 | 67 | 48 | 75 | 99 | 70 | 76 | 100 | 89 | 79 | 100 | 98 | 100 | 100 | 100 | 100 | 100 | 100
Activity 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 13 | 100 | 0 | 89 | 100 | 0 | 100
Activity 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 11 | 100 | 0 | 100 | 100 | 0 | 100
Activity 4 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 30 | 1 | 32 | 60 | 1 | 32 | 60 | 4 | 100 | 60 | 4 | 100 | 60 | 100 | 100 | 60 | 100 | 100 | 100
For the Action | 0 | 0 | 3 | 0 | 0 | 8 | 2 | 45 | 12 | 4 | 66 | 17 | 5 | 98 | 24 | 5 | 100 | 30 | 61 | 100 | 40 | 100 | 100 | 95 | 100 | 100 | 100