## Milestones
Upgrade of the railway line Devínska Nová Ves - SK/CZ state border, Malacky-Kúty section
Activity | Milestone number | Milestone description | Indicative completion date | [7 empty] | Means of verification | Percentage of activities and milestones on the project
|  |  | GA | ASR 2017 | ASR 2018 | ASR 2019 | ASR 2020 | ASR 2021 | ASR 2022 | ASR 2023 |  | Technical progress (%) |  | Total technical progress 100% on the project
A1 | 1 | Preparation of design documentation for territorial decision(s) (preliminary design) started | 2018-08-01 | 2019-01-01 | 1.6.2019 | reached/splnené 5.12.2019 | reached/splnené 5.12.2020 | reached 5.12.2019 | reached 5.12.2019 | reached 5.12.2019 | Minutes from kick off meeting with design contractor | 1% | 100% | 80% | 100%
A1 | 2 | Design documentation for territorial decision(s) (preliminary design) prepared | 2019-02-28 | 2019-07-31 | 2019-12-31 | 30.11.2020 | 2021-04-30 | 2022-09-15 | 2023-04-28 | reached 26.7.2023 | Taking Over Certificate by the beneficiary | 35%
A1 | 3 | Territiorial decision(s) issued | 2019-08-31 | 2020-01-31 | 2020-06-30 | 31.01.2021 | 2021-09-30 | 2022-12-15 | 31.08.2023 | 27.03.2024 | Territorial decision(s) issued by competent authority | 4%
A1 | 4 | Preparation of design documentation for building permits and construction execution (detailed/executive design) started | 2019-10-01 | 2020-03-01 | 2020-07-01 | 15.3.2021 | 15.11.2021 | 15.02.2023 | 30.09.2023 | reached 30.09.2023 | Approval decision by Ministry of Transport sent to the design contractor | 1%
A1 | 5 | Draft design documentation for building permits and construction execution (detailed/executive design) prepared | 2020-06-30 | 2020-11-30 | 2021-04-30 | 28.02.2022 | 30.04.2022 | 15.07.2023 | 30.11.2023 | 29.04.2024 | Taking Over Certificate by the beneficiary | 40%
A1 | 6 | Approval decision of Ministry of Transport to Design documentation for building permits and construction execution (detailed/executive design) issued | 2020-10-15 | 2021-03-15 | 31.5.2021 | 31.03.2022 | 31.03.2022 | 15.08.2023 | 31.12.2023 | 11.07.2024 | Approval Decision by Ministry of Transport | 5%
A1 | 7 | Application for first building permit submitted | 2021-02-28 | 2021-07-31 | 2021-09-01 | 31.5.2022 | 31.05.2022 | 15.10.2023 | 16.01.2024 | 31.07.2024 | Confirmation by competent authority | 1%
A1 | 8 | First building permit issued | 2021-05-31 | 2021-10-31 | 2021-11-30 | 31.7.2022 | 31.07.2022 | 15.12.2023 | 29.03.2024 | 31.08.2024 | Building permit issued by competent authority | 5%
A1 | 9 | Last building permit issued | 2022-09-30 | 2022-12-31 | 2022-12-31 | 31.08.2023 | 31.08.2023 | 31.10.2024 | 31.12.2024 | 3.12.2024 | Building permit issued by competent authority | 8%
A2 | 10 | Public procurement procedure for design contract published | 2017-10-31 | 2018-03-31 | reached/splnené 14.4.2018 | reached/splnené 14.4.2018 | reached/splnené 14.4.2018 | reached 14.4.2018 | reached 14.4.2018 | reached 14.4.2018 | Tender published on Office for Public Procurement and OJEU | 30% | 100% | 20%
A2 | 11 | EIA opinion issued | 2017-12-31 | 2018-04-30 | reached/splnené 8.3.2018 | reached/splnené 8.3.2018 | reached/splnené 8.3.2018 | reached 8.3.2018 | reached 8.3.2018 | reached 8.3.2018 | Copy ofEIA opinion | 20%
A2 | 12 | Kick of meeting organised | 2018-02-28 | 2018-02-15 | reached/splnené 15.2.2018 | reached/splnené 15.2.2018 | reached/splnené 15.2.2018 | reached 15.2.2018 | reached 15.2.2018 | reached 15.2.2018 | Minutes, list of participants | 5%
A2 | 13 | Communication plan approved | 2018-06-30 | 2018-06-30 | reached/splnené 28.6.2018 | reached/splnené 28.6.2018 | reached/splnené 28.6.2018 | reached 28.6.2018 | reached 28.6.2018 | reached 28.6.2018 | Acceptance letter of beneficiary | 10%
A2 | 14 | Contract signed for design contractor | 2018-07-31 | 2018-12-31 | 2019-05-31 | reached/splnené 19.11.2019 | reached/splnené 19.11.2019 | reached 19.11.2019 | reached 19.11.2019 | reached 19.11.2019 | Copy of signed contract | 30%
A2 | 15 | Final meeting organised | 2022-12-31 | 2022-12-31 | 2022-12-31 | 31.08.2023 | 31.08.2023 | 31.10.2024 | 31.12.2024 | 31.12.2024 | Minutes, list of participants | 5%

## Technical progress
Technical progress | [12 empty] | 68.6 | %
| Milestones | tech | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | % ∑ | % ∑ left
A1 | M1 | 1% | 0% | 0% | 1% | 0% | 0% | 0% | 0% |  | 1% | 0% | Reached
| M2 | 35% | 0% | 0% | 0% | 26% | 2% | 2% | 5% |  | 35% | 0% | Reached
| M3 | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 4% | Unreached
| M4 | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 1% |  | 1% | 0% | Reached
| M5 | 40% | 0% | 0% | 0% | 0% | 0% | 0% | 25% |  | 25% | 15% | Unreached
| M6 | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 5% | Unreached
| M7 | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 1% | Unreached
| M8 | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 5% | Unreached
| M9 | 8% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 8% | Unreached
80 |  | 100% | 0% | 0% | 1% | 26% | 2% | 2% | 31% | 0% | 62% | 38% | 49.6
| Milestones | tech | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | % ∑ | % ∑ left
A2 | M10 | 30% | 20% | 10% | 0% | 0% | 0% | 0% | 0% |  | 30% | 0% | Reached
| M11 | 20% | 17% | 3% | 0% | 0% | 0% | 0% | 0% |  | 20% | 0% | Reached
| M12 | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 0% |  | 5% | 0% | Reached
| M13 | 10% | 0% | 10% | 0% | 0% | 0% | 0% | 0% |  | 10% | 0% | Reached
| M14 | 30% | 0% | 20% | 10% | 0% | 0% | 0% | 0% |  | 30% | 0% | Reached
| M15 | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 5% | Unreached
20 |  | 100% | 37% | 48% | 10% | 0% | 0% | 0% | 0% | 0% | 95% | 5% | 19
Action % ∑ |  |  | 7.4% | 9.6% | 2.8% | 20.8% | 1.6% | 1.6% | 24.8% | 0%