## Gantt chart
Type | Name of the activity | Start | End | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024
|  |  |  | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII.
A1 | Preliminary and detailed/executive design | 2019-12-05 | 2024-12-31
M1 | Preparation of design docuentation for territorial decision(s) (preliminary design) started |  | 2019-12-05 | bar: 2019 XII.
M2 | Design documentation for territorial decision(s) (preliminary desig) prepared |  | 2023-07-26 | bar: 2023 VII.
M3 | Territiorial decision(s) issued |  | 2024-03-27 | bar: 2024 III.
M4 | Preparation of design documentation for building permits and construction execution |  | 2023-09-30 | bar: 2023 IX.
M5 | Draft design documentation for building permits and construction execution |  | 2024-04-29 | bar: 2024 IV.
M6 | Approval decision of Ministry of Transport to Design documentation for building permits and construction execution (detailed/executive design) issued |  | 2024-07-11 | bar: 2024 VII.
M7 | Application for first building permit submitted |  | 2024-07-31 | bar: 2024 VII.
M8 | First building permit issued |  | 2024-08-31 | bar: 2024 VIII.
M9 | Last building permit issued |  | 2024-12-31 | bar: 2024 XII.
A2 | Project management and public procurement | 2017-02-07 | 2024-12-31
M10 | Public procurement procedure for design contractor published |  | 2018-04-14 | bar: 2018 IV.
M11 | EIA opinion issued |  | 2018-03-08 | 2018 III.: M11
M12 | Kick of meeting organised |  | 2018-02-15 | 2018 II.: M12
M13 | Communication plan approved |  | 2018-06-28 | 2018 VI.: M13
M14 | Contract signed for design |  | 2019-11-19 | 2019 XI.: M14
M15 | Final meeting organised |  | 2024-12-31 | 2024 XII.: M15