## Asr info
CEF | Transport
Action Code | 2016-SK-TMC-0219-W
Exercise Year | 2024
Version | 1
Actual Action Start Date | 07/02/2017
Actual Action End Date | 31/12/2024
A. Maximum EU contribution (Art. 3) | €50,319,391.67
B. Pre-financing rate (Art. 4.1.2) | 50%
C. Maximum pre-financing payment (Art. 4.1.2) (=B*A) | €25,159,695.84
D. Maximum ceiling for the sum of pre-financing and interim payments (Art 4.1.3) (=80%*A) | €40,255,513.34
E. Sum of Previous Pre-financing Payments | €25,159,695.84
F. Sum of Interim Payments | €15,095,817.76
G. Sum of pre-financing and interim payments (E+F) | €40,255,513.60

## Eligible costs (€)
Update of the indicative breakdown of estimated eligible costs of the Action 2016-SK-TMC-0219-W (€)
|  |  | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
| 1 Construction works and author supervision | 77.95
1 | Železnice Slovenskej republiky |  |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total for activity 1
| 2 Construction works | 77.95
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18844662 | 18844661.53 | 21452354 | 29444056.32 | 23968405 | 28865962.14 | 0 | 6658542.48
Total for activity 2
| 3 Project management, public procurement and building permits procedures | 77.95
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 120 | 14000 | 14000 | 50000 | 2320 | 223880 | 0
Total for activity 3
Total eligible costs
1 | Železnice Slovenskej republiky
Total cumulated eligible costs
1 | Železnice Slovenskej republiky

## Financing needs (€)
Financing needs of the Action 2016-SK-TMC-0219-W (€)
|  |  | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
1 Construction works and author supervision
1 | Železnice Slovenskej republiky
Totals for activity 1
2 Construction works
1 | Železnice Slovenskej republiky
Totals for activity 2
3 Project management, public procurement and building permits procedures
1 | Železnice Slovenskej republiky
Totals for activity 3
Total financing needs
1 | Železnice Slovenskej republiky
Total cumulated financing needs
1 | Železnice Slovenskej republiky

## Progress Overview
Progress Overview of the Action 2016-SK-TMC-0219-W (at accumulated level)
| 2017 |  |  | 2018 |  |  | 2019 |  |  | 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024
| Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress
Activity name | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR
Activity 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 30 | 0 | 0 | 57 | 0 | 0 | 72 | 0 | 0 | 100
Activity 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 29 | 22 | 50 | 63 | 58 | 64 | 100 | 92 | 88 | 100 | 100 | 100
Activity 3 | 0 | 0 | 10 | 0 | 0 | 35 | 0 | 0 | 50 | 0 | 0 | 77 | 0 | 1 | 77 | 5 | 86 | 97 | 22 | 100 | 97 | 100 | 100 | 100
For the Action | 0 | 0 | 2 | 0 | 0 | 7 | 0 | 0 | 10 | 0 | 0 | 28 | 29 | 22 | 51 | 62 | 58 | 69 | 100 | 92 | 87 | 100 | 100 | 100