## Milestones
Upgrade of the Váh – Varín – Strečno railway section (2016-SK-TMC-0219-W)
Table 1 Indicative completion dates of the milestones and technical progress
Milestone number | Milestone description | Indicative completion date | [7 empty] | Means of verification |  | Technical progress1 (%)
|  | GA | ASR 2017 | ASR 2018 | ASR 2019 | ASR 2020 | ASR 2021 | ASR 2022 | ASR (for period 2023) |  | Milestone reached Y/N
1 | Activity 1 - Start of Construction works supervision /Začiatok dozoru stavebných prác | 2019-04-01 | 2019-07-01 | 2020-02-01 | 2020-11-20 | 2020-12-15 | 2020-12-15 | 2020-12-15 | 2020-12-15 | Notification by beneficiary |  | 1 | 100 | 20 | 100
2 | Activity 1 - Submission of first interim report on Construction works supervision /Predloženie prvej priebežnej správy o stavebnom dozore | 2019-12-31 | 2020-01-01 | 2020-07-31 | 2021-05-31 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 2021-06-30 | Interim supervision report |  | 14 |  |  |  | The percentage rating corresponds to the duration of the performance of the construction supervision activity.
3 | Activity 1 - Submission of second interim report on Construction works supervision /Predloženie druhej priebežnej správy o stavebnom dozore | 2020-12-31 | 2021-01-01 | 2021-07-31 | 2022-05-31 | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2022-06-30 | Interim supervision report |  | 28
4 | Activity 1 - Submission of third interim report on Construction works supervision /Predloženie tretej priebežnej správy o stavebnom dozore | 2021-12-31 | 2022-01-01 | 2022-07-31 | 2023-05-31 | 2023-06-30 | 2023-06-30 | 2023-06-30 | 2023-06-30 | Interim supervision report |  | 29
5 | Activity 1 - Completion of Construction works supervision /ukončenie dozoru stavebných prác | 2022-12-31 | 2022-12-31 | 2023-09-30 | 2024-05-31 | 2024-06-30 | 2024-06-30 | 2024-06-30 | 2024-12-31 | Final report and notification by beneficiary |  | 28
6 | Activity 2 - Start of preliminary construction works /Začiatok prípravných stavebných prác | 2019-04-01 | 2019-07-01 | 2020-02-01 | 2020-11-20 | 2020-11-13 | 2020-11-13 | 2020-11-13 | 2020-11-13 | Notification by beneficiary |  | 5 | 100 | 60
7 | Activity 2 - Start of construction works /Začiatok stavebných prác | 2019-05-01 | 2019-07-01 | 2020-02-01 | 2020-12-01 | 2020-12-15 | 2020-12-15 | 2020-12-15 | 2020-12-15 | Notification by beneficiary |  | 5
8 | Activity 2 - Completion of sub-section UČS 54 Váh – Varín /ukončenie sekcie UČS 54 Váh-Varín | 2021-03-31 | 2021-04-30 | 2021-11-30 | 2022-09-30 | 2023-11-30 | 2023-11-30 | 2024-05-31 | 2024-12-31 | Taking Over Certificates |  | 40 |  |  |  | The percentage rating corresponds to the estimated volume of work per individual CPC in financial terms.
9 | Activity 2 - Completion of sub-section UČS 55 Varín – Strečno /ukončenie sekcie UČS 55 Varín-Strečno | 2022-12-31 | 2022-12-31 | 2023-09-30 | 2024-05-31 | 2023-12-31 | 2023-12-31 | 2024-05-31 | 2024-12-31 | Taking Over Certificates |  | 50
10 | Activity 3 - Kick-off meeting organised /Zorganizované úvodné stretnutie | 2017-12-31 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | 2017-12-11 | Minutes, list of participants |  | 3 | 100 | 20
11 | Activity 3 - First building permit issued/Vydané prvé stavebné povolenie | 2018-02-28 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | 2017-07-10 | Building permit issued by competent authority |  | 5
12 | Activity 3 - Last building permit issued /Vydané posledné stavebné povolenie | 2018-04-30 | 2018-06-30 | 2019-08-31 | 2020-06-30 | 2020-07-10 | 2020-07-10 | 2020-07-10 | 2020-07-10 | Building permit issued by competent authority; revised/updated project documentation regarding the assessment of cumulative impacts of the project on Natura 2000 and relevant outcomes of such assessment |  | 15
13 | Activity 3 - Public procurement procedure for construction works published /Zverejnený postup verejného obstarávania stavebných prác ​ | 2018-05-31 | 2018-08-31 | 2019-04-30 | 2019-10-15 | 2019-10-15 | 2019-10-15 | 2019-10-15 | 2019-10-15 | Tender published on Office for Public Procurement and OJEU |  | 20
14 | Activity 3 - Communication plan approved /schválený komunikačný plán | 2018-06-30 | 2018-06-30 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | 2018-06-28 | Acceptance letter of beneficiary, Copy of Communication plan |  | 4
15 | Activity 3 - Public procurement procedure for project management and audit support published/Zverejnený postup verejného obstarávania na riadenie projektu a podporu auditu | 2018-06-30 | 2019-01-31 | 2019-08-31 | 2020-12-31 | 2021-06-30 | 2022-05-13 | 2022-05-13 | 2022-05-13 | Tender published on Office for Public Procurement and OJEU |  | 10
16 | Activity 3 - Contract signed for Construction works supervision/podpis zmluvy o stavebnom dozore | 2019-03-31 | 2019-06-30 | 2020-01-31 | 2020-11-19 | 2020-10-19 | 2020-10-19 | 2020-10-19 | 2020-10-19 | Award Notice, Signed Contract 3 |  | 10
17 | Activity 3 - Contract signed for construction works /Podpis zmluvy na stavebné práce | 2019-03-31 | 2019-06-30 | 2020-01-31 | 2020-11-19 | 2020-11-12 | 2020-11-12 | 2020-11-12 | 2020-11-12 | Award Notice, Signed Contract |  | 20
18 | Activity 3 - Contract signed for project management and audit support /Podpísaná zmluva o riadení projektu a podpore auditu | 2019-03-31 | 2019-10-31 | 2020-05-31 | 2021-09-30 | 2022-03-31 | 2022-06-30 | 2022-07-07 | 2022-07-07 | Award Notice, Signed Contract |  | 10
19 | Activity 3 - Final event organised /zorganizované záverečné podujatie | 2022-12-31 | 2022-12-31 | 2023-09-30 | 2024-05-31 | 2024-06-30 | 2024-06-30 | 2024-06-30 | 2024-12-31 | Media reports |  | 3

## Technical Progress
Technical progress cumulative | [12 empty] | 86.6 | %
| Milestones | tech | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | % ∑ | % ∑ left
A1 | M1 | 1% | 0% | 0% | 0% | 1% | 0% | 0% | 0% |  | 1% | 0% | Reached
| M2 | 14% | 0% | 0% | 0% | 6% | 8% | 0% | 0% |  | 14% | 0% | Reached
| M3 | 28% | 0% | 0% | 0% | 0% | 15% | 13% | 0% |  | 28% | 0% | Reached
| M4 | 29% | 0% | 0% | 0% | 0% | 0% | 14% | 15% |  | 29% | 0% | Reached
| M5 | 28% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 28% | Unreached
20 |  | 100% | 0% | 0% | 0% | 7% | 23% | 27% | 15% | 0% | 72% | 28% | 14.4
| Milestones | tech | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | % ∑ | % ∑ left
A2 | M6 | 5% | 0% | 0% | 0% | 5% | 0% | 0% | 0% |  | 5% | 0% | Reached
| M7 | 5% | 0% | 0% | 0% | 5% | 0% | 0% | 0% |  | 5% | 0% | Reached
| M8 | 40% | 0% | 0% | 0% | 4% | 6% | 7% | 15% |  | 32% | 8% | Unreached
| M9 | 50% | 0% | 0% | 0% | 5% | 25% | 7% | 9% |  | 46% | 4% | Unreached
60 |  | 100% | 0% | 0% | 0% | 19% | 31% | 14% | 24% | 0% | 88% | 12% | 52.8
| Milestones | tech | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | % ∑ | % ∑ left
A3 | M10 | 3% | 3% | 0% | 0% | 0% | 0% | 0% | 0% |  | 3% | 0% | Reached
| M11 | 5% | 2% | 3% | 0% | 0% | 0% | 0% | 0% |  | 5% | 0% | Reached
| M12 | 15% | 5% | 3% | 5% | 2% | 0% | 0% | 0% |  | 15% | 0% | Reached
| M13 | 20% | 0% | 15% | 5% | 0% | 0% | 0% | 0% |  | 20% | 0% | Reached
| M14 | 4% | 0% | 4% | 0% | 0% | 0% | 0% | 0% |  | 4% | 0% | Reached
| M15 | 10% | 0% | 0% | 0% | 0% | 10% | 0% | 0% |  | 10% | 0% | Reached
| M16 | 10% | 0% | 0% | 0% | 10% | 0% | 0% | 0% |  | 10% | 0% | Reached
| M17 | 20% | 0% | 0% | 5% | 15% | 0% | 0% | 0% |  | 20% | 0% | Reached
| M18 | 10% | 0% | 0% | 0% | 0% | 0% | 10% | 0% |  | 10% | 0% | Reached
| M19 | 3% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 3% | Unreached
20 |  | 100% | 10% | 25% | 15% | 27% | 10% | 10% | 0% | 0% | 97% | 3% | 19.4
Action % ∑ |  |  | 2% | 5% | 3% | 18.2% | 25.2% | 15.8% | 17.4% | 0%