**Action's implementation technical progress (cumulated %)**

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | **2017** | | **2018** | | **2019** | | **2020** | | **2021** | | **2022** | | **2023** | | **2024** | |
| Action level | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR |
|  | 2 | 2 | 7 | 7 | 10 | 10 | 28 | 28 | 51 | 51 | 75 | 75 | 97 | 97 | 100 | 100 |
| Activity | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR |
| 1 | N/A | 0 | N/A | 0 | N/A | 0 | 7 | 7 | 30 | 30 | 59 | 57 | 86 | 72 | 100 | 100 |
| 2 | N/A | 0 | N/A | 0 | N/A | 0 | 19 | 19 | 46 | 50 | 69 | 64 | 95 | 88 | 100 | 100 |
| 3 | 10 | 10 | 35 | 35 | 50 | 50 | 77 | 77 | 87 | 77 | 87 | 97 | 97 | 97 | 100 | 100 |

**All the activities and the Action will achieve 100% of technical progress by their actual end dates**