## Gantt chart
Type | Name of the activity | Start | End | 2017 | [11 empty] | 2018 | [11 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022 | [11 empty] | 2023 | [11 empty] | 2024
|  |  |  | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII. | I. | II. | III. | IV. | V. | VI. | VII. | VIII. | IX. | X, | XI. | XII.
A1 | Construction works and author supervision | 2020-12-15 | 2024-12-31
M1 | Activity 1 - Start of Construction works supervision |  | 2020-12-15 | [47 empty] | M1
M2 | Activity 1 - Submission of first interim report on Construction works supervision |  | 2021-06-30 | [53 empty] | M2
M3 | Activity 1 - Submission of second interim report on Construction works supervision |  | 2022-06-30 | [65 empty] | M3
M4 | Activity 1 - Submission of third interim report on Construction works supervision |  | 2023-06-30 | [77 empty] | M4
M5 | Activity 1 - Completion of Construction works supervision |  | 2024-12-31 | [95 empty] | M5
A2 | Construction works | 2020-11-13 | 2024-12-31
M6 | Activity 2 - Start of preliminary construction works |  | 2020-11-13 | [46 empty] | M6
M7 | Activity 2 - Start of construction works |  | 2020-12-15 | [47 empty] | M7
M8 | Activity 2 - Completion of sub-section UČS 54 Váh – Varín |  | 2024-12-31 | [95 empty] | M8
M9 | Activity 2 - Completion of sub-section UČS 55 Varín – Strečno |  | 2024-12-31 | [95 empty] | M9
A3 | Project management, public procurement and building permits procedures | 2017-02-07 | 2024-12-31
M10 | Activity 3 - Kick-off meeting organised |  | 2017-12-11 | [11 empty] | M10
M11 | Activity 3 - First building permit issued |  | 2017-07-10 | [6 empty] | M11
M12 | Activity 3 - Last building permit issued (Vydané posledné stavebné povolenie) |  | 2020-07-10 | [42 empty] | M12
M13 | Activity 3 - Public procurement procedure for construction works published |  | 2019-10-15 | [33 empty] | M13
M14 | Activity 3 - Communication plan approved |  | 2018-06-28 | [17 empty] | M14
M15 | Activity 3 - Public procurement procedure for project management and audit support published |  | 2022-05-13 | [64 empty] | M15
M16 | Activity 3 - Contract signed for Construction works supervision |  | 2020-10-19 | [45 empty] | M16
M17 | Activity 3 - Contract signed for construction works |  | 2020-11-12 | [46 empty] | M17
M18 | Activity 3 - Contract signed for project management and audit support |  | 2022-07-07 | [66 empty] | M18
M19 | Activity 3 - Final event organised |  | 2024-12-31 | [95 empty] | M19