| European Commission European Climate, Infrastructure and Environment Executive Agency (CINEA) Connecting Europe Facility | ASR-2024-2015-SK-TM-0207-M-Modernisation of two sections of the CZ/SK state border - Devinska Nová Ves railway line Reporting period: 1 January 2023 - 31 December 2023 |  |
| --- | --- | --- |
| 1. INFORMATION ON THE ACTION |  |  |
| Grant Agreement Nº |  | INEA/CEF/TRAN/M2015/1131671 |
| Action number |  | 2015-SK-TM-0207-M |
| Action title |  | Modernisation of two sections of the CZ/SK state border - Devinska Nová Ves railway line |
| PCI (for energy and synergy only) |  |  |

| Author of the report |  |
| --- | --- |
| Name | Roman Havelka |
| Position | Project Manager |
| Entity | Železnice Slovenskej republiky |
| Telephone Nº | +421220293321 |
| E-mail | havelka.roman@zsr.sk |

2. INFORMATION ON THE PROGRESS OF THE ACTION (GA II.23.1.1.c or SESAR FPA II.23.1b.c)

2.1. Overall progress of the Action until the end of the previous reporting period

| Planned dates (GA) |  | Previous ASR dates |  | Actual dates |  | Overall technical progress achieved at the end of the previous reporting period (%)* |
| --- | --- | --- | --- | --- | --- | --- |
| Start | End | Start | End | Start | End |  |
| 17/02/2016 | 31/12/2024 | 17/02/2016 | 31/12/2024 | 17/02/2016 | 31/12/2024 | 85% |
| *Please explain how the percentage of the progress achieved has been estimated/calculated |  |  |  |  |  |  |
| The technical progress achieved by the Action at the end of the previous reporting period based on weighted technical progress expressed as percentage is 85%. (Annex 1) The determination of technical progress is based on an already defined reporting method from previous ASRs. It also monitors its progress in each milestone so that progress can be determined as accurately (i.e., at milestone level), especially in a project of this kind, as financial progress never really fits into technical progress. |  |  |  |  |  |  |

Overview of progress since the start of the Action The overview should include a description of the actual progress of the Action and per activity since the start of the Action until at the end of the previous reporting period, referring to the main issues, milestones and events that affected the progress.

Overall, the implementation of the Action is long overdue compared to the Grant Agreement. In view of this, in the 2019, the scope of the project was reduced and the total eligible costs decreased with the deadline of the project until 31/12/2022. Critical milestone no.3 (Contract signed for design-build contractor) has been established in the framework of Amendment No. 3, which was to be reached by 29/05/2020. At the same time, new milestones have been identified and the original milestones that have been retained have been updated with the achievement dates. Activity 1 Public procurement, authorisation procedures, detailed design and as-built documentation Contains critical milestones and in accordance with Amendment No. 3, these are Milestone 3, Milestone 5, Milestone 10 and Milestone 13. Milestone 1 Public procurement procedure for design-build contractor (01/02/2017, in GA: 01/02/2017) The verification of fulfilment (Annex 10.1, 10.2). The procurement process for the selection of the contractor continued, where further actions leading to the conclusion of a contract with the contractor. Milestone 2 Public procurement procedure for Engineering/construction works supervision published (29/02/2020, in GA: 29/02/2020) Construction supervision is still performed by our own internal capacities within the performance of the contract (project work). Based on the decision of Railways of the Slovak Republic, the construction supervision within this project will only be internal (Annex 26). For this reason, Milestones M2 and M4 are no longer relevant. Milestone 3 Contract signed for design-build contractor (09/09/2020, in GA: 09/09/2020) The Contract for Work No.1/2017, which was published in the Central Register of Contracts of the Office of the Government of the Slovak Republic on 09/09/2020 with effect from 10/09/2020 https://www.crz.gov.sk/index.php?ID=4957074&l=sk, by which the milestone No.3 was fulfilled (Annex 3). After signing the contract with the contractor, Railways of the Slovak Republic established an implementation team, whose task is to effectively fulfill tasks and solve problems in order to reduce possible delays based on the possibility of coordination of work of various departments and cooperation between them. Contract signed for contractor (Annex 10.3, 10.4). Milestone 4 Contract signed for Engineering/construction works supervision (30/11/2020, in GA: 30/11/2020) Based on the decision of Railways of the Slovak Republic, the construction supervision within this project will only be internal (Annex 26). The preparation of public procurement for supervision will no longer be continued, so M2 a M4 are irelevant. Milestone 5 EIA consent decision issued (08/03/2018, in GA: 08/03/2018) . The EIA opinion (M5) no. 2264/2017-1.7 of 19/02/2018 was issued by the Ministry of the Environment of the Slovak Republic (hereinafter MoE) and was published on 08/03/2018 on the website of the MoE SR https://www.enviroportal.sk/sk/eia/detail/modernizacia-zeleznicnej-trate-bratislava-hl-st-kuty-lanzhot-cz-usek-t, but was not valid (Annex 8). On 26 April 2018, public information on appeal (remonstrance) and on submission appeal (remonstrance) (Annex 15 and 16) was published. On 12/02/2019, the Environment Minister of the SR rejected the appeal (remonstrance), which means that the EIA Final Statement is valid (Annex 17). Milesone 6 Start of detailed design (30/06/2020, GA: 30/06/2020) Following the signing of the contract with the contractor, the project work was started (Annex 24). Milestone 7 State expertise for sub-section Brodské (excl.) – State Border SK/CZ issued (30/09/2020, in GA: 30/09/2020) Is not carried out due to legislative provisions of the Slovak Republic. The performance of state expertise is governed by Act no. 254/1998 Coll. on Public Works, as amended, and the Methodological Instruction of the Ministry of Transport and Construction of the Slovak Republic No. 44/2020 for the performance of expert activities and departmental control. Milestone 8 DBPC (Documentation for building permit and construction) for sub-section Brodské (incl.) – State Border SK/CZ (30/11/2020, in GA: 30/11/2020) The documentation was processed as a subsequent step of project documentation by an authorized designer. Milestone 9 DTD (Documentation for the territorial decision(s)) for section Devínska Nová Ves (excl.) – Malacky (incl.) and sub-section Kúty (excl.) – Brodské (incl.) (31/12/2020, in GA: 31/12/2020) The documentation was processed as a subsequent step of project documentation by an authorized designer. The verification of fulfilment (Annex 28.1, 28.2, 28.3). Milestone 10 First building permit for sub-section Brodské (incl.) – State Border SK/CZ (km 72+750 – 74+900) (31/01/2021, in GA: 31/01/2021) . With the issuance of a building permit, construction work could begin. Milestone 11 Territorial decision(s) for section Devínska Nová Ves (excl.) – Malacky (incl.) and sub-section Kúty (excl.) – Brodské (incl.) and State expertise issued (31/08/2021, in GA: 31/08/2021) This was followed by processing of the Documentation for building permit and construction, the construction permit and the implementation of the construction. Milestone 12 Documentation for building permit and construction) for section Devínska Nová Ves (excl.) – Malacky (incl.) and sub-section Kúty (excl.) – Brodské (incl.) delivered (30/09/2021, in GA: 30/09/2021) . In order to save time and the legislative possibility, the processing of Documentation for building permit and construction took place simultaneously at the time of securing the territorial decision and expert assessments. Activity 2 Engineering/construction works supervision After signing the contract with the contractor M2, which was signed on 09.09.2020, the contractor was notified of the internal construction supervision, which will be part of the implementation team. Milestone 15 Start of Engineering/construction works supervision (30/06/2020, in GA: 30/06/2020) The internal construction supervision was established and based on the decision of Railways of the Slovak Republic, only the internal construction supervision will be during the whole implementation of the Action (Annex 23). Milestone 16 Submission of interim report on detailed design and engineering/constructifon works supervision (31/12/2020, in GA: 31/12/2020) The construction supervisor works on the construction site on a daily basis. The verification of fulfilment (Annex 22.1). Milestone 17 Submission of interim report on detailed design and engineering/construction works supervision (31/12/2021, in GA: 31/12/2021) The construction supervisor works on the construction site on a daily basis. The verification of fulfilment (Annex 22.2) Activity 3 Construction works Milestone 19 Start of construction works in sub-section Brodské (incl.) – State Border (km 72,750-74,900) (28/01/2022, in GA: 31/01/2021) Construction works in this sub-section began with the handover of construction site (Annex 31). The following construction works took place in 2023 on the Brodské (including) - state border section: - constructed access roads (4 km) to the construction site; - establishment of a construction site and managed intermediate landfills; - felling of trees; - dismantling the old traction line, traction supports, traction gates; - concreting and installation of a new traction line, traction supports, traction gates; - construction of a temporary rail connection due to lockouts on the side of the Czech Republic; - demolition of the "big bridge" on the 2nd track; - dismantling and unloading of the railway top and bottom of the track; - demolition of bridge piers and supports; - directional extension of two "smaller bridges" in front of the "big bridge"; - demolition of the pillars of two "small bridges" in front of the "big bridge"; - ramming sheet piles, drilling 28 piles under the foundations of new bridge piers; - construction of new bridge piers; - assembly, welding of the steel structure of the "big bridge" imported from the production plant in Italy (for 2nd track); The bridge on the second track across the Morava River was completed and is in early use. Work on the subject bridge building started on 28/01/2022, with the demolition of the original bridge, the demolition of two bridge piers and abutments, the drilling and concreting of 32 piles, the concreting of the foundations of bridge piers and bridge abutments, and the subsequent construction of bridge abutments and piers. On the embankment of the railway body, the assembly, welding and painting of the steel bridge structure took place at the same time, which was pushed out across the Morava river to the other bank after the assembly was completed. On both sides of the bridge, frame underpasses were built, which are designed for the passage of maintenance equipment. A new traction line, traction supports, railway top and bottom, signaling and security equipment were built. At the same time, work continued on two smaller bridges in front of the main bridge over the Morava River. Towards the end of 2023, work continued on the first track. The Contractor is obliged to provide all necessary statements, building permits and approvals of transport routes for access to the construction site. It is also necessary to carry out a survey of engineering networks for underground engineering work. Activity 4 Project management, communication/dissemination and financial audit Milestone 21 Kick off meeting organised (08/02/2017, in GA: 08/02/2017) . Kick off meeting was organized on 08/02/2017. The verification of fulfilment (Annex 12). Milestone 22 Communication plan approved (11/12/2017, in GA: 11/12/2017) The communication plan was approved on 11/12/2017. The verification of fulfilment (Annex 11). On 21/06/2023 Amendment n°4 was signed which extends the project implementation period to 31/12/2024.

2.2. Progress per activity

| Activity 1 | Title | Planned Start/End date (GA) |  | Previous ASR Start/end dates |  | Actual Start/End date |  |  | Overall technical progress achieved until the end of the previous reporting period (%)* |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Public procurement, authorisation procedures, detailed design and as-built documentation | 17/02/2016 | 31/12/2024 | 17/02/2016 | 31/12/2024 | 17/02/2016 |  | 31/12/2024 | 94% |
| *Please explain how the percentage of the progress achieved has been estimated/calculated |  |  |  |  |  |  |  |  |  |
| Total technical progress has the following weighted technical progress, expressed as a percentage: M1 is reached (total value of the Milestone in Activity is 3%), M2- 0% (total value of the Milestone in Activity is 0%), M3 is reached (total value of the Milestone in Activity is 10%), M4- 0% (total value of the Milestone in Activity is 0%), M5 is reached (total value of the Milestone in Activity is 8%), M6 is reached (total value of the Milestone in Activity is 5%), M7 is reached (total value of the Milestone in Activity is 10%), M8 is reached (total value of the Milestone in Activity is 10%), M9 is reached (total value of the Milestone in Activity is 10%), M10 is reached (total value of the Milestone in Activity is 10%), M11 is reached (total value of the Milestone in Activity is 10%), M12 is reached (total value of the Milestone in Activity is 10%), M13 is partially reached (5% of total value 10%) and M14 is partially reached (3% of total value 4%). The methodology for calculating this value is based on the weighted technical progress indicated as a percentage (Annex 1). The methodology was chosen and applied in all previously submitted ASR, since in projects of this kind financial progress never really corresponds to technical progress. The cumulative technical progress of the action, including the planned technical progress, is also attached in Annex 2. |  |  |  |  |  |  |  |  |  |
| Milestone no | Title1 | Planned completion date (GA) |  | Previous ASR date |  |  | Actual completion date |  | Reached (Y/N) |
| 1 | Public procurement procedure for design-build contractor published | 01/02/2017 |  | 01/02/2017 |  |  | 01/02/2017 |  | Yes |
| Explanation for any deviation from planned completion date |  |  |  |  |  |  |  |  |  |
| 2 | Public procurement procedure for Engineering/construction works supervision published | 29/02/2020 |  | 29/02/2020 |  |  | 29/02/2020 |  | Yes |
| Explanation for any deviation from planned completion date |  |  |  |  |  |  |  |  |  |
| 3 | Contract signed for design-build contractor | 29/05/2020 |  | 09/09/2020 |  |  | 09/09/2020 |  | Yes |
| Explanation for any deviation from planned completion date |  |  |  |  |  |  |  |  |  |
| 4 | Contract signed for Engineering/construction works supervision | 30/11/2020 |  | 30/11/2020 |  |  | 30/11/2020 |  | Yes |
| Explanation for any deviation from planned completion date |  |  |  |  |  |  |  |  |  |
| 5 | EIA consent decision issued | 08/03/2018 |  | 08/03/2018 |  |  | 08/03/2018 |  | Yes |
| Explanation for any deviation from planned completion date |  |  |  |  |  |  |  |  |  |
| 6 | Start of detailed design | 30/06/2020 |  | 30/06/2020 |  |  | 30/06/2020 |  | Yes |
| Explanation for any deviation from planned completion date |  |  |  |  |  |  |  |  |  |
| 7 | State expertise for sub-section Brodské (excl.) – State Border SK/CZ issued | 30/09/2020 |  | 30/09/2020 |  |  | 30/09/2020 |  | Yes |
| Explanation for any deviation from planned completion date |  |  |  |  |  |  |  |  |  |
| 8 | DBPC (Documentation for building permit and construction) for sub-section Brodské (incl.) – State Border SK/CZ (km 72,750-74,900) delivered | 30/11/2020 |  | 30/11/2020 |  |  | 30/11/2020 |  | Yes |
| Explanation for any deviation from planned completion date |  |  |  |  |  |  |  |  |  |
| 9 | DTD (Documentation for the territorial decision(s)) for section Devínska Nová Ves (excl.) – Malacky (incl.) and sub-section Kúty (excl.) – Brodské (incl.) delivered | 31/12/2020 |  | 31/12/2020 |  |  | 31/12/2020 |  | Yes |
| Explanation for any deviation from planned completion date |  |  |  |  |  |  |  |  |  |
| 10 | First building permit for sub-section Brodské (incl.) – State Border SK/CZ (km 72,750-74,900) issued | 31/01/2021 |  | 31/01/2021 |  |  | 31/01/2021 |  | Yes |
| Explanation for any deviation from planned completion date |  |  |  |  |  |  |  |  |  |
| 11 | Territorial decision(s) for section Devínska Nová Ves (excl.) – Malacky (incl.) and sub-section Kúty (excl.) – Brodské (incl.) and State expertise issued | 31/08/2021 |  | 31/08/2021 |  |  | 31/08/2021 |  | Yes |
| Explanation for any deviation from planned completion date |  |  |  |  |  |  |  |  |  |
| 12 | DBPC (Documentation for building permit and construction) for section Devínska Nová Ves (excl.) – Malacky (incl.) and sub-section Kúty (excl.) – Brodské (incl.) delivered | 30/09/2021 |  | 30/09/2021 |  |  | 30/09/2021 |  | Yes |
| Explanation for any deviation from planned completion date |  |  |  |  |  |  |  |  |  |
| 13 | First building permit for section Devínska Nová Ves (excl.) – Malacky (incl.) and sub-section Kúty (excl.) – Brodské (incl.) issued | 20/09/2023 |  | 20/09/2023 |  |  | 30/11/2024 |  | No |
| Explanation for any deviation from planned completion date |  |  |  |  |  |  |  |  |  |
| The date has been moved due to obstructions from the municipality of Plavecký Štvtok. |  |  |  |  |  |  |  |  |  |
| 14 | Expert reports on land acquisition completed | 05/11/2023 |  | 05/11/2023 |  |  | 31/12/2024 |  | No |
| Explanation for any deviation from planned completion date |  |  |  |  |  |  |  |  |  |
| The date has been moved due to obstructions from the municipality of Plavecký Štvtok. |  |  |  |  |  |  |  |  |  |

| Activity 2 | Title | Planned Start/End date (GA) |  | Previous ASR Start/end dates |  | Actual Start/End date |  |  | Overall technical progress achieved until the end of the previous reporting period (%)* |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Engineering/construction works supervision | 30/06/2020 | 31/12/2024 | 30/06/2020 | 31/12/2024 | 30/06/2020 |  | 31/12/2024 | 90% |
| *Please explain how the percentage of the progress achieved has been estimated/calculated |  |  |  |  |  |  |  |  |  |
| Total technical progress has the following weighted technical progress, expressed as a percentage: M15 is reached (total value of the Milestone in Activity is 30%), M16 is reached (total value of the Milestone in Activity is 20%), M17 is reached (total value of the Milestone in Activity is 20%) The methodology for calculating this value is based on the weighted technical progress indicated as a percentage (Annex 1) The methodology was chosen and applied in all previously submitted ASR, since in projects of this kind financial progress never really corresponds to technical progress. The cumulative technical progress of the action, including the planned technical progress, is also attached in Annex 2. |  |  |  |  |  |  |  |  |  |
| Milestone no | Title1 | Planned completion date (GA) |  | Previous ASR date |  |  | Actual completion date |  | Reached (Y/N) |
| 15 | Start of Engineering/construction works supervision | 30/06/2020 |  | 30/06/2020 |  |  | 30/06/2020 |  | Yes |
| Explanation for any deviation from planned completion date |  |  |  |  |  |  |  |  |  |
| 16 | Submission of interim report on detailed design and engineering/construction works supervision | 31/12/2020 |  | 31/12/2020 |  |  | 31/12/2020 |  | Yes |
| Explanation for any deviation from planned completion date |  |  |  |  |  |  |  |  |  |
| 17 | Submission of interim report on detailed design and engineering/construction works supervision | 31/12/2021 |  | 31/12/2021 |  |  | 31/12/2021 |  | Yes |
| Explanation for any deviation from planned completion date |  |  |  |  |  |  |  |  |  |
| 18 | Completion of construction works supervision for sub-section Brodské (incl.) – State Border (km 72,750-74,900) | 31/12/2024 |  | 31/12/2024 |  |  | 31/12/2024 |  | No |
| Explanation for any deviation from planned completion date |  |  |  |  |  |  |  |  |  |
| The construction supervisor performs regular physical inspections of the building. |  |  |  |  |  |  |  |  |  |

| Activity 3 | Title | Planned Start/End date (GA) |  | Previous ASR Start/end dates |  | Actual Start/End date |  |  | Overall technical progress achieved until the end of the previous reporting period (%)* |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Construction works | 30/06/2020 | 31/12/2024 | 30/06/2020 | 31/12/2024 | 30/06/2020 |  | 31/12/2024 | 80% |
| *Please explain how the percentage of the progress achieved has been estimated/calculated |  |  |  |  |  |  |  |  |  |
| Total technical progress has the following weighted technical progress, expressed as a percentage: M19 is reached (total value of the Milestone in Activity is 30%) and M20 reached 50% (total value of the Milestone in Activity is 70%) The methodology for calculating this value is based on the weighted technical progress indicated as a percentage. (Annex 1). The methodology was chosen and applied in all previously submitted ASR, since in projects of this kind financial progress never really corresponds to technical progress. The cumulative technical progress of the action, including the planned technical progress, is also attached in Annex 2. |  |  |  |  |  |  |  |  |  |
| Milestone no | Title1 | Planned completion date (GA) |  | Previous ASR date |  |  | Actual completion date |  | Reached (Y/N) |
| 19 | Start of construction works in sub-section Brodské (incl.) – State Border (km 72,750-74,900) | 31/01/2021 |  | 31/01/2021 |  |  | 28/01/2022 |  | Yes |
| Explanation for any deviation from planned completion date |  |  |  |  |  |  |  |  |  |
| The date 31/01/2021 stated as “Planned completion date (GA)” and “Previous ASR date” was not correctly presented due to an administrative mistake, the correct dates should have been 28/01/2022. Construction work started on 28/01/2022 with the handover of construction site (Annex 31). Access roads were built, trees were cut down and dismantling of the old and concreting and installation of new traction lines, supports, traction gates were carried out. There was also the dismantling of the "big bridge" on the second track and the installation of the steel structure of the "big bridge" imported from the production plant in Italy. The bridge has been completed and is in early use. Work on the bridge object in question began on 28/01/2022 with the demolition of the original bridge, the demolition of two pillars and supports, the drilling and concreting of 32 piles, the concreting of the foundations of the pillars and supports of the bridge, then the construction of bridge supports and pillars took place. On the embankment of the railway body, the assembly, welding and painting of the steel bridge structure took place at the same time, which was pushed out across the Morava river to the other bank after the assembly was completed. On both sides of the bridge, frame underpasses were built, which are intended for the passage of maintenance equipment. A new traction line, traction supports, railway top and bottom, signaling and security equipment were built. At the same time, work continued on two smaller bridges in front of the main bridge over the Morava River. Towards the end of 2023, work continued on the first track |  |  |  |  |  |  |  |  |  |  |
| 20 | Completion of construction works in sub-section Brodské (incl.) – State Border (km 72,750-74,900) | 31/12/2024 |  | 31/12/2024 |  |  | 31/12/2024 |  | No |
| Explanation for any deviation from planned completion date |  |  |  |  |  |  |  |  |  |
| In order to reach the set milestone, activities will be ensured in 2024 with the completion of the installation of the bridge over the Morava River on the 1st track and the related finishing works on the railway infrastructure. |  |  |  |  |  |  |  |  |  |

| Activity 4 | Title | Planned Start/End date (GA) |  | Previous ASR Start/end dates |  | Actual Start/End date |  |  | Overall technical progress achieved until the end of the previous reporting period (%)* |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Project management, communication/dissemination and financial audit | 17/02/2016 | 31/12/2024 | 17/02/2016 | 31/12/2024 | 17/02/2016 |  | 31/12/2024 | 60% |
| *Please explain how the percentage of the progress achieved has been estimated/calculated |  |  |  |  |  |  |  |  |  |
| Total technical progress has the following weighted technical progress, expressed as a percentage: M21 is meet at 30% out of total value of the Milestone in Activity 30%, M22 is meet at 30% out of the total value of the Milestone in Activity 30%. The methodology for calculating this value is based on the weighted technical progress indicated as a percentage. (Annex 1). The methodology was chosen and applied in all previously submitted ASR, since in projects of this kind financial progress never really corresponds to technical progress. The cumulative technical progress of the action, including the planned technical progress, is also attached in Annex 2. |  |  |  |  |  |  |  |  |  |
| Milestone no | Title1 | Planned completion date (GA) |  | Previous ASR date |  |  | Actual completion date |  | Reached (Y/N) |
| 21 | Kick-off meeting organised | 08/02/2017 |  | 08/02/2017 |  |  | 08/02/2017 |  | Yes |
| Explanation for any deviation from planned completion date |  |  |  |  |  |  |  |  |  |
| 22 | Communication plan approved | 11/12/2017 |  | 11/12/2017 |  |  | 11/12/2017 |  | Yes |
| Explanation for any deviation from planned completion date |  |  |  |  |  |  |  |  |  |
| 23 | Final event organised | 31/12/2024 |  | 31/12/2024 |  |  | 31/12/2024 |  | No |
| Explanation for any deviation from planned completion date |  |  |  |  |  |  |  |  |  |
| This milestone will be reached only after all remaining milestones are met. |  |  |  |  |  |  |  |  |  |

2.3 If total actual costs/units deviates >5% compared to latest Grant Agreement in force, please explain why

Activity 1 Public procurement, authorisation procedures, detailed design and as-built documentation Activity 1 Public procurement, authorisation procedures, detailed design and as-built documentation Activity 1, the difference -23,32% arose on the basis of a Contract for Work with the Contractor in comparison with the estimate given in Amendment No. 3 to the GA of 13,080,000.00 EUR. Total costs for Activity 1 is 10,029,212.62 € Activity 2 Engineering/construction works supervision Activity 2 Engineering/construction works supervision Under activity 2, there was a change in costs. Due to the fact that ŽSR will have only internal supervision during the project implementation, the costs of construction supervision will be 0 EUR. Activity 3 Construction works Activity 3 Construction works Within activity 3, the difference is -41.52%. The difference arose on the basis of a Contract for Work with the Contractor in comparison with the estimate given in Amendment No. 3 Grant Agreement, which is € 35,503,280.00 for a section of 72,750-74,900 km. Total costs for Activity 2 is 20,763,342.75 €. The contract has been modified and subsequence 71,600-74,900 has been divided in two subsections 71,600-72,750 nad 72,750-74,900 in accordance to Grand Agreement (Annex 33.1 and 33.2)

2.4. Description of the Action's and activities' progress planned in the on-going reporting period and until the end of implementation of the Action a) Provide a description of the planned progress of the activities in the on-going reporting period and, where applicable, beyond the on-going reporting period up until the end of the implementation of the Action (if the on-going reporting period is not the last one). b) Highlight and explain any deviation (e.g. on objectives of the Action, the completion of the planned activities, the cost-breakdown, Action's end date, etc.) in comparison to the latest grant agreement in force and, where applicable, latest ASR. c) Identify any expected/foreseen risk(s) that may challenge the actual end date of the Action and the associated mitigation plan(s).

- Planned progress of the activities Activity 1 Public procurement, authorisation procedures, detailed design and as-built documentation Milestone 13 First building permit for section Devínska Nová Ves (excl.) – Malacky (incl.) and sub-section Kúty (excl.) – Brodské (incl.) issued (30/11/2024, in GA: 20/09/2023) We expect the first building permit for sub-section Devínska Nová Ves (exl.) – Malacky (incl.) to be issued in the month of May 2024. Assumption of issuing the first building permit 11/2024 for the sub-section Kúty (excl.) - Brodské (incl.) due to new comments and requirements of the concerned authorities. The delay in fulfilling the set milestone results from the obstructive action of the municipality of Plavecký Štvrtok, which submitted inadequate objections to all the initiated territorial and construction proceedings, which resulted in a fundamental delay of the entire permitting process. Railways of the Slovak republic has been communicating the above-mentioned problem for a long time at the national level with all interested entities (Ministry of Transport of the Slovak Republic, relevant licensing authorities) and they are initiating all available means of communication to eliminate the obstructionist actions of the municipality. Many negotiations took place with the participation of the municipality, representatives of the Ministry of Transport of the Slovak Republic (including the Minister of Transport of the Slovak Republic) and other interested bodies, but without reaching a mutual agreement. Likewise, no progress was achieved through written suggestions to the Malacky District Prosecutor's Office following the need to review the legality of the Spatial Plan of the municipality of Plavecký Štvrtok and at the same time the legality of the summary binding opinion of the municipality of Plavecký Štvrtok. Railways of the Slovak republic has been informing about the above-mentioned problem for a long time as part of providing regular information about the project. In addition to the described main reason for delaying the completion of Milestone 13, currently the extension of the issuance of the first building permits also causes the process of property rights settlement, which is largely caused by insufficient staffing of the relevant authorities, which causes significant obstructions in engineering activities for the construction process. Milestone 14 Expert reports on land acquisition completed (31/12/2024, in GA: 30/10/2023) Activity 2 Engineering/construction works supervision Milestone 18 Completion of construction works supervision for sub-section Brodské (incl.) – state border (km 72,750-74,900) (31/12/2024, in GA: 31/12/2024) The construction supervisor performs regular physical inspections of the building. At the same time, he participates in solving technical problems. Activity 3 Construction works Milestone 20 Completion of construction works in sub-section Brodské (incl.) – State Border (km 72,750-74,900) (31/12/2024, in GA: 31/12/2024) In the course of 2024, the following was carried out in connection with the modernization of the railway bridge in the 1st track: - dismantling of the old traction line in parallel with the construction of new foundations for traction supports; - dismantling of the "big bridge; - the production of the new steel structure of the railway bridge in a specialized production plant in Italy is ongoing. In connection with the modernization of the railway bridge in the 1st track and the filling of Milestone no. 20, it is necessary to perform the following activities: - completion of the steel bridge structure in the Italian plant and its subsequent transport to the territory of the Slovak Republic, where it will be completed; - subsequent completion of works on the related railway infrastructure. - Deviations in comparison to the latest grant agreement in force (latest ASR) With the aim of harmonizing the status of the implementation of the project valid for ASR 2022 with the wording of the Grant Agreement, on 21/06/2023, Amendment n°4 to the Grant Agreement was signed. Based on the aforementioned change, the completion date of the project was changed to 31/12/2024. The main reason for the said change was delays in reaching the Milestone 13 (First building permit for section Devínska Nová Ves (excl.) – Malacky (incl.) and sub-section Kúty (excl.) – Brodské (incl.) issued), the fulfillment of which was delayed for a long time for objective reasons. The reasons for the delay in the completion of the Milestone 13 persisted during the year 2023, and for this reason the delay in its completion is expected again. The planned date for the Milestone 13 is 11/2024. Due to the established rules of time eligibility, the project completion date remains unchanged. Other deadlines and goals of the project remain unchanged. The number of milestones and activities remain unchanged in accordance with Amendment n°4 to the Grant Agreement. The financial plan has been updated based on the current milestone completion dates and the estimated project completion date. - Expected/foreseen risk(s) The implementation of the project and the related achievement of the set dates of milestones and the overall completion of the project is significantly influenced by the following facts: Continued obstruction proceedings in the municipality of Plavecký Štvrtok due to disagreement with the construction of a road underpass, which is supposed to replace the existing railway crossing The mentioned action significantly slowed down the permitting processes. In 3/2024, a confirming decision of the appeals body was issued to the issued territorial decision for UCS 04. The appeals body rejected the objections of the participants in the proceedings. On the basis of the above, it is possible to proceed with the submission of the application for the issuance of a building permit for UCS 04. However, the territorial proceedings are still ongoing due to the obstructions of the municipality of Plavecký Štvrtok on UCS 03. In total, the current proceedings of the municipality of Plavecký Štvrtok have an impact of up to 910 days from a time point of view. In this context, the deadline for the Milestone 13 (First building permit for section Devínska Nová Ves (excl.) – Malacky (incl.) and sub-section Kúty (excl.) – Brodské (incl.) issued) milestone has been moved to 11/2024. The final date of completion of the project is not affected. Obstructive proceedings of the municipality of Plavecký Štvrtok also have an impact on ongoing construction proceedings, where the municipality also raises its unfounded objections, which unreasonably complicates and prolongs construction proceedings. Insufficient progress by the contractor In the monitored period, there was a significant decrease in the activity of the contractor during the implementation of those parts of the work where there are no obstacles to the implementation of construction works. For this reason, there are significant time delays that may affect the successful completion of the project implementation deadline. In this context, Railways of the Slovak republic has been making efforts towards the contractor for a long time to rectify the situation without delay. Considering the seriousness of the situation and its negative impact on the international obligations arising from the implementation of the project, as well as the obligations arising from the financing of the project through the CEF instrument, Railways of the Slovak republic is negotiating with the Contractor at the statutory level, including with the participation of representatives of the Ministry of Transport of the Slovak Republic and the Ministry of Finance of the Slovak Republic. Due to the international structure of the association, which is the contractor for the project, representatives of the Italian Embassy in Slovak republic are also part of the negotiations. Currently, the contractor is expected to submit binding and updated time schedules, at the same time, the contractor was invited to take immediate and effective measures in connection with the deployed capacities, which will demonstrably guarantee that the work will be completed in the required time. Property of legal settlement and delay of statements of relevant authorities Before issuing a building permit, it is necessary, in accordance with SR legislation, to prove the relationship of the constructor e. i. Railways of the Slovak republic to the land that will be affected by the construction. This relationship is demonstrated either by the purchase of the relevant land or the establishment of an easement ("temporary contract with the owner of the land") or by expropriation (when the owner of the land does not agree to the sale, rent or easement, the land is "taken away" for the benefit of the state on the basis of an expert opinion ). Since it is a linear construction that extends to a lot of land, there was a need for expropriation proceedings, which are within the competence of state administration authorities (Bratislava District Office), but these authorities do not have time to carry out these expropriation proceedings. The authorities were offered personnel or administrative assistance - they did not accept. In the case of temporary and permanent land acquisition, the time required to reach an agreement with the landowners may be extended. Other risks In relation to the possible risks within activity 3 (construction work), which could affect the construction period, the prediction of their occurrence is relatively difficult and, in principle, can only be based on experience with other (completed or currently underway) railway infrastructure modernization construction. From practical experience, there are known cases when there were time disproportions compared to the construction work schedule as a result of so-called force majeure, i.e. floods, when there was deterioration of the already built part of the work. Engineering networks of other administrators (water supply, telecommunications, gas pipelines, sewerage, etc.) also pose risks, where it is not possible to rule out their deviation from the documents provided to the designer at the time of preparation of the project documentation and the need for reworking, which concerns new administrative procedures and actions, which administration is time-consuming. It cannot also be ruled out that, upon detection of unsuitable physical-mechanical properties of the rock in which the building is to be founded, it is not possible to rule out a change in the foundation of artificial structures - e.g. bearing capacity and deformation characteristics (modules), requiring modification of construction procedures, or change of foundation technology. Last but not least, a certain degree of risk is also created by possible archaeological finds, where the adoption of extraordinary measures is required in accordance with the current legislation of the Slovak Republic. One of the measures is the close cooperation of Czech Railways and Railways of the Slovak republic in the preparation and implementation of the construction of the border bridge. A Memorandum was signed between the Czech Republic and the Slovak Republic on cooperation at the level of the ministries of transport of both republics in the preparation and implementation of the reconstruction of the railway bridge connection on the SB SK-CZ in the Kúty - Lanžhot section in 2016. (Annex 7.1-7.2).

3. VISIBILITY OF UNION FUNDING (GA II.23.1.1.i or SESAR FPA II.23.1b.i)

What measures have been taken within the previous reporting period to publicise the Action, including EU funding (GA II.7.1)?

Information on this project is published on the official website of ŽSR in the section: Verejnosť a médiá / Modernizácia tratí / Projekty spolufinancované EÚ / Stavby v realizácii / Modernizácia železničnej trate v dvoch úsekoch štátna hranica CZ/SK – Devínska Nová Ves, hyperlink: http://www.zsr.sk/5106, ensuring a fair and high visibility of EU co-financing. Information about the project is updated four times a year (31 March, 30 June, 30 September and 31 December). Information on the project was provided in articles on other websites: https://www.asb.sk/stavebnictvo/inzinierske-stavby/stavba-zsr-modernizacia-zeleznicnej-trate-devinska-nova-ves-statna-hranica-sr-cr-v-druhom-roku-vystavby Modernizácia trate na Záhorí pokračuje. Vlaky tu budú jazdiť rýchlosťou do 200 km/h - Bratislavskykraj.sk (see Annex 4.2, 4.3)

4. OTHER SOURCES OF EUROPEAN UNION FUNDS (CEF-E and Synergy only, GA II.23.1.1.m )

If applicable, provide information about other sources of EU funds (CEF, ERDF, Cohesion Fund, H2020, TEN, EEPR, EIPA, etc.) used for the project of common interest (e.g. previous or subsequent phases not covered by the Grant Agreement).

Not applicable

5. COMPLIANCE WITH EU LEGISLATION (GA.II.23.1.1g and h, or SESAR FPA II.23.1b.g and h)

5.1. Overview of environmental aspects, compliance with EU and national legislation, issues during the implementation of the Action and measures taken.

The Ministry of the Environment of the Slovak Republic published EIA opinion on 08/03/2018 on the https://www.enviroportal.sk/sk/eia/detail/modernizacia-zeleznicnej-trate-bratislava-hl-st-kuty-lanzhot-cz-usek-t, but was not valid (Annex 8). On 26 April 2018, public information on appeal (remonstrance) and on submission appeal (remonstrance) (Annex 15 and 16) was published. The Environment Minister of the SR on 12/02/2019, rejected the appeal (remonstrance), which means that the EIA Final Statement is valid (Annex 17). . Based on elaborated EIA design documentation (intention impact of construction, assessment report, expert opinion), which came into force on 12/02/2019 (Annex 17), we define the following environmental impact areas, which are listed in (Annex 14).

5.2. Where relevant, information on the compliance with EU legislation notably on procurement: - information on the contracts awarded or planned for the implementation of the Action and on compliance with the requirements set out in GA II.9 and II.10 - regarding other matters, notably public procurement, competition, regulatory matters, (CEF-E only) the update of the CBCA decision, etc.

The PP process is carried out in accordance with Act no. 343/2015 Coll. on public procurement as amended, based on the European Parliament and Council Directives 2014/23/EU, 2014/24/EU and 2014/25/EU. It is a procedure under the Act on Public Procurement based on the EP Directives. EU Member States have an obligation to transpose these Directives into Member State legislation. It is an open competition. In the case of these projects, the Directive 2014/24/EU will apply with regard to EU funding. There have been complaints, namely; 1. Initiation for review - because of the suspicion of the existence of an irregularity in the drawdown of European Union funds on 16/06/2017 - the complaint was notified to the contracting authority. (Annex 20) 2. Initiation to check the legality of the procedure of Železnice Slovenskej republiky, Bratislava in short form "ŽSR", Klemensova 8, 813 61 Bratislava, IČO: 31 364 501 as a legal entity established by the central state administration body, pursuant to Act no. 10/1996 Coll. on control in the state administration as amended by legal regulations dated 13/02/2019 - the complaint was notified to the contracting authority. (Annex 21.1) 3. Complaint to the European Commission under Article 3 of Council Directive 89/665 / EEC of 27/02/2019 - the complaint was notified to the contracting authority. (Annex 20.2, 20.4) 4. Notice of filing an administrative action dated 11/03/2019 - the notice was notified to the contracting authority. (Annex 20.3) As these documents / letters were delivered to the contracting authority in all cases only, the results in the individual processes are not known to the contracting authority. 5. Letter from EUROPE INVEST delivered to the Office of the Government of the Slovak Republic, Office of the Prime Minister of the Slovak Republic dated 7.04.2020 Since these documents / letters have been delivered to the contracting authority in all cases for information only, the results of the individual processes are not known to the contracting authority. (Individual documents / letters Annex 20-20.4 ASR.) Milestone 1 Public procurement procedure for design-build contractor On 01/02/2017 the notice of PP publication was sent for publication in the OJ (Https://ted.europa.eu/udl?uri=TED:NOTICE:36648-2017:TEXT:SK:HTML) Milestone 3 Contract signed for design-build contractor The conclusion of the contract is the result of PP - an open competition. Identification of the successful candidate: Group: "JV ICM - VAHOSTAV - SK" • Leading member: ICM S.P.A., Vialle dell´ Industria No.42, 36100 Vicenza, Italian Republic • Member: VÁHOSTAV - SK, a.s., Priemyselná 6, 821 09 Bratislava, SR Contract price: 274 985 419.17 EUR without VAT The contract has been modified and subsequence 71,600-74,900 has been divided in two subsections 71,600-72,750 nad 72,750-74,900 in accordance to Grand Agreement (Annex 33.1 and 33.2) 16/09/2020 - announcement of the result of PP was published in OJ https://ted.europa.eu/udl?uri=TED:NOTICE:433622-2020:TEXT:SK:HTML&src=0 Milestone 4 Contract signed for Engineering/construction works supervision Based on the decision of ŽSR, the construction supervision within this project will be only internal. For this reason, these Milestones M2 and M4 are no longer relevant.

6. IMPLEMENTATION SCHEDULE, GOVERNANCE AND MONITORING, OTHER RELEVANT ADMINISTRATIVE PROVISIONS (GA II.23.1.1.k and l, or SESAR FPA II.23.1b.k and l)

6.1. In the first ASR, information on implementation schedule, such as critical path, key performance rates and risk analysis; in subsequent ASR, information on any modifications and, if applicable, on the progress of the implementation of the arrangements referred to in previous ASR. If there are changes in the Action timetable as compared to the latest planning (Grant Agreement or previous ASR), attach an updated Gantt chart.

Action's planned implementation schedule and planned technical progress (cumulated %) is enclosed in the table in Annex 1, implementation schedule of Activities is in Annex 1.2. The updated Gantt Chart is presented in Annex 6. The shifts in the deadlines for M3 were not due to ŽSR's inactivity but due to the application of objections and appeals in the PP process, which applicants may file in accordance with the law, whether the objections are justified or not. Another delay was caused by an inspection before the conclusion of the contract from the level of PPO. Therefore, in this case, it is not possible to apply mitigating measures from the position of ŽSR and in any way influence further delays. Within the framework of the mitigation measures, a close cooperation with the Czech Republic (SŽDC) is being established, whose project "Modernization of the Lanžhot-SK border railway line" financed by CEF 2016 (2016-CZ-TMC-0038-M) / SK state border - Devinska Nová Ves railway line. The established working groups continue to cooperate actively, their task is to coordinate both projects within the framework of CEF co-financing and cooperation.

Action's implementation technical progress (cumulated %)

|  | 2016 |  | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Action level | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR |
|  | 0 | 0 | 4 | 4 | 7 | 7 | 10 | 10 | 15 | 15 | 52 | 55 | 79 | 78 | 87 | 83 | 100 | 100 |
| Activity | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR | Previous ASR | Current ASR |
| 1 | 0 | 0 | 3 | 3 | 11 | 11 | 19 | 19 | 26 | 26 | 76 | 76 | 93 | 93 | 100 | 94 | 100 | 100 |
| 2 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | 30 | 30 | 70 | 70 | 80 | 80 | 90 | 90 | 100 | 100 |
| 3 | N/A | 0 | N/A | 0 | N/A | 0 | N/A | 0 | 0 | 0 | 30 | 30 | 70 | 70 | 80 | 80 | 100 | 100 |
| 4 | 0 | 0 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 100 | 100 |

All the activities and the Action will achieve 100% of technical progress by their actual end dates.

6.2. In the first ASR, information on governance and monitoring of the Action, such as organizational structure, internal coordination, communication and reporting, and decision making process; in subsequent ASR, information on any modifications and, if applicable, on the progress of the implementation of the arrangements referred to in previous ASR.

Within our organization the Investment department is liable for the implementation of the project. The overall management and the decision making process at the department is ensured by the director and two deputy directors – the deputy director for EU funds management and the deputy director for preparation and prices management. Preparation and implementation of the projects are carried out through the following sections at the Investment Department of ŽSR Directorate General Bratislava (internal designation Department O220), performing their main activities as follows: Section of procurement of the EU investments and projects • organizing the entire public procurement process (from establishing a working group for preparing tender documentation to disclosing documents after a contract has been entered into) • cooperating in ASR preparation Section of Proprietary Preparation of Investments • ensuring proprietary and legal settlement for the needs of investment construction, financed from internal resources, capital transfers and EU funds • representing Slovak Railways at expropriation proceedings as well as other proceedings related to proprietary and legal settlement of constructions Section of EU Constructions and Projects Preparation • complete management of project preparation constructions financed from internal resources, capital transfer and EU funds in the extent of the methodological procedure for investor activities in Slovak Railways • processing the subjects of procurement procedures for design contractors at all design documentation stages, including requirements for an authorized construction geodesist • preparing requests for conducting national expert inspection, intra-ministerial expert inspection, ministerial expert inspection • preparing notifications of construction start to relevant authorities • preparing requests for issuing approval protocols and expert assessments Section of EU programs: • managing of and responsibility for compliance with CEF implementation conditions • managing technical assistance of the EU programs • organizing and managing the end beneficiary process management • ensuring relation with state administration and the EC representing Slovak Railways at meetings with representatives of the EU, EC, MoTC SR and other organizations, responsibility for meeting conditions resulting from the Grant Agreement in the extent of activities of the Department, monitoring compliance with conditions, deadlines, deductions Section of EU Constructions and Projects Implementation • ensuring the control of compliance of the construction implementation with the approved project documentation, contractual conditions and the other valid legislation and the valid regulations of Slovak Railways, the Slovak Republic and the EC in the area of his scope of operation, preparation of materials in accordance with requirements and internal manuals • control of compliance of the performance of activity of construction supervision with the Contract on Provision of Services • participation in inspection days of the construction, technical inspections, hand-overs and take-overs, monitoring and assessing weekly, monthly and quarterly reports sent by the contractor or the building inspector, preparing documents for lockout activities and a train diagram board Section of financial management of EU projects • verification of the contractor´s invoices • management of payments to the contractors • financial reporting (requests for payment, financial statements, supporting financial documents, etc.) • preparation of financial plans • monitoring of financial progress • participation in meetings related to project implementation • cooperation on ASR preparation The given sections are being involved in communication process on regular daily basis including weekly meetings of the director, the deputy directors and the heads of the sections.

6.3. In the first ASR, information on other relevant administrative provisions, such as quality controls and audits; in subsequent ASR, information on any modifications and, if applicable, on the progress of the implementation of the arrangements referred to in previous ASR.

So far, no external audits related to the Action have been performed. • The nature of construction works, respectively. a wide range of specialized activities with a different focus (railway superstructure and substructure, electricity infrastructure, notification and security technology, telecommunications, etc.) require the cooperation of all interested departments of ŽSR. • The communication takes place in the form of official correspondence, working meetings at the construction management level (Contractor, during inspection days carried out at three-week intervals or as required by the Construction Supervision), as well as at ŽSR Directorate General level during operational workshops. In addition to the control days, the contractor's production meetings are held weekly. • The progress of the construction work is recorded in the weekly reports of the contractor, which are submitted to the Client each Monday. The contractor also submits a report on the progress of construction works in monthly reports. The reports evaluate the construction process in terms of time and substance fulfilment, current issues and possible risks that emerged during the actual implementation. Upon completion of the construction work, the construction supervisor issues Taking Over Certificate and submits Final Report. So far, no external audits related to the Action have been performed.

ANNEX: Financial information (GA II.23.1.1.d to f or SESAR FPA II.23.1b.d to f)

| CERTIFICATION OF THE MEMBER STATE* (applicable only for ASR and for beneficiaries established in the European Union) |  |
| --- | --- |
| Name |  |
| Position |  |
| Entity |  |
| Telephone Nº |  |
| E-mail |  |
| In compliance with Article II.23.1 (or SESAR FPA II.23.1b) of the GA, it is certified that the information provided by the following Beneficiary(ies) in the ASR is full, reliable and true. - Železnice Slovenskej republiky |  |
| Date and signature |  |
| Stamp (optional) |  |

* In line with the terms of Art. 22 of the CEF Regulation