## Asr info
CEF | Transport
Action Code | 2015-SK-TM-0207-M
Exercise Year | 2024
Version | 1
Actual Action Start Date
Actual Action End Date
A. Maximum EU contribution (Art. 3) | €37,569,269.60
B. Pre-financing rate (Art. 4.1.2) | 50%
C. Maximum pre-financing payment (Art. 4.1.2) (=B*A) | €18,784,634.80
D. Maximum ceiling for the sum of pre-financing and interim payments (Art 4.1.3) (=80%*A) | €30,055,415.68
E. Sum of Previous Pre-financing Payments | €16,655,757.50
F. Sum of Interim Payments | €0.00
G. Sum of pre-financing and interim payments (E+F) | €16,655,757.50

## Eligible costs (€)
Update of the indicative breakdown of estimated eligible costs of the Action 2015-SK-TM-0207-M (€)
|  |  | 2016 |  | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
| 1 Public procurement, authorisation procedures, detailed design and as-built documentation | 73.4
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3191458 | 3191458.5 | 1519736 | 1519736.1 | 5567753 |  | 2801053
Total for activity 1
| 2 Engineering/construction works supervision | 73.4
1 | Železnice Slovenskej republiky |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1216325 |  | 1216325
Total for activity 2
| 3 Construction works | 73.4
1 | Železnice Slovenskej republiky |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 4266242 | 4266242.33 | 16247366 |  | 14989672
Total for activity 3
| 4 Project management, communication/dissemination and financial audit | 73.4
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10024 | 10024 | 50000 |  | 108337
Total for activity 4
Total eligible costs
1 | Železnice Slovenskej republiky
Total cumulated eligible costs
1 | Železnice Slovenskej republiky

## Financing needs (€)
Financing needs of the Action 2015-SK-TM-0207-M (€)
|  |  | 2016 |  | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
1 Public procurement, authorisation procedures, detailed design and as-built documentation
1 | Železnice Slovenskej republiky
Totals for activity 1
2 Engineering/construction works supervision
1 | Železnice Slovenskej republiky
Totals for activity 2
3 Construction works
1 | Železnice Slovenskej republiky
Totals for activity 3
4 Project management, communication/dissemination and financial audit
1 | Železnice Slovenskej republiky
Totals for activity 4
Total financing needs
1 | Železnice Slovenskej republiky
Total cumulated financing needs
1 | Železnice Slovenskej republiky

## Progress Overview
Progress Overview of the Action 2015-SK-TM-0207-M (at accumulated level)
| 2016 |  |  | 2017 |  |  | 2018 |  |  | 2019 |  |  | 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024
| Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress
Activity name | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR
Activity 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 11 | 0 | 0 | 19 | 0 | 0 | 26 | 24 | 68 | 76 | 36 | 100 | 93 | 79 | 100 |  | 100 | 100
Activity 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 70 | 0 | 0 | 80 | 50 | 0 |  | 100 | 0
Activity 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 12 | 100 | 70 | 58 | 100 |  | 100 | 100
Activity 4 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 60 | 0 | 0 | 60 | 0 | 0 | 60 | 0 | 0 | 60 | 6 | 100 | 60 | 36 | 100 |  | 100 | 100
For the Action | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 36 | 0 | 18 | 100 | 0 | 63 | 100 | 0 | 100 | 100 | 0