## Asr info
CEF | Transport
Action Code | 2015-SK-TM-0207-M
Exercise Year | 2024
Version | 1
Actual Action Start Date | 2016-02-17
Actual Action End Date | 2024-12-31
A. Maximum EU contribution (Art. 3) | €37,569,269.60
B. Pre-financing rate (Art. 4.1.2) | 50%
C. Maximum pre-financing payment (Art. 4.1.2) (=B*A) | €18,784,634.80
D. Maximum ceiling for the sum of pre-financing and interim payments (Art 4.1.3) (=80%*A) | €30,055,415.68
E. Sum of Previous Pre-financing Payments | €16,655,757.50
F. Sum of Interim Payments | €0.00
G. Sum of pre-financing and interim payments (E+F) | €16,655,757.50

## Eligible costs (€)
Update of the indicative breakdown of estimated eligible costs of the Action 2015-SK-TM-0207-M (€)
|  |  | 2016 |  | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
| 1 Public procurement, authorisation procedures, detailed design and as-built documentation | 73.4
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3191458 | 3191458.5 | 1519736 | 1519736.1 | 5567753 | 2394954.99 | 2801053 | 5973850.41 | 13080000 | 13080000 | 0%
|  | Total for activity 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3191458 | 3191458.5 | 1519736 | 1519736.1 | 5567753 | 2394954.99 | 2801053 | 5973850.41 | 13080000 | 13080000 | 0%
| 2 Engineering/construction works supervision | 73.4
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1216325 | 0 | 1216325 | 2432650 | 2432650 | 2432650 | 0%
|  | Total for activity 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1216325 | 0 | 1216325 | 2432650 | 2432650 | 2432650 | 0%
| 3 Construction works | 73.4
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4266242 | 4266242.33 | 16247366 | 7436732.01 | 14989672 | 23800305.66 | 35503280 | 35503280 | 0%
|  | Total for activity 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4266242 | 4266242.33 | 16247366 | 7436732.01 | 14989672 | 23800305.66 | 35503280 | 35503280 | 0%
| 4 Project management, communication/dissemination and financial audit | 73.4
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10024 | 10024 | 50000 | 2320 | 108337 | 156017 | 168361 | 168361 | 0%
|  | Total for activity 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10024 | 10024 | 50000 | 2320 | 108337 | 156017 | 168361 | 168361 | 0%
| Total eligible costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3191458 | 3191458.5 | 5796002 | 5796002.43 | 23081444 | 9834007 | 19115387 | 32362823.07 | 51184291 | 51184291 | 0%
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3191458 | 3191458.5 | 5796002 | 5796002.43 | 23081444 | 9834007 | 19115387 | 32362823.07 | 51184291 | 51184291 | 0%
| Total cumulated eligible costs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3191458 | 3191458.5 | 8987460 | 8987460.93 | 32068904 | 18821467.93 | 51184291 | 51184291 | 51184291 | 51184291 | 0%
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3191458 | 3191458.5 | 8987460 | 8987460.93 | 32068904 | 18821467.93 | 51184291 | 51184291 | 51184291 | 51184291 | 0%

## Financing needs (€)
Financing needs of the Action 2015-SK-TM-0207-M (€)
|  |  | 2016 |  | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | 2024 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
| 1 Public procurement, authorisation procedures, detailed design and as-built documentation | 73.4
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2342530.172 | 2342530.539 | 1115486.224 | 1115486.2974 | 4086730.702 | 1757896.9627 | 2055972.902 | 4384806.2009 | 9600720 | 9600720 | 0%
|  | Totals for activity 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2342530.172 | 2342530.539 | 1115486.224 | 1115486.2974 | 4086730.702 | 1757896.9627 | 2055972.902 | 4384806.2009 | 9600720 | 9600720 | 0%
| 2 Engineering/construction works supervision | 73.4
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 892782.55 | 0 | 892782.55 | 1785565.1 | 1785565.1 | 1785565.1 | 0%
|  | Totals for activity 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 892782.55 | 0 | 892782.55 | 1785565.1 | 1785565.1 | 1785565.1 | 0%
| 3 Construction works | 73.4
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3131421.628 | 3131421.8702 | 11925566.644 | 5458561.2953 | 11002419.248 | 17469424.3544 | 26059407.52 | 26059407.52 | 0%
|  | Totals for activity 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3131421.628 | 3131421.8702 | 11925566.644 | 5458561.2953 | 11002419.248 | 17469424.3544 | 26059407.52 | 26059407.52 | 0%
| 4 Project management, communication/dissemination and financial audit | 73.4
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7357.616 | 7357.616 | 36700 | 1702.88 | 79519.358 | 114516.478 | 123576.974 | 123576.974 | 0%
|  | Totals for activity 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7357.616 | 7357.616 | 36700 | 1702.88 | 79519.358 | 114516.478 | 123576.974 | 123576.974 | 0%
| Total financing needs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2342530.172 | 2342530.539 | 4254265.468 | 4254265.7836 | 16941779.896 | 7218161.138 | 14030694.058 | 23754312.1334 | 37569269.594 | 37569269.594 | 0%
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2342530.172 | 2342530.539 | 4254265.468 | 4254265.7836 | 16941779.896 | 7218161.138 | 14030694.058 | 23754312.1334 | 37569269.594 | 37569269.594 | 0%
| Total cumulated financing needs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2342530.172 | 2342530.539 | 6596795.64 | 6596796.3226 | 23538575.536 | 13814957.4606 | 37569269.594 | 37569269.594 | 37569269.594 | 37569269.594 | 0%
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2342530.172 | 2342530.539 | 6596795.64 | 6596796.3226 | 23538575.536 | 13814957.4606 | 37569269.594 | 37569269.594 | 37569269.594 | 37569269.594 | 0%

## Progress Overview
Progress Overview of the Action 2015-SK-TM-0207-M (at accumulated level)
| 2016 |  |  | 2017 |  |  | 2018 |  |  | 2019 |  |  | 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023 |  |  | 2024
| Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress
Activity name | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR
Activity 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 11 | 0 | 0 | 19 | 0 | 0 | 26 | 24 | 100 | 76 | 36 | 100 | 93 | 79 | 100 | 94 | 100 | 100 | 100
Activity 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 70 | 0 | 0 | 80 | 50 | 0 | 90 | 100 | 0 | 100
Activity 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 12 | 0 | 70 | 58 | 0 | 80 | 100 | 0 | 100
Activity 4 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 60 | 0 | 0 | 60 | 0 | 0 | 60 | 0 | 0 | 60 | 6 | 0 | 60 | 36 | 0 | 60 | 100 | 0 | 100
For the Action | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 100 | 0 | 18 | 100 | 0 | 63 | 100 | 0 | 100 | 100 | 0