## Draft
Places and deadlines of performance
Subject-matter of the contract: Helicopter technology - medium-weight helicopters
Business name or name of the tenderer: Address or registered office of the tenderer:
Item of requirement | Item name | Place of performance | Deadline of performance from the effective date of the contract | Note
1. | Helicopter | Bratislava | 27 months
1.3.1 | Flight crew training | The Seller’s training centre or an approved training organisation | Completion of required training within three to one month prior to helicopter delivery
1.3.2 | Training of aircraft maintenance technicians | The Seller’s training centre or an approved training organisation | Completion of required training within twelve to six months prior to helicopter delivery
1.4.1. | Documentation in the prescribed scope | Documentation in paper form delivered in Bratislava; Documentation in electronic form made available online on the Seller’s infrastructure | Documentation in paper form delivered together with the helicopter; Documentation in electronic form made available online at least six months before delivery of the helicopter
Optional equipment and related services
2.1. | On-board hoist equipment, winch (HHO), with a minimum lifting capacity of 250 kg (removable components). | Bratislava | With the helicopter, in the case of a separate contract, delivery within 12 months from the date of order
2.2 | Removable parts of fast roping system | Bratislava | With the helicopter, in the case of a separate contract, delivery within 12 months from the date of order
2.3 | Removable parts of rappelling system | Bratislava | With the helicopter, in the case of a separate contract, delivery within 12 months from the date of order
2.4. | Cargo hook with a minimum load capacity of 1,500 kg (removable parts). | Bratislava | With the helicopter, in the case of a separate contract, delivery within 12 months from the date of order
2.5. | Searchlight and its controls (removable parts). | Bratislava | With the helicopter, in the case of a separate contract, delivery within 12 months from the date of order
2.6. | Electro-optical system (EOS) (removable parts). | Bratislava | With the helicopter, in the case of a separate contract, delivery within 12 months from the date of order
2.7. | Electro-optical system operator station (removable parts) | Bratislava | With the helicopter, in the case of a separate contract, delivery within 12 months from the date of order
2.8. | Air-to-ground video downlink system | Bratislava | With the helicopter
2.9. | Diagnostic equipment and software for Cockpit Voice and Flight Data Recorder (CVFDR) | Bratislava | With the helicopter, in the case of a separate contract, delivery within 3 months from the date of order
2.10.1. | Wire strike protection system – wire cutter. | Bratislava | With the helicopter, in the case of a separate contract, delivery within 12 months from the date of order
2.10.2.1. | External sling monitoring system - camera | Bratislava | With the helicopter
2.10.2.2. | External sling monitoring system - rearview mirror | Bratislava | With the helicopter
2.10.3. | Traffic collision avoidance system (e.g., TCAS, TIS, or others) | Bratislava | With the helicopter
2.10.4. | Ground proximity warning system (GPWS/EGPWS/HTAWS or equivalent) | Bratislava | With the helicopter
2.10.5 | Weather radar | Bratislava | With the helicopter
2.10.6. | Flotation system. | Bratislava | With the helicopter, in the case of a separate contract, delivery within 6 months from the date of order
2.10.7. | Automatic Identification System (AIS) (vessel identification and information). | Bratislava | With the helicopter
2.10.8. | System for detecting and locating targets during emergency transmissions (direction finder). | Bratislava | With the helicopter
2.10.9. | Marine radio station (30–512 MHz). | Bratislava | With the helicopter
2.10.10. | A flight tracking system. | Bratislava | With the helicopter
2.10.11. | Equipment for offshore flights. | Bratislava | With the helicopter
2.10.12. | Additional equipment for flights in harsh environments. | Bratislava | With the helicopter
3.1. | Spare parts support programme based on hourly rate for a period of 5 years of operation | Bratislava | With the helicopter
3.2.1. | A terrain database and a database of obstacles and airports including updates for a period of 4 years. | Bratislava | With the helicopter
3.2.2. | Navigation database covering the EU including updates for a period of 4 years. | Bratislava | With the helicopter
3.2.3. | Data for a moving map covering the Slovak Republic at street address level including updates for a period of 4 years. | Bratislava | With the helicopter
Non-compulsory equipment (if applicable)
4.1 | An additional system to protect engines against the ingestion of solid particles. | Bratislava | With the helicopter, in the case of a separate contract, delivery within 12 months
4.2.1. | Additional fuel tanks - pre-installation (fixed components) | Bratislava | With the helicopter
4.2.2. | Additional fuel tanks (removable components) | Bratislava | With the helicopter, in the case of a separate contract, delivery within 12 months
4.3.1. | Lightweight removable seats - pre-installation (fixed components) | Bratislava | With the helicopter
4.3.2. | Lightweight removable seats (removable components) | Bratislava | With the helicopter, in the case of a separate contract, delivery within 12 months
4.4. | Pre-installation for a handheld radio station. | Bratislava | With the helicopter
4.5. | Holders for illuminated navigation charts or iPads (universal) in the cockpit. | Bratislava | With the helicopter
4.6. | A system to prevent the undercarriage from sinking into the ground (“bear paws” or equivalent). | Bratislava | With the helicopter, in the case of a separate contract, delivery within 12 months
4.7.1. | USB-C ports for charging mobile devices in the flight crew compartment. | Bratislava | With the helicopter
4.7.2. | USB-C ports for charging mobile devices in the passenger compartment. | Bratislava | With the helicopter